## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-ME-DS-0001
Document Title: DETAILED D/SH FOR COMPRESSOR (API-618) WITH CERTIFICATES |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-SVTR-HY-0032 |  |  | Transmital Date:2023/12/24
[5 empty] | CRS No:PEDCO-CRS- BK-GCS-HY-120-ME-DS-0001_V02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments :
1 | فرمت مدرك بهم ريخته مي باشد.اصلاح گردد. |  | BK-SUR-ENG-MEC-02-08610 | 2023-10-15 | اصلاح شد.
2 | با توجه به Replysheet دريافتي واضح است كه مدرك از سوي آن پيمانكار مورد بررسي قرار نگرفته و پاسخ سازنده (خطاب به شركت هيرگان) بدون بررسي به پتروايران ارسال شده.لازم است پس از بررسي ، نسبت به ارائه اطلاعات لازم به سازنده جهت اعمال نظرات(براي نمونه آيتم اول نظرات بخش فرايند) بر روي اين مدرك ، اقدام گردد. |  | BK-SUR-ENG-MEC-02-08610 | 2023-10-15 | موارد به نحو مقتضی اعمال گردید
3 | با توجه موارد بالا مدرك قابل بررسي نبوده و همچنين به دليل عدم ارسال اين مدرك به ذينفع اصلي پروژه ، لازم است پس از اعمال نظرات نسبت به جايگزيني اين مدرك بر روي همين ترانسميتال با همين ويرايش اقدام شود. |  | BK-SUR-ENG-MEC-02-08610 | 2023-10-15 | مطابق این بند، مدرک جدید با همان رویژن قبلی ارسال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 10/14/2023 |  |  |  |  | Date: