## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-EL-DS-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-0044 |  |  | Transmital Date: 2023/11/25
Document Title: D/SH (W/CURVE, DRAWING & CERTIFICATE) FOR COMPRESSOR MAIN MOTOR |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS- BK-GCS-HY-120-EL-DS-0001_V01 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/6836 | 1402/01/09 | نقطه نظرات به نحو مقتضی اعمال گردید. |  |  | Noted Closed.
2 | گواهينامه ارائه شده مربوط به موتور هاي تيپ YBX3-315 است كه ارتباطي با موتور YBXKK-800-14 مذكور در ديتا شيت ندارد وبايستي با گواهينامه درست جايگزين گردد. |  | BK-SUR-ENG-MEC-02-08825 | 2023-11-26
3 | گواهينامه شماره SHEx/SHEx23.3195X كه در رديف شماره 25 ديتا شيت به آن اشاره شده است ارائه گردد |  | BK-SUR-ENG-MEC-02-08825 | 2023-11-26
4 | در رديف هاي 71 و 72 نام سلزنده ياتاقان ها ذكر گردد |  | BK-SUR-ENG-MEC-02-08825 | 2023-11-26
5 | مداركي كه در عنوان مدرك قيد شده اند شامل نقشه ها و نمودارها (drawing and curves)‌ بايستي در پيوست ديتا شيت ارسال شوند |  | BK-SUR-ENG-MEC-02-08825 | 2023-11-26
6 | كاتالوگ موتور ارسال گردد و موتور پيشنهادي بر روي كاتالوگ مارك گردد. |  | BK-SUR-ENG-MEC-02-08825 | 2023-11-26
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Me.Karimi Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 11/26/2023 |  |  |  |  | Date: