## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-IN-LI-0005_V01
Document Title: I/O LIST |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO--SVTR-HY-0010 |  |  | Transmital Date:2024/01/30
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-IN-LI-0005_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 | مدارک مرجع ذکر گردد. |  | 02/2294/162120 | 1402/04/26 | مدرک مرجع، P&ID است که در ستون مربوطه برای هر آیتم ذکر شده است.
2 | در ستون Tag Number:تجهیرات مربوط به هر ردیف کمپرسور در ردیف جداگانه ذکر شود و از آوردن عبارت A/B/C بصورت مشترک خودداری شود . این موضوع برای دیگر ستونها و ردیفها نیز رعایت گردد. |  | 02/2294/162120 | 1402/04/26 | اعمال گردید.
3 | در ستونLCP,UCp ,System هر ردیف کمپرسور بصورت مشخص نمایش داده شود. |  | 02/2294/162120 | 1402/04/26 | مورد تایید است.
4 | این مدرک پس از نهایی سازی نقشه های P&ID و دیگر مدارک سازنده بروز رسانی گردد. |  | 02/2294/162120 | 1402/04/26 | براساس آخرین P&ID به روز شده است.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: