## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-GE-DW-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: NAME PLATE DRAWING |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0009 |  |  | Transmital Date: 2024/02/07
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-GE-DW-0001-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به متفاوت بودن مشخصات سيلندرهاي مرحله اول و دوم ، براي هر سيلندر NAME PLATE جداگانه ارائه گردد. |  | BK-SUR-ENG-MEC-02-08063 | 2023-07-09 | Havayar Reply: Confirmed
2 | مطابق با بند 6.16.5 استاندارد API 618 موارد زير به NAME PLAT اضافه گردد :‌ 1- MAWP 2- Cold piston end-clearance setting for each end |  | BK-SUR-ENG-MEC-02-08063 | 2023-07-09 | Havayar Reply: 1- Noted 2- Confirmed Will be issued after assembly and test
3 | مطابق با بند 6.16.4 استاندارد API 618 لازم است براي Frame هر رديف NAME PLATE جداگانه ارائه گردد.همچنين الزامات بند 6.16.6 جهت موتورهاي القايي رعايت گردد. |  | BK-SUR-ENG-MEC-02-08063 | 2023-07-09 | Havayar Reply: Noted
4 | الزامات بند 7.9.5.1.21 استاندارد API 618 در خصوص PULSATION SUPPRESSION مد نظر قرار گيرد. |  | BK-SUR-ENG-MEC-02-08063 | 2023-07-09 | Havayar Reply: Confirmed. The nameplate for the Suppression device will be issued after manufacturing.
5 | نظرات ذينفع اصلي پروژه متعاقبا ارسال مي گردد. |  | BK-SUR-ENG-MEC-02-08063 | 2023-07-09 | Havayar Reply: Please clarify.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 7/11/2023 |  |  |  |  | Date: