## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-PF-0001-V02 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0043 |  |  | Transmital Date: 2023/11/12
Document Title: PROCESS FLOW DIAGRAMS |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-PR-PF-0001-V02 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مدرک ارائه شده توسط سازنده، دمای 153 درجه سانتی گراد برای خروجی کمپرسور مرحله دوم در نظر گرفته شده است که این مورد بر خلاف بند 6.5.1 استاندارد API-618 و SPEC پروژه می باشد. شایان ذکر است که این افزایش دما صرفا در ویرایش قبلی PFD مطرح شده و در هیچ یک از مدارک پیشین ارائه شده توسط سازنده از جمله داده برگ کمپرسور به آن اشاره ای نشده است. همچنین پاسخ ارائه شده توسط سازنده به نظر مطرح شده در دراین مورد، فاقد هر گونه استدلال فنی جهت توجیه دلیل این افزایش دما می باشد. |  | BK-SUR-ENG-MEC-02-08819 | 2023-11-25
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 11/25/2023 |  |  |  |  | Date: