## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-QC-PR-0007-V00 |  |  |  |  | EPC Contractor Tr. No: |  |  | Transmital Date:
Document Title: Bare-block MRT Procedure |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0068 |  |  | Transmital Date: 2024/04/17
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-QC-PR-0007-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (Vendor) |  |  | Client Conclusion
1 |  |  | BK-SUR-ENG-QAC-02-09197 | 2024-04-07 | Noted. This project is a project to which API 618 is applied. API 618 5th is specified in Test Condition Section.
2 |  |  | BK-SUR-ENG-QAC-02-09197 | 2024-04-07 | This project is a project in which only the bare body to which API 618 is applied is manufactured and the test run is conducted through a Mechanical Running Test (Bare Body_No Load Test). Therefore, this comment is not applicable.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 13-Nov-23 |  |  |  |  | Date: