## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-PF-0001-V03 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0067 |  |  | Transmital Date: 2024/03/10
Document Title: PROCESS FLOW DIAGRAMS |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-HY-0067 |  |  | Transmital Date: 2024/03/10
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-PR-PF-0001_V03 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دمای 153 درجه سانتی گراد برای حالت کارکرد زمستان در جدول H&M اصلاح شده ولی همچنان در توضیحات C-2102 و AE-2102 این دما اصلاح نشده است. |  | BK-SUR-ENG-MEC-02-09152 | 2024-03-17
2 | اصلاح دمای خروجی کمپرسور مرحله دوم از 153 درجه به 149 درجه قابل قبول می باشد اما چگونگی این کاهش دما در حالیکه سایر پارامترها به ویژه دمای خروجی کمپرسور در فصل تابستان بدون تغییر باقی مانده دارای ابهام می باشد. |  | BK-SUR-ENG-MEC-02-09152 | 2024-03-17
3 | دمای خروجی از کمپرسور مرحله دوم ( درحالت کارکرد زمستان) در آخرین ویرایش دیتاشیت 150 درجه سانتی گراد می باشد. ضروریست این تناقض برطرف گردد. |  | BK-SUR-ENG-MEC-02-09152 | 2024-03-17
4 | عبارت NNF بر روی خطوط Drain خروجی از Scrubber مراحل اول و دوم درج گردد. |  | BK-SUR-ENG-MEC-02-09152 | 2024-03-17
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 3/17/2024 |  |  |  |  | Date: