## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-IN-LI-0001 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0030 |  |  | Transmital Date: 2023/10/07
Document Title: CAUSE & EFFECT CHARTS LIST |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-IN-LI-0001-V01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بررسی وضعیت Lub Oil Cooler و Heater سیستم Lubricator در شرایط Start / Stop و Emergency Shutdown اضافه گردد. آیا دو تجهیز مذکور در شرایط Normal Operation بصورت دائم در سرویس می باشند؟ درخصوص Heater سیستم روغن Lubricator آیا نیاز به سیستم کنترل دمایی نمی باشد تا درصورت بالارفتن دما این Heater خاموش گردد؟ |  | BK-SUR-ENG-MEC-02-08614 | 2023-10-17
2 | آیا منظور از note-3 این است که امکان compressor start از UCP وجود دارد؟ |  | BK-SUR-ENG-MEC-02-08614 | 2023-10-17
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Oct 2023 |  |  |  |  | Date: