## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DW-0007
Document Title:HOOK UP DRAWING |  |  |  |  | PEDCO Tr. No.::BK-HD-PEDCO-SVTR-HY-0070 |  |  | Transmital Date: 2024/06/08
[5 empty] | CRS No: NISOC-CRS- BK-GCS-HY-120-IN-DW-0007-V0 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 |  |  | 03/2291/48549 | 1403/02/10 | 1- با توجه به نمونه فایل ارسال شده از جانب کارفرما، صرفا قطعات مربوط به ابزاردقیق در جدول در ظر گرفته شده است و در رویژن جدید مدرک قطعات پایپینگ از جدول حذف گردیده است. 2- اصلاح گردید. 3- اعمال گردید. 4- اعمال گردید. 5-اصلاح گردید. 6- اصلاح گردید. 7-اعمال گردید. 8- اعمال گردید.
2
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: