## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DW-0003-V00
Document Title: JB TERMINATION DRAWING |  |  |  |  | PEDCO Tr. No.BK-HD-PEDCO-SVTR-HY-0051 |  |  | Transmital Date:2024/07/09
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-IN-DW-0003_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 |  |  | 02/2294/444836 | 1402/11/01 | با توجه به جلسه Hazop مدرک اصلاح شده است.
2 |  |  | 02/2294/444836 | 1402/11/01 | با توجه به جلسه Hazop مدرک اصلاح شده است.
3 |  |  | 02/2294/444836 | 1402/11/01 | تمامی سیگنال های موجود در مدرک JB به UCP می رود. که مشخص شده است.
4 |  |  | 02/2294/444836 | 1402/11/01 | تمامی سیگنال های موجود در مدرک JB به از فیلد به UCP می رود. سیگنال های ارتباطی UCP و IRP به این مدرک مرتبط نمی باشد.
5 |  |  | 02/2294/444836 | 1402/11/01 | مشاهده شد.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: