## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-QC-PR-0002-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Tr.Letter Date:
Document Title: WPS & PQR |  |  |  |  | Tr. No.: BK-HD-PEDCO-SVTR-HY-0047 |  |  | Transmital Date:2024/10/01
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-QC-PR-0002-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در قسمت Reference Standard، استاندارد API 618 و NACE MR 0175/ISO15156 و در فرم WPS اسامي كليه استانداردهاي مرجع ذكر گردد. |  |  | 12 -Dec-2023 | استاندارد API 618 و NACE MR 0175/ISO15156 اضافه شد.در فرم wps به استانداردها رفرنس داده شد.
2 | فرمت PQR ارائه نشده است. |  |  | 12 -Dec-2023 | مدرک در نسخه بعدی کاملا تغییر کرده است و تمامی نظرات اعمال شده است.
3 | براي PQR هاي ارائه شده نتايج تست سختي سنجي ارائه نشده است. |  |  | 12 -Dec-2023 | مدرک در نسخه بعدی کاملا تغییر کرده است و تمامی نظرات اعمال شده است.
4 | ساير نقطه نظرات در مدرك درج گرديده است. |  |  | 12 -Dec-2023 | مدرک در نسخه بعدی کاملا تغییر کرده است و تمامی نظرات اعمال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: Havayar | Signature
| Date: 12-Dec-2023 |  |  |  |  | 2024-08-19