## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-PF-0001 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: PROCESS FLOW DIAGRAMS (PFD) |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-HY-0077 |  |  | Transmital Date: 2024/10/16
[5 empty] | CRS No: PECO- CRS-BK-GCS-HY-120-PR-PF-0001_V04 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علیرغم عدم ارائه پاسخ مناسب و قانع کننده به نظر شماره 2 در CRS ویرایش پیشین این مدرک، در این مقطع نظری مطرح نمی باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای فنی و مالی-قراردادی پیمانکار و سازنده، بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار و سازنده، اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار می باشد. |  | BK-SUR-ENG-MEC-03-09356 | 2024-06-11 | ضمن تشکر از بررسی مجدد مدرک، این مورد مد نظر قرار گرفته شده است.
2 | با توجه به عدم ارائه پاسخ مناسب به نظرات کارفرما در خصوص استعلام نسبت تراکم و دمای خروجی بهینه از سازنده کمپرسورها که در نامه های شماره 391934 مورخ 1402/9/27 و 29974 مورخ 1403/01/29 توسط ایشان اعلام شده است، تا زمان ارسال مستندات مناسب از سوی سازنده و پیمانکار، این مدرک جهت بررسی به ذینفع اصلی پروژه ارسال نمی گردد. |  | BK-SUR-ENG-MEC-03-09356 | 2024-06-11 | با توجه به ارائه توضیحات در جلسات پیشین و پاسخ مورد قبل، به نظر این مورد نیز مرتفع شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 06/11/2024 |  |  |  |  | Date: