## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-ME-DW-0001-V02 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: COMPRESSOR PACKAGE GENERAL ARRANGEMENT DRAWING |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-HY-0088 |  |  | Transmital Date: 2024/10/26
[5 empty] | CRS No: CRS-PEDCO-BK-GCS-HY-120-ME-DW-0001-V02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments :
1 | Pulsation study , approach 3 shall be supplied by vendor |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
2 | Rotation arrows shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Will be added in next revision
3 | Flywheel data shall be added (Power, RPM, Dimention and …) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please note that Flywheel data is Vendor design Data and we cannt issue that. Power, RPM and package overall dimension will be issued.
4 | shaft end dimentional and tolerances for the coupling shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | It is issued in relative document
5 | Barring device data shall be added a DWG shall be shown here |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | It will issued in IOM
6 | Earthing lug shall be specified and shown. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
7 | TP numbers shall be revised.for example TP-01-A/B/C |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
8 | lifting lug calculation shall be provided |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please note that lifting lug calculation data is Vendor design Data and we cannt issue that.
9 | Add TP number |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
10 | views name shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
11 | Coupling Manufacturer & Detail Data shall be added (As per API 618 : the manufacturer,Size and type of coupling and the location of guard and their coverage shall be added) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document.
12 | Equipments Tag NO. shall be added (Table of compressor specifications and equipments include Tag NO. , Type , Services , Operating and Design data and ... shall be added) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
13 | Joints shall be reviesd |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
14 | add Compressor , motor , lube oil system , cooling system & ... specification tables include its Details and reference standard. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
15 | reference document shall be added |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
16 | in according to MOM (1401/12/16) , Lube oil system , cooling system , ElectroMotor & pulsation suppression device detail drawing and final pressure code calculation shall be added. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
17 | Table of weights shall be added and specified maintenance heaviest weight (Empty , Fabricated , Total , Operating and maintenance heaviest weight) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Overall weight, maximum maintenace weight and major part weight will be added
18 | Maximum allowable nozzle load shall be specified and shown on a table |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
19 | Maintenace area shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted.
20 | all piping supports shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
21 | for the safety issue, all the nozzles and parts shall be within the skids |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Clarify please
22 | Anchor bolts pocket and details shall be specified & shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
23 | Mounting plate shall be shown separately with its details |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please clarify
24 | Foundation plan shall be added |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
25 | All the material shall be list based on ASTM code in a table. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
26 | vendor shall specified Distance between Lifting lugs |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
27 | DBSE shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
28 | Elevation of all TP shall be shown from its center line |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
29 | Maximum Elevation shall be shown, if there is any ladder or plat form is necessary , vendor shall specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Note.
30 | Codes and standards for pressure parts shall be specified in notes |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document
31 | lifting lug details shall be provided for suppressors |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD
Piping comments:
1 | با توجه به عدم تطابق محل اتصال پايپينگ ورودي و خروجي مراحل 1 و 2 كمپرسور با مدل سه بعدي ايستگاه تقويت فشار گاز مورد تأييد نمي باشد. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا در این رابطه شفاف سازی نمائید
Civil and Structure comments :
1 | فايل پيوست مشاهده گردد. ( كامنت هاي كمپرسور) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا در رابطه با فایل پیوست شفاف سازی نمائید. به کامنت های Civil بیان شده پاسخ داده شده است
Instrument comments :
1 | 1- محل قرار گیری نازل های ابزاردقیق مشخص نمی باشد. 2- محل قرار گیری سنسورهای Vibration و دما مشخص نمی باشد. 3- موقعیت قرارگیری LCP و تمامی جعبه تقسیم ها نشان داده شود. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا ویرایش جدید را مشاهده فرمائید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 7/22/2024 |  |  |  |  | Date: