## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-LI-0001_V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: UTILITY CONSUMPTION LIST |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0013 |  |  | Transmital Date:2024/11/26
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-PR-LI-0001_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص میزان مصرف و مشخصات Cooling Water اطلاعاتی ارائه نشده است. |  | BK-SUR-ENG-MEC-02-08115 | 2023-07-19 | درج خواهد شد.
2 | در خصوص میزان مصرف و مشخصات Lube oil اطلاعاتی ارائه نشده است. |  | BK-SUR-ENG-MEC-02-08115 | 2023-07-19 | در مدرک Lubricant List با شماره BK-GCS-HY-120-ME-LI -0001 درج شده است.
3 | عدد مصرف نیتروژن برای Purge درج شده است و برای مصارف و مشخصات Seal gas اطلاعاتی ارائه نشده است. |  | BK-SUR-ENG-MEC-02-08115 | 2023-07-19 | در کمپرسور رفت و برگشتی، نیتروژن تنها برای Purge Gas مورد استفاده قرار می گیرد و بحث Sealing مطرح نمی گردد.
4 | میزان توان الکتریکی مصرفی می بایست در مدرک درج گردد. |  | BK-SUR-ENG-MEC-02-08115 | 2023-07-19 | در مدرک ELECTRICAL/UPS CONSUMPTION LOAD LIST با شماره BK-GCS-HY-120-EL-LI-0001 درج شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 19 Jul 2023 |  |  |  |  | Date: