## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-QC-PR-0007-V01 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0072 |  |  | Transmital Date: 2025/01/26
Document Title: Bare-Block MRT Procedure |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-QC-PR-0007_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Document no. does not match with VPIS |  |  | 2024-04-07 |  |  |  | Closed.
2 | All pre-requirements before FAT to be outlined in the procedure |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
3 | According to API 618, Para. 8.3.3 & 8.3.3.1 : All compressors, drivers and gear units shall be shop tested in accordance with the vendor's standard. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
4 | Reference codes, standards and specifications shall be specified in the procedure. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
5 | Pre-tests, intermediate stops and inspections which are required prior to the 4-hour continuous test shall be defined in the test procedure. Prior to a witness mechanical running or performance test, confirmation of the successful completion of the applicable preliminary test shall be provided. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
6 | Before recording the parameters, compressor brings to the rated speed and then runs for 30 minutes to get lube oil temprature , viscosity, bearing temprature and vibration ampilitudes stabilized.After operating parameters stabilized, the test technician records the parameters in each 15 minutes. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
7 | There is a conflict between 2.1 and 3.2 paragraph for tolerance of specified number of revolutions. |  |  | 2024-04-07 | Please note that: MRT is done in Korea with electrical network frequecny 60 Hz.
8 | Below items shall be added and measured : 1- inlet/outlet oil temprature 2- inlet/outlet oil pressure 3- oil filter diffrential pressure 4- oil viscosity 5- speed 6- main bearing and packing temperature 7- Noise Level 8-Piston Rod Temprature(During and immediately after test) 9- Cylenderes external temprature(During and immediately after test) 10- oil leakage on oil scraper rings 11- cylinder and frame vibration 12- Piston rod runout 13-Power consumption |  |  | 2024-04-07 | Check MRT report.
9 | All tested parameters shall be in ranges that specified in Alarm and setpoints Document(Approved Document) and also in according to api 618. Range of operating values and tolerances for these parameters shall be specified in the procedure |  |  | 2024-04-07 | Please note that MRT is done.Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
10 | Vibration shall be measured for compressor components such as compressor skid, cylinder, distance pieces, crank case and cylinder flange pressure pulsation. Location of vibration measuring devices shall be in according to ISO 20816-8 , par. 4.3 |  |  | 2024-04-07 | Please check MRT report
11 | Location of measurement tools for Temperature, Speed, Vibration, Pressure, Viscosity, Shaft and Piston Run Out, etc. to be specified |  |  | 2024-04-07 | Please check MRT report |  |  | Open
12 | If replacement or modification of bearings, or dismantling to replace or modify other parts are required to correct mechanical or performance deficiencies, the initial test shall be deemed not acceptable and the final shop tests shall be run after these deficiencies are corrected. Additional dismantling is required if evidence of malfunction is found. The purchaser shall specify if dismantling for inspection (other than that required by evidence of malfunctioning during testing) is required |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure. |  |  | Open
13 | A bar-over test of the frame and cylinders shall be made in the vendor’s shop to verify piston end clearances and rod runout. The final bar-over test shall be performed with all compressor cylinder valves in place to demonstrate no piston interference. Vertical and horizontal piston-rod runout (cold) at packing case flanges shall also be measured during this test. Bar-over test results shall become a part of the purchaser’s records The test shall be done during the assembly and also after the mechanical running test which is called final bar over test. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
14 | Inspection format (including acceptance criteria and measured value) to be attached to procedure |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
15 | Calibration of inspection and testing tools to be discussed |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
16 | For other comments, please find attached file. |  |  | 2024-04-07 | Due to NISOC acceptance on MRT procedure document and also successful MRT with confirmation of all clients (include EPC contractor, general contractor and owner), please drop the comment. MRT has been dove according to API 618 and approved procedure.
17 | Document title. does not match with VPIS |  |  | 2024-04-29 | This document shall be added to VPIS according to previous discussion. VPIS will be modified.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: