## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-EL-DS-0002-V01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-SVTR-HY-0031 |  |  | Transmital Date: 2025/02/01
Document Title: DATASHEET (W/DRAWING) FOR AUXILIARY MOTORS |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0031 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-HY-120-EL-DS-0002_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 | ` |  | 03/2294/124967 | 1403/04/03 | 1- فایل Native برای موتورهای Aux. قابل دریافت نیست ولی drawingشان ارائه شده است. 2- مورد تأیید است. 3- تایپ الکترو موتورها مشخص گردیده است و از آنجا که محصول روتین نیستند کاتالوگی ندارند و صرفاً دیتا شیت به همراه drawing ارائه شده است. 4- سیم‌پیچها دارای شش سر هستند. 5- الکتروموتورها دارای دو کپ مجزا در طرفین استاتور می‌باشند.
2 | ` |  | 03/2294/124967 | 1403/04/03 | 6- ملاحظه گردید. 7- در فاینال بوک ارائه خواهد شد. 8- قطعات یدکی مطابق مدرک SPARE PART LIST (BK-GCS-HY-120-GE-LI-0002) ارائه خواهد شد. 9- بعد از تأمین موتور به همراه موتور، routine test report نیز دریافت خواهد شد. 10- ملاحظه شد.
3 |  |  | 03/2294/124967 | 1403/04/03 | 11- ملاحظه و اصلاح گردید. 12- Instruction manual ارائه شده مربوط به محصولات روتین است و از آنجا که موتور ارائه شده از type خاص است موارد درج شده طبق دیتا شیت برای این موتور صحیح می باشد. 13- تایپ الکترو موتورهای ارائه شده از نوع خاص هستند و از آنجا که محصول روتین نیستند کاتالوگی ندارند و صرفاً دیتا شیت به همراه drawing و نمودارها و گواهی ضد انفجار ارائه شده است. 14- از آنجا که Instruction manual در خواست شده بود، تنها برای محصولات روتین این دستور العمل موجود می باشد و برای این موتور خاص،Instruction manual ندارد. 15- در این رویژن شماره drawing با گواهینامه ATEX مطابقت دارد.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: 1403.07.07 |  |  |  |  | Date: