## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DW-0002-V00
Document Title: CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING |  |  |  |  | PEDCO Tr. No.:: BK-HD-PEDCO-SVTR-HY-0066 |  |  | Transmital Date:2025/02/03
[5 empty] | CRS No: NISOC-CRS-BK-GCS-HY-120-IN-DW-0002_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 |  |  | 02/2294/545698 | 1402/12/28 | با توجه به اینکه تنها ارتباط سیستم کنترل از طریق شبکه با DCS می باشد موارد سایبری بایستی در DCS دیده شود. این مورد برای UCP های پکیج Applicable نمی باشد.
2 |  |  | 02/2294/545698 | 1402/12/28 | مورد تایید است و رعایت شده است.
3 |  |  | 02/2294/545698 | 1402/12/28 | در این خصوص الزامی برای در نظر گرفتن کارت 16 کانال برای سیگنال دیجیتال در MR پروژه موجود در قرار داد وجود ندارد. در نظر دشاته باشید طبق اسپک سیگنال های Critical بصورت Redundant دیده شده است.
4 |  |  | 02/2294/545698 | 1402/12/28 | درنظر گرفته شده است . لطفا به وایرینگ مراجعه گردد.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: