## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-ME-DW-0001 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0106 |  |  | Transmital Date: 2025/03/09
Document Title: COMPRESSOR PACKAGE GENERAL ARRANGEMENT DRAWING |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-GCS-HY-120-ME-DW-0001_V03 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03/2294/333745 | 03/08/22 | جلسه Model Review مربوطه برگزار و مدرک با آخرین اطلاعات دریافتی از سازندگان مربوطه اسکید آب و روغن و .. بروزرسانی و مجددا ارائه میگردد.
2 |  |  | 02/2294/355128 | 1403/09/05
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 7/22/2024 |  |  |  |  | Date: