## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-ME-DW-0001 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0106 |  |  | Transmital Date: 2025/03/09
Document Title: COMPRESSOR PACKAGE GENERAL ARRANGEMENT DRAWING |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No: CRS-PEDCO-BK-GCS-HY-120-ME-DW-0001_V03 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments :
V02
1 | Pulsation study , approach 3 shall be supplied by vendor |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | Open
2 | Rotation arrows shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Will be added in next revision |  |  | To Follow API 618
3 | Flywheel data shall be added (Power, RPM, Dimention and …) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please note that Flywheel data is Vendor design Data and we cannt issue that. Power, RPM and package overall dimension will be issued. |  |  | ok
4 | shaft end dimentional and tolerances for the coupling shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | It is issued in relative document |  |  | ok
5 | Barring device data shall be added a DWG shall be shown here |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | It will issued in IOM |  |  | ok
6 | Earthing lug shall be specified and shown. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open.its not shown
7 | TP numbers shall be revised.for example TP-01-A/B/C |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open,it shall be according to project P&ID
8 | lifting lug calculation shall be provided |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please note that lifting lug calculation data is Vendor design Data and we cannt issue that. |  |  | ok
9 | Add TP number |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open, not added
10 | views name shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open
11 | Coupling Manufacturer & Detail Data shall be added (As per API 618 : the manufacturer,Size and type of coupling and the location of guard and their coverage shall be added) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document. |  |  | in naccording to Annex F of API 618 , (1-h) : size and type of coupling and the location of guard and their coverage shall be added
12 | Equipments Tag NO. shall be added (Table of compressor specifications and equipments include Tag NO. , Type , Services , Operating and Design data and ... shall be added) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | Not acceptable, it shall be specified
13 | Joints shall be reviesd |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | ok
14 | add Compressor , motor , lube oil system , cooling system & ... specification tables include its Details and reference standard. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | open
15 | reference document shall be added |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open
16 | in according to MOM (1401/12/16) , Lube oil system , cooling system , ElectroMotor & pulsation suppression device detail drawing and final pressure code calculation shall be added. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | open,it shall be added with its joints to compressor package to GA.find attached MOM
17 | Table of weights shall be added and specified maintenance heaviest weight (Empty , Fabricated , Total , Operating and maintenance heaviest weight) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Overall weight, maximum maintenace weight and major part weight will be added |  |  | ok
18 | Maximum allowable nozzle load shall be specified and shown on a table |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | ok
19 | Maintenace area shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | open
20 | all piping supports shall be shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | Open, Not shown for all pipe more than 2" shall be shown
21 | for the safety issue, all the nozzles and parts shall be within the skids |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Clarify please |  |  | closed
22 | Anchor bolts pocket and details shall be specified & shown |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | ok
23 | Mounting plate shall be shown separately with its details |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please clarify |  |  | closed
24 | Foundation plan shall be added |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | ok
25 | All the material shall be list based on ASTM code in a table. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | Not accepted. Refere to Client conclusion, item 12
26 | vendor shall specified Distance between Lifting lugs |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | Open, Not shown
27 | DBSE shall be specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | according to Annex F of API 618 , (1-e) , it shall be shown
28 | Elevation of all TP shall be shown from its center line |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | open,Elevation and distance from skid's edge shall be specified
29 | Maximum Elevation shall be shown, if there is any ladder or plat form is necessary , vendor shall specified |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Noted. |  |  | ok, but it seems laders and platform shall be considered to access to some valves , barring device and where is necessary to access
30 | Codes and standards for pressure parts shall be specified in notes |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please refer to the relevant document |  |  | ok
31 | lifting lug details shall be provided for suppressors |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | Please check new revision of GAD |  |  | ok
Piping comments:
1 | با توجه به عدم تطابق محل اتصال پايپينگ ورودي و خروجي مراحل 1 و 2 كمپرسور با مدل سه بعدي ايستگاه تقويت فشار گاز مورد تأييد نمي باشد. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا در این رابطه شفاف سازی نمائید |  |  | مدل سه بعدي كمپرسور در مدل سه بعدي ايستگاه پياده سازي شده و لوله هاي ورودي و خروجي مراحل 1 و2 به نازلهاي كمپرسور متصل گردد.
Civil and Structure comments :
1 | فايل پيوست مشاهده گردد. ( كامنت هاي كمپرسور) |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا در رابطه با فایل پیوست شفاف سازی نمائید. به کامنت های Civil بیان شده پاسخ داده شده است |  |  | در خصوص کنترل ارتفاع حداقل مورد نیاز رواداری بین ارتفاع زیر هوک جرثقیل تا بلندترين قسمت تجهیز از سوی بخش piping/mechanical اقدام مقتضی صورت پذیرد و و اعلام گردد تا در آتی نیاز به اصلاح ترازهای سازه ای و ... نباشد.
Instrument comments :
1 | 1- محل قرار گیری نازل های ابزاردقیق مشخص نمی باشد. 2- محل قرار گیری سنسورهای Vibration و دما مشخص نمی باشد. 3- موقعیت قرارگیری LCP و تمامی جعبه تقسیم ها نشان داده شود. |  | BK-SUR-ENG-MEC-03-09412 | 2024-07-22 | لطفا ویرایش جدید را مشاهده فرمائید |  |  | 3- با توجه به محل قرارگيري پايپ ها، به نظر مي رسد كه دسترسي LCP مناسب نباشد و مي بايست در نزديك ترين و در دسترس ترين نقطه در نظر گرفته شود. لطفا بررسي و اصلاح گردد.
V03
1 | Cable trays shall be shown |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | GAD will issued base on API 618 Requierment
2 | All instrument and electrical and mechanical equipment shall be added |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | GAD will issued base on API 618 Requierment
3 | Tables of weights shall be revised |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Recheck new revision of GAD
4 | all changes shall be mareked up by Revision cloude |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Noted
5 | Nozzle table : descripton of TP-20 shall be revised.(Vent to Flare) |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Recheck new revision of GAD
6 | Description of all TP shall be added in isometric view ( Page 1) |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Check new revision of GAD
7 | Flange size of Collection pots shall be revised. |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Recheck new revision of GAD
8 | Acc. To previos Instrument Comment about LCPs' locatiotion, Note that accessiblity to be rechecked and updated. It seems Pipes routes in both sides (West and East of LCP and gauge boards) are kinds of obstacles to LCPs' accissiblities. |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Final coclusion in last meeting will be followed (Model review meeting on 1403.10.05)
9 | All Name Plate shall be shown |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Check name Plate drawing
10 | Comments on Snubber, oil package and water package will be added after submitting it. |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Snubber ouline drawing is approved
11 | find pipng comments on attached file |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Noted
12 | NISOC comments shall be considered |  | BK-SUR-ENG-MEC-03-09672 | 2027-11-09 | Noted
13 |  |  | 1-8746 | 1403/09/10 | جلسه مورد نظر برگزارواصلاحات مقتضی اعمال گردید.
14 |  |  | 1-8804 | 1403/09/12
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 7/22/2024 |  |  |  |  | Date: