## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-GE-VL-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-SVTR-HY-0007 |  |  | Transmital Date: 2025/03/16
Document Title: SUB VENDOR LIST |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-GCS-HY-120-GE-VL-0001_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| شرکت PIDEMCO طبق توضیحات سامانه MOPتولید کننده اورینگ و گسکت بوده و برای فیلتر روغنی مورد تائید نیست. در ضمن با توجه به اعمال تغییرات ضروری است مدرک با نشان ویرایش ارسال گردد. |  | 02/2294/158569 | 1402.04.24 | Noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 7/1/2023 |  |  |  |  | Date: