## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 3
9184 – 073 - 053 |  |  | BK |  | GCS | HY | 120 |  | PM | LI | 0001 | V01
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V01 |  | MAR.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | M.Mehrshad
V00 |  | JAN.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | M.Mehrshad
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
Class: 2 |  |  |  | CLIENT Doc. Number:
status:
IFR: Issued For Review
IFR: Issued For Review
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 3
9184 – 073 - 053 |  |  | BK | GCS |  | HY | 120 | PM | LI | 0001 |  | V01
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | [6 empty] | 65
2 | X | X | [6 empty] | 66
3 | X | X | [6 empty] | 67
4 | [8 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: | [8 empty] | پروژه | بسته کاری | صادرکننده |  | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: از
9184 – 073 - 053 | [8 empty] | BK | GCS | HY |  | 120 | PM | LI | 0001 | V01
S/R No. | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | Doc. No. | Document Description |  |  | Doc. Class | Status
General/ Management
List
| BK | GCS | HY | 120 | PM | LI | 0001 |  | VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  | 2 | IFR
| BK | GCS | HY | 120 | PM | LI | 0001 |  | WORK BREAKDOWN STRUCTURE |  |  | 2 | IFR
| BK | GCS | HY | 120 | GE | LI | 0002 |  | SUB VENDOR LIST |  |  | 2 | IFR
| BK | GCS | HY | 120 | PM | SH | 0003 |  | TIME SCHEDULE |  |  | 2 | IFR
| BK | GCS | HY | 120 | GE | LI | 0006 |  | SPARE PART LIST |  |  | 2 | IFR
| BK | GCS | HY | 120 | GE | LI | 0004 |  | FINAL DATA BOOK INDEX |  |  | 2 | IFR
| BK | GCS | HY | 120 | GE | LI | 0007 |  | PACKING LIST |  |  | 1 | IFA
Drawing/Diagram
| BK | GCS | HY | 120 | GE | DW | 0008 |  | NAME PLATE DRAWING |  |  | 2 | IFR
Reports
| BK | GCS | HY | 120 | GE | RT | 0009 |  | FINAL DATA BOOK |  |  | 1 | IFA
QA/QC
Procedure/Plan
| BK | GCS | HY | 120 | QC | PR | 0016 |  | INSPECTION & TEST PLAN (ITP) |  |  | 1 | IFA
| BK | GCS | HY | 120 | QC | PR | 0012 |  | W.P.S & P.Q.R |  |  | 2 | IFR
| BK | GCS | HY | 120 | QC | PR | 0011 |  | SURFACE PREPARATION AND PAINTING PROCEDURE |  |  | 2 | IFR
| BK | GCS | HY | 120 | QC | PR | 0015 |  | NDE PROCEDURE |  |  | 2 | IFR
| BK | GCS | HY | 120 | QC | PR | 0014 |  | HYDROSTATIC/ PNEUMATIC TEST PROCEDURE |  |  | 2 | IFR
| BK | GCS | HY | 120 | QC | PR | 0018 |  | FAT PROCEDURE |  |  | 2 | IFR
| BK | GCS | HY | 120 | QC | PR | 0019 |  | SAT (PERFORMANCE TEST) PROCEDURE |  |  | 2 | IFR
Manual
| BK | GCS | HY | 120 | QC | ML | 0021 |  | INSTALLATION, OPERATION & MAINTENANCE MANUAL |  |  | 2 | IFR
Process
Calculation
| BK | GCS | HY | 120 | PR | DW | 0024 |  | CALCULATION NOTE FOR PSV SIZING |  |  | 2 | IFR
| BK | GCS | HY | 120 | PR | DW | 0024 |  | CALCULATION NOTE FOR CONTROL VALVE SIZING |  |  | 2 | IFR
Philosophy
| BK | GCS | HY | 120 | PR | DW | 0024 |  | CONTROL PHILOSOPHY |  |  | 2 | IFR
Drawing/Diagram
| BK | GCS | HY | 120 | PR | DW | 0023 |  | PFD |  |  | 2 | IFR | Added
| BK | GCS | HY | 120 | PR | DW | 0023 |  | P&I DIAGRAMS |  |  | 2 | IFR
List
| BK | GCS | HY | 120 | IN | LI | 0083 |  | UTILITY CONSUMPTION LIST |  |  | 2 | IFR | Added
| BK | GCS | HY | 120 | PR | LI | 0029 |  | EQUIPMENT LIST |  |  | 2 | IFR
Mechanical
Drawing/Diagram
| BK | GCS | HY | 120 | ME | DW | 0042 |  | COMPRESSOR PACKAGE GENERAL ARRANGEMENT DRAWING |  |  | 2 | IFR
[9 empty] | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIAL |  |  | 3 | IFI | Added
| BK | GCS | HY | 120 | ME | DW | 0042 |  | CROSS SECTIONAL DRAWING |  |  | 2 | IFR | Added
Datasheet
| BK | GCS | HY | 120 | ME | DW | 0042 |  | DETAILED D/SH FOR COMPRESSOR (API-618) WITH CERTIFICATES |  |  | 2 | IFR | Modified
Instrument
Datasheet
| BK | GCS | HY | 120 | IN | DT | 0073 |  | INSTRUMENT DATASHEETS / CERTIFICATES |  |  | 2 | IFR | Modified
| BK | GCS | HY | 120 | IN | DT | 0075 |  | DATASHEET FOR CONTROL/REGULATOR VALVES |  |  | 2 | IFR | Modified
| BK | GCS | HY | 120 | IN | DT | 0077 |  | DATASHEET FOR ON/OFF VALVES (IF ANY) |  |  | 2 | IFR | Modified
| BK | GCS | HY | 120 | IN | DT | 0074 |  | DATASHEET FOR SAFETY VALVES |  |  | 2 | IFR | Modified
[9 empty] | CONTROL PANEL PARTS DATA SHEET/LICENCE LIST/ CERTIFICATES |  |  |  | IFR | Added
List
| BK | GCS | HY | 120 | IN | LI | 0083 |  | CAUSE & EFFECT CHARTS LIST |  |  | 2 | IFR
| BK | GCS | HY | 120 | IN | LI | 0083 |  | INSTRUMENT/F&G LIST |  |  | 2 | IFI | Modified
| BK | GCS | HY | 120 | IN | LI | 0083 |  | INSTRUMENT CABLE LIST |  |  | 2 | IFI | Added
| BK | GCS | HY | 120 | IN | LI | 0083 |  | ALARM & SET POINT LIST |  |  | 2 | IFI | Added
| BK | GCS | HY | 120 | IN | LI | 0083 |  | I/O List |  |  | 2 | IFI | Added
Drawing/Diagram
| BK | GCS | HY | 120 | IN | DW | 0087 |  | HMI AND GRAPHICS PRINTOUT |  |  | 2 | IFR
| BK | GCS | HY | 120 | IN | DW | 0090 |  | PLC WIRING DIAGRAM & TERMINAL DETAILS |  |  | 2 | IFR
| BK | GCS | HY | 120 | IN | DW | 0091 |  | OVERAL CONTROL/SAFETY SYSTEM CONFIGURATION DIAGRAM |  |  | 2 | IFR | Modified
[9 empty] | LCP AND GAUGE BOARD LAYOUT |  |  | 2 | IFR | Added
[9 empty] | INSTRUMENT CABLE ROUTE/ MAIN TUBING LAYOUT DRAWING |  |  | 2 | IFR | Added
| BK | GCS | HY | 120 | IN | DW | 0092 |  | CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING |  |  | 2 | IFR
[9 empty] | JB TERMINATION DRAWING |  |  | 2 | IFR | Added
[9 empty] | INSTRUMENT EARTH DISTRIBUTION DIAGRAM |  |  | 2 | IFR | Added
| BK | GCS | HY | 120 | IN | DW | 0092 |  | CP CONTROL AND SAFETY LOOP DIAGRAM |  |  | 2 | IFR | Modified
| BK | GCS | HY | 120 | IN | DW | 0092 |  | UCP CONTROL AND SAFETY LOGIC DIAGRAM |  |  | 2 | IFR | Modified
| BK | GCS | HY | 120 | IN | DW | 0092 |  | HOOK UP DRAWING |  |  | 2 | IFR | Added
Electrical
Datasheet
| BK | GCS | HY | 120 | EL | DT | 0100 |  | D/SH (W/CURVE, DRAWING & CERTIFICATE) FOR COMPRESSOR MAIN MOTOR |  |  | 2 | IFR
| BK | GCS | HY | 120 | EL | DT | 0098 |  | DATASHEET (W/DRAWING) FOR AUXILIARY MOTORS |  |  | 2 | IFR
Drawing/Diagram
| BK | GCS | HY | 120 | IN | DW | 0090 |  | ELECTRICAL WIRING DIAGRAM AND CABLE LIST |  |  | 2 | IFI | Added
List
| BK | GCS | HY | 120 | EL | LI | 0101 |  | ELECTRICAL/UPS CONSUMPTION LOAD LIST |  |  | 2 | IFR | Modified
Class Definitions: 1 : All Documents shall be approved by client, otherwise next revision could not issued (w / IFA Status up to Final Revision that will be AFC). 2: All Documents should be approved by client, but after 14 days will be deemed approved (w / IFR Status up to Final Revision that will be AFC).).