## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 3
9184 – 073 - 053 |  |  | BK |  | GCS | IGK | 120 |  | PM | LI | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V00 |  | MAR.2025 |  | IFA |  |  |  | IGK |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 3
9184 – 073 - 053 |  |  | BK | GCS |  | IGK | 120 | PM | LI | 0001 |  | V00
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | [7 empty] | 65
2 | X | [7 empty] | 66
3 | X | [7 empty] | 67
4 | [8 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه:3 از 3
9184 – 073 - 053 |  | BK | GCS | IGK | 120 | PM | LI | 0001 | V00
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/Common For DCS,ESD
1.1 | BK-GCS-IGK-120-PM-LI-0001 | Vendor Print Index & Schedule (VPIS) | [7 empty] | IFA/AFC
1.2 | BK-GCS-IGK-120-PM-WB-0001 | Work Breakdown Structure (WBS) | [7 empty] | IFA/AFC
1.3 | BK-GCS-IGK-120-PM-SH-0001 | Time Schedule | [7 empty] | IFI
1.4 | BK-GCS-IGK-120-QC-PR-0001 | Inspection & Test Plan (ITP) | [7 empty] | IFA/AFC
1.5 | BK-GCS-IGK-120-QC-PR-0002 | Packing, Marking And Shipping Procedure | [7 empty] | IFA/AFC
1.6 | BK-GCS-IGK-120-GE-VL-0001 | Sub Vendor List | [7 empty] | IFA/AFC
1.7 | BK-GCS-IGK-120-GE-LI-0001 | Spare part list for commissioning and two years operation | [7 empty] | IFA/AFC
1.8 | BK-GCS-IGK-120-GE-LI-0002 | Final Data Book Index | [7 empty] | IFA/AFC
1.9 | BK-GCS-IGK-120-GE-DO-0001 | Final Data Book | [7 empty] | IFA/AFC
1.10 | BK-GCS-IGK-120-GE-ML-0001 | Manual/Catalogue | [7 empty] | IFI
1.11 | BK-GCS-IGK-120-IN-SP-0001 | Functional Design Specification-DCS/ESD Hardware | [7 empty] | IFA/AFC
1.12 | BK-GCS-IGK-120-IN-SP-0002 | Functional Design Specification-DCS/ESD Software | [7 empty] | IFA/AFC
1.13 | BK-GCS-IGK-120-IN-SP-0003 | HMI Graphic Functional Design Specification | [7 empty] | IFA/AFC
1.14 | BK-GCS-IGK-120-IN-PR-0001 | DCS/ESD FAT Procedure | [7 empty] | IFA/AFC
1.15 | BK-GCS-IGK-120-IN-PR-0002 | DCS/ESD SAT Procedure | [7 empty] | IFA/AFC
1.16 | BK-GCS-IGK-120-IN-CN-0001 | Power Consumption & Heat Dissipation Summary | [7 empty] | IFI
1.17 | BK-GCS-IGK-120-IN-DG-0001 | DCS/ESDTypical Loop Diagram | [7 empty] | IFA/AFC
1.18 | BK-GCS-IGK-120-IN-DG-0002 | Architecture Diagram | [7 empty] | IFA/AFC
1.19 | BK-GCS-IGK-120-IN-DG-0003 | Auxiliary Console & Desk Layout, Arrangement/wiring Diagram | [7 empty] | IFA/AFC
1.20 | BK-GCS-IGK-120-IN-DG-0004 | HMI Graphic Pages | [7 empty] | IFA/AFC
1.21 | BK-GCS-IGK-120-EL-DG-0001 | Grounding Plan & Earthing Diagram Principle | [7 empty] | IFA/AFC
2 | DCS
2.1 | BK-GCS-IGK-120-IN-LI-0001 | DCS IO Allocation | [7 empty] | IFA/AFC
2.2 | BK-GCS-IGK-120-IN-DG-0005 | DCS Cabinets Layout/Wiring Diagram | [7 empty] | IFA/AFC
2.3 | BK-GCS-IGK-120-IN-LI-0002 | DCS Bill of Material/License List | [7 empty] | IFA/AFC
2.4 | BK-GCS-IGK-120-IN-RE-0001 | DCS Loop Diagram Printout | [7 empty] | IFA/AFC
2.5 | BK-GCS-IGK-120-IN-RE-0002 | DCS Application Software Printout | [7 empty] | IFI
3 | ESD
3.1 | BK-GCS-IGK-120-IN-LI-0003 | ESD IO Allocation | [7 empty] | IFA/AFC
3.2 | BK-GCS-IGK-120-IN-DG-0006 | ESD Cabinets Layout/wiring Diagram | [7 empty] | IFA/AFC
3.3 | BK-GCS-IGK-120-IN-LI-0004 | ESD Bill of Material/LICENS LIST | [7 empty] | IFA/AFC
3.4 | BK-GCS-IGK-120-IN-RE-0003 | ESD Loop Diagram Printout | [7 empty] | IFA/AFC
3.5 | BK-GCS-IGK-120-IN-RE-0004 | ESD Application Software Printout | [7 empty] | IFI
3.6 | BK-GCS-IGK-120-IN-LI-0005 | ESD Modbus Mapping list | [7 empty] | IFI