## Sheet1 (hidden)
WBS | Task Name | W.F.
0 | BINAK OILFIELD DEVELOPMENT | 100 | 100 | 100
1 | DOCUMENTS | 15 | 5 | 5
1.1 | Vendor's Document (According to VPIS) Document Subject According to client Approval | 14.75 | 4.9 | 4.9167 |  | 98.33%
1.1.1 | WORK BREAKDOWN STRUCTURE FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.2 | VENDOR PRINT INDEX & SCHEDULE (VPIS) FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.3 | TIME SCHEDULE FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.4 | FINAL VENDOR DATA BOOK INDEX FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.5 | SHIPPING & INSTALLATION MANUAL (INCLUDING HANDLING, TRANSPORTATION, STORAGE AND ERECTION) FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.6 | SUB-VENDOR LIST FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.7 | MARKING & PACKING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, REBOILER, DRUMS, FILTERS, COLUMNS, EXCHANGERS) | 0.11 | 0.7458% | 0.036667 |  | 0.7458%
1.1.8 | MARKING & PACKING PROCEDURE FOR GLYCOL CIRCULATION PUMPS | 0.1 | 0.678% | 0.033333 |  | 0.678%
1.1.9 | INSPECTION AND TEST PLAN FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.4746% | 0.023333 |  | 0.4746%
1.1.10 | HARDNESS TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.11 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.12 | PICKLING AND PASSIVATION PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.13 | POSTWELD HEAT TREATMENT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.14 | PMI PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.15 | HYDROSTATIC TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.16 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.17 | WELD REPAIR PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.18 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.19 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.20 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.21 | UCP LOGIC DESCRIPTION FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.22 | BMS LOGIC DESCRIPTION FOR DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.23 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.24 | PROCESS DATA SHEET FOR DEHYDRATION COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.25 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.26 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.27 | PROCESS DATA SHEET FOR GLYCOL STRIPPING COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.28 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.29 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.30 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN CONDENSER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.31 | PROCESS DATA SHEET FOR GLYCOL REBOILER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.32 | PROCESS DATA SHEET FOR GLYCOL SURGE VESSEL | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.33 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.34 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.35 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.36 | EQUIPMENT LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.37 | ALARM & TRIP SET POINT LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.38 | UTILITY CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.39 | CHEMICAL CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.40 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.41 | PERFORMANCE TEST PROCEDURE FOR GAS DEHYDRATION PACKAGE (SAT Procedure)) | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.42 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.43 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.44 | Mechanical Calculation Book for C-100 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.45 | Lifting Calculation Book for C-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.46 | General Arrangement Drawing for C-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.47 | Detail of Body for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.48 | NOZZLE & Manhole Detail Drawing for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.49 | External Attachment Drawing for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.50 | Internal Welded Attachments for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.51 | Name Plate Detail Drawing for C-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.52 | NDT Map for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.53 | Welding Map for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.54 | Mechanical Calculation Book for C-200 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.55 | General Arrangement Drawing for C-200 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.56 | Detail of Body & Nozzle drawing for C-200 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.57 | Name Plate Detail Drawing for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.58 | Internal Welded & External Attachments for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.59 | NDT Map for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.60 | Welding Map for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.61 | Mechanical Calculation Book for C-300 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.62 | General Arrangement Drawing for C-300 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.63 | Detail drawing for C-300 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.64 | Name Plate Detail Drawing for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.65 | NDT Map for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.66 | Welding Map for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.67 | Mechanical & Lifting Calculation Book for V-120 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.68 | General Arrangement Drawing for V-120 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.69 | Detail of Body for V-120 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.70 | Nozzle & Manhole Detail Drawing for V-120 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.71 | External Attachments & Saddle drawing for V-120 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.72 | Name Plate Detail Drawing for V-120 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.73 | NDT Map for V-120 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.74 | Welding Map for V-120 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.75 | Mechanical Calculation Book for F-100 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.76 | General Arrangement Drawing for F-100 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.77 | Detail Drawing for F-100 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.78 | Name Plate Detail Drawing for F-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.79 | Mechanical Calculation Book for F-200 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.80 | General Arrangement Drawing for F-200 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.81 | Detail Drawing for F-200 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.82 | Name Plate Detail Drawing for F-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.83 | Mechanical Calculation Book for E-100 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.84 | General Arrangement Drawing for E-100 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.85 | Detail Drawing for E-100 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.86 | Name Plate Detail Drawing for E-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.87 | Mechanical Calculation Book for E-200 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.88 | General Arrangement Drawing for E-200 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.89 | Detail Drawing for E-200 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.90 | Name Plate Detail Drawing for E-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.91 | Mechanical Calculation Book for E-300 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.92 | General Arrangement Drawing for E-300 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.93 | Detail Drawing for E-300 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.94 | Name Plate Detail Drawing for E-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.95 | Mechanical & Lifting Calculation Book for R-100 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.96 | General Arrangement Drawing for R-100 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.97 | Detail of Body for R-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.98 | Nozzle & Manhole Detail Drawing for R-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.99 | Detail of Saddle drawing for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.100 | Internal & External Welded Attachments for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.101 | Name Plate Detail Drawing for R-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.102 | NDT Map for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.103 | Welding Map for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.104 | Mechanical & Lifting Calculation Book for V-130 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.105 | General Arrangement Drawing for V-130 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.106 | Detail of Body for V-130 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.107 | Nozzle & Manhole Detail Drawing for V-130 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.108 | External Attachments & Saddle drawing for V-130 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.109 | Name Plate Detail Drawing for V-130 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.110 | NDT Map for V-130 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.111 | Welding Map for V-130 | 0.42 | 0.028475 | 0.14 |  | 2.847%
1.1.112 | BURNER DATA SHEET FOR GLYCOL REBOILER | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.113 | BURNER DRAWING FOR GLYCOL REBOILER | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.114 | LUBRICATION LIST FOR GAS DEHYDRATION PACKAGE | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.115 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.116 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.117 | PUMPS INSTALLATION, OPERATION AND MAINTENANCE MANUAL FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.118 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.119 | TWO YEARS & COMMISSIONING SPARE PART LIST FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.120 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.121 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.122 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.123 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (30%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.124 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (60%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.125 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (90%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.126 | PACKAGE PLOT PLAN FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.127 | PIPING GENERAL ARRANGEMENT DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.128 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.129 | LINE LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.130 | TIE-IN-LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.131 | SUPPORT LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.132 | STRESS ANALYSIS REPORT FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.133 | Electrical single line diagram | 0.15 | 0.010169 | 0.05 |  | 1.017%
1.1.134 | Power and control cable list | 0.16 | 0.010847 | 0.053333 |  | 1.085%
1.1.135 | Earthing detail layout | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.136 | Electrical load list | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.137 | Electrical/Instrument Cable Route Layout | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.138 | Electrical motor data sheets | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.139 | Electrical panel layout and wiring diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.140 | Local control station (LCS) panel layout and wiring diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.141 | Instrument list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.142 | Input/Output signal list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.143 | Instrument and electrical block schematic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.144 | UCP system configuration diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.145 | BMS system configuration diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.146 | Instrument junction box layout and wiring termination diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.147 | Burner operation panel layout & wiring diagram with connections & dimensions | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.148 | Control valve calculation sheets | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.149 | Instrument D.S. for control valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.150 | Instrument cable list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.151 | Instrument D.S. for On/Off valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.152 | Instrument D.S. for H2O analyzer | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.153 | Instrument D.S. for temperature gauge | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.154 | Instrument D.S. for temperature transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.155 | Instrument D.S. for pressure gauges and differential gauges | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.156 | Instrument D.S. for pressure transmitters and differentia pressure transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.157 | Pressure safety valves calculation | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.158 | Pressure safety valves data sheet | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.159 | Instrument D.S. for pressure regulator valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.160 | Flow element calculation sheets | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.161 | Instrument D.S. for flow elements | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.162 | Instrument D.S. for level gauges | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.163 | Instrument D.S. for level transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.164 | Hook up drawing | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.165 | Instrument location layout | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.166 | Flame scanner data sheet | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.167 | UCP panel layout and arrangement | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.168 | BMS panel layout and arrangement | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.169 | UCP system wiring diagram and connections | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.170 | BMS system wiring diagram and connections | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.171 | UCP and BMS system power consumption list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.172 | Instrument loop diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.173 | Modbus IO list (Modbus mapping list) | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.174 | FAT procedure for UCP system | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.175 | FAT procedure for BMS system | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.176 | UCP system Logic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.177 | BMS system Logic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.178 | PRINT OUT OF HMI FOR BMS and UCP | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.2 | WPS-PQR | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.3 | WQT | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.4 | NDT Procedures (VT-PT-MT-UT-RT) | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.5 | NDT Personal Certificate | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.6 | Calibration | 0.05 | 0.01 | 0.016667 |  | 0.3333%
2 | TEST AND INSPECTION ACTIVITIES | 78 | 88 | 88
2.1 | Vessel | 30.39 | 30.39 | 30.39 |  | 38.96%
2.1.1 | Raw Material Of Pressure Parts | 7 | 0.23034 | 7 |  | 23.03%
| PLATE |  | 0 | 4.2 | √ | 60%
| FLANG |  | 0 | 2.1 | √ | 30%
| PIPE |  | 0 | 0.7 | √ | 10%
2.1.2 | Raw Material Of Non-Pressure Parts | 2.15 | 0.070747 | 2.15 |  | 7.075%
| PLATE |  | 0 | 1.935 | √ | 90%
| PROFILE |  | 0 | 0.215 | √ | 10%
2.1.3 | Internals | 0.61 | 0.020072 | 0.61 |  | 2.007%
2.1.4 | VT & DT For Raw Material | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.5 | Consumable Material (Electrode) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.6 | Cutting & Marking | 1.52 | 0.050016 | 1.52 | √ | 5.002%
2.1.7 | Rolling & Forming | 2.43 | 0.079961 | 2.43 | √ | 7.996%
2.1.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) | 2.13 | 0.070089 | 2.13 | √ | 7.009%
2.1.9 | Welding | 3.95 | 0.12998 | 3.95 | √ | 13%
2.1.10 | Ferrite Check For Welding Gladded Parts | 2.43 | 0.079961 | 2.43 | √ | 7.996%
2.1.11 | NDT (VT,MT.PT,UT,RT) | 1.22 | 0.040145 | 1.22 |  | 4.014%
2.1.12 | Weld Repair | 1.52 | 0.050016 | 1.52 |  | 5.002%
2.1.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 1.22 | 0.040145 | 1.22 |  | 4.014%
2.1.14 | Final Visual and Dimensional | 0.91 | 0.029944 | 0.91 |  | 2.994%
2.1.15 | PWHT (If Any) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.16 | Hardness Check | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.17 | NDT After PWHT | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.18 | Pneumatic Test (Pad Test) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.19 | Hydrostatic Test Water Quality | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.20 | Hydrostatic Test | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.21 | Draining & Drying | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.22 | Abrasive & Paint Material | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.2 | Heat Exchangers | 4.72 | 4.66 | 4.66 |  | 6.051%
2.2.1 | Raw Material for Pressure parts | 1.12 | 0.24034 | 1.1058 |  | 23.73%
| PLATE |  | 0 | 0.66346 | √ | 60%
| FLANG |  | 0 | 0.33173 | √ | 30%
| PIPE |  | 0 | 0.11058 | √ | 10%
2.2.2 | Raw Material for Non-Pressure parts | 0.37 | 0.079399 | 0.3653 |  | 7.839%
| PLATE |  | 0 | 0.32877 | √ | 90%
| PROFILE |  | 0 | 0.03653 | √ | 10%
2.2.3 | VT & DT For Raw Material | 0.05 | 0.01073 | 0.049364 | √ | 1.059%
2.2.4 | Consumable Material (Electrode) | 0.05 | 0.01073 | 0.049364 | √ | 1.059%
2.2.5 | Cutting & Marking | 0.23 | 0.049356 | 0.22708 | √ | 4.873%
2.2.6 | Rolling & Forming | 0.37 | 0.079399 | 0.3653 | √ | 7.839%
2.2.7 | Tube to Tube Sheet Joint {Expansion) | 0.35 | 0.075107 | 0.34555 | √ | 7.415%
2.2.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, … ) | 0.61 | 0.1309 | 0.60225 |  | 12.92%
2.2.9 | Welding | 0.37 | 0.079399 | 0.3653 |  | 7.839%
2.2.10 | NDT (VT,MT.PT,UT,RT) | 0.19 | 0.040773 | 0.18758 |  | 4.025%
2.2.11 | Weld Repair | 0.23 | 0.049356 | 0.22708 |  | 4.873%
2.2.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 0.19 | 0.040773 | 0.18758 |  | 4.025%
2.2.13 | Final Visual and Dimensional | 0.14 | 0.030043 | 0.13822 |  | 2.966%
2.2.14 | PWHT (If Any) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.15 | Hardness Check | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.16 | NDT After PWHT | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.17 | Pneumatic Test (Pad Test) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.18 | Hydrostatic Test Water Quality | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.19 | Hydrostatic Test | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.20 | Draining & Drying | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.21 | Abrasive & Paint Material | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.3 | Re-boiler | 2.32 | 2.45 | 2.45 |  | 2.974%
2.3.1 | Raw Material for Pressure parts | 0.59 | 0.24082 | 0.62306 |  | 25.43%
| PLATE |  | 0 | 0.37384 | √ | 60%
| FLANG |  | 0 | 0.18692 | √ | 30%
| PIPE |  | 0 | 0.062306 | √ | 10%
2.3.2 | Raw Material for Non-Pressure parts | 0.21 | 0.085714 | 0.22177 |  | 9.052%
| PLATE |  | 0 | 0.19959 | √ | 90%
| PROFILE |  | 0 | 0.022177 | √ | 10%
2.3.4 | Consumable Material (Electrode) | 0.02 | 0.0081633 | 0.021121 | √ | 0.8621%
2.3.5 | Cutting & Marking | 0.12 | 0.04898 | 0.12672 | √ | 5.172%
2.3.6 | Rolling & Forming | 0.21 | 0.085714 | 0.22177 | √ | 9.052%
2.3.7 | Weld Preparation and Fit-Up (Shell,Nozzle, ... ) | 0.33 | 0.13469 | 0.34849 | √ | 14.22%
2.3.8 | Welding | 0.21 | 0.085714 | 0.22177 | √ | 9.052%
2.3.9 | NDT (VT,MT.PT,UT,RT) | 0.11 | 0.044898 | 0.11616 |  | 4.741%
2.3.10 | Weld Repair | 0.14 | 0.057143 | 0.14784 |  | 6.034%
2.3.11 | NDT After Weld Repair (VT,MT.PT,UT,R T) | 0.11 | 0.044898 | 0.11616 |  | 4.741%
2.3.12 | Final Visual and Dimensional | 0.07 | 0.028571 | 0.073922 |  | 3.017%
2.3.13 | PWHT (If Any) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.14 | Hardness Check | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.15 | NDT After PWHT | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.16 | Pneumatic Test (Pad Test) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.17 | Hydrostatic Test Water Quality | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.18 | Hydrostatic Test | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.19 | Draining & Drying | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.20 | Abrasive & Paint Material | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.21 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.4 | Field Instruments (Transmitters/ Switch/ Gauge/ Analizer etc.) | 9.36 | 14.71 | 14.71 |  | 12%
2.4.1 | Visual Dimensional Inspection(Appearance) | 3.18 | 0.21618 | 4.9976 |  | 33.97%
2.4.2 | Calibration Check | 2.34 | 0.15908 | 3.6775 |  | 25%
2.4.3 | Tag & Model No & Specification Check | 1.59 | 0.10809 | 2.4988 |  | 16.99%
2.4.4 | Review Material, IP,ATEX Certificate | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.4.5 | Pressure & Performance Test | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.4.6 | Packing Inspection& Painting | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.5 | Cable, Wires & Tray | 1.56 | 1.96 | 1.96 |  | 2%
2.5.1 | Cable & Wires | 0.78 | 0.39796 | 0.98 |  | 50%
2.5.1.1 | Visual Inspection | 0.39 | 0.98 | 0.49
2.5.1.2 | Type Test Sertificate or Manufacturer Catalogue | 0.39 | 0.98 | 0.49
2.5.2 | Tray | 0.78 | 0.39796 | 0.98 |  | 50%
2.5.2.1 | Material Inspection | 0.39 | 0.98 | 0.49
2.5.2.2 | Visual & Dimensional Inspection | 0.39 | 0.98 | 0.49
2.6 | Junction Box | 2.35 | 2.94 | 2.94 |  | 3.013%
2.6.1 | Review IP, ATEX Certificate | 0.94 | 0.31973 | 1.176 |  | 40%
2.6.2 | Tag & Model No Check | 0.59 | 0.20068 | 0.73813 |  | 25.11%
2.6.3 | Review IP, ATEX certificate | 0.47 | 0.15986 | 0.588 |  | 20%
2.6.4 | Packing inspection and painting | 0.35 | 0.11905 | 0.43787 |  | 14.89%
2.7 | Local Panel (Outdoor-Hazardous Area) | 3.12 | 2.94 | 2.94 |  | 4%
2.7.1 | Visual Inspection & Dimenslonal Check | 1.09 | 0.37075 | 1.0271 |  | 34.94%
2.7.2 | Accessories Tag & Model No Check | 0.31 | 0.10544 | 0.29212 |  | 9.936%
2.7.3 | Construction | 1.4 | 0.47619 | 1.3192 |  | 44.87%
2.7.4 | Review IP, ATEX Certificate | 0.16 | 0.054422 | 0.15077 |  | 5.128%
2.7.5 | Packing Inspection & Painting | 0.16 | 0.054422 | 0.15077 |  | 5.128%
2.8 | Control Panel (Indoor-Safe Area) | 7.02 | 12.25 | 12.25 |  | 9%
2.8.1 | Visual Inspection/ QTY & Dimensional Check | 2.81 | 0.22939 | 4.9035 |  | 40.03%
2.8.2 | Tag & Model No Check | 1.76 | 0.14367 | 3.0712 |  | 25.07%
2.8.3 | Function & Performance test (Power & Start-up Check, I/O Check) | 1.4 | 0.11429 | 2.443 |  | 19.94%
2.8.4 | Main equipment & Accessories Certificate IP , ATEX, SIL Certificate Check) | 1.05 | 0.085714 | 1.8323 |  | 14.96%
2.9 | Valves | 3.09 | 7.84 | 7.84 |  | 3.962%
2.9.1 | Manual Valves | 1.62 | 0.20663 | 4.1103 |  | 52.43%
2.9.1.1 | Material Inspection | 0.81 | 3.92 | 2.0551 |  | 50%
2.9.1.2 | Visual and Dimensional Inspection | 0.65 | 3.1457 | 0.8246 |  | 40.12%
2.9.1.3 | Other Required Tests | 0.16 | 0.77432 | 0.081442 |  | 9.877%
2.9.2 | Inst.Valves (Shut Down, On/Off, Control & Safety Valves) | 1.47 | 0.1875 | 3.7297 |  | 47.57%
2.9.2.1 | Material Inspection | 0.52 | 2.7733 | 1.3194 |  | 35.37%
2.9.2.2 | Visual and Dimensional & QTY Inspection | 0.3 | 1.6 | 0.76117 |  | 20.41%
2.9.2.3 | Construction | 0.37 | 1.9733 | 0.93877 |  | 25.17%
2.9.2.4 | Accessory | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.5 | Pressure Test | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.6 | Calibration | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.7 | Performance test | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.1 | Strainers | 1.56 | 2.94 | 2.94 |  | 2%
2.10.1 | Material Inspection | 0.78 | 0.26531 | 1.47 |  | 50%
2.10.2 | Visual and Dimensional Inspection | 0.62 | 0.21088 | 1.1685 |  | 39.74%
2.10.3 | Hydro Test | 0.16 | 0.054422 | 0.30154 |  | 10.26%
2.11 | Piping Items (Pipe, Flange, Fitting, Gasket, Bolt & Nuts) | 2.35 | 3.92 | 3.92 |  | 3.013%
2.11.1 | Material Inspection | 0.82 | 0.20918 | 1.3678 | √ | 34.89%
2.11.2 | Visual and Dimensional Inspection | 0.35 | 0.089286 | 0.20372 | √ | 14.89%
2.11.3 | Weld Preparation and Fit-Up | 0.47 | 0.1199 | 0.040744 |  | 20%
2.11.4 | Welding | 0.47 | 0.1199 | 0.0081488 |  | 20%
2.11.5 | NDT( VT, MT, PT, UT, RT) | 0.12 | 0.030612 | 0.00041611 |  | 5.106%
2.11.6 | Hydrostatic Test | 0.12 | 0.030612 | 2.1248e-05 |  | 5.106%
2.12 | Pump | 1.56 | 2.94 | 2.94 |  | 2%
2.12.1 | Final Visual and Dimensional Inspection | 1.01 | 0.34354 | 1.9035 |  | 64.74%
2.12.2 | Performance test | 0.55 | 0.18707 | 1.0365 |  | 35.26%
2.13 | Ladder & Platform | 1.56 | 1.96 | 1.96 |  | 2%
2.13.1 | Visual and Dimensional Check After Welding | 1.56 | 0.79592 | 1.96
2.14 | Chemical Injection Package | 3.14 | 4.17 | 4.17 |  | 4.026%
2.14.1 | Raw Material for Tank | 1.09 | 0.26139 | 1.4475 | √ | 34.71%
2.14.2 | Final Inspection For Fabricated Tank | 0.16 | 0.038369 | 0.21248 | √ | 5.096%
2.14.3 | Piping & Structure Works | 1.25 | 0.29976 | 1.66 |  | 39.81%
2.14.4 | Performance test | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.5 | Packing Inspection | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.6 | IRN | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.7 | Final Book | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.15 | Reboiler Burner | 1.56 | 1.96 | 1.96 |  | 2%
2.15.1 | Final Visual and Dimensional Inspection | 1.01 | 0.51531 | 1.269 |  | 0.64744
2.15.2 | Burner Test | 0.55 | 0.28061 | 0.69103 |  | 0.35256
2.16 | Painting of Package Assembly (Piping, Structure) | 0.78 | 0.98 | 0.98 |  | 1%
2.16.1 | Abrasive & Paint Material | 0.39 | 0.39796 | 0.49 |  | 50%
2.16.2 | Blasting & Painting (Each Layer DFT, Adhesion) | 0.39 | 0.39796 | 0.49
2.17 | Pickling (For Stainless Steel Part) | 0.78 | 0.98 | 0.98 |  | 1%
2.17.1 | Pickling and Passivation | 0.78 | 0.79592 | 0.98
2.18 | Preservation | 0.78 | 0 | 0 |  | 1%
2.18.1 | N2 Purge /Silica | 0.78 | 0 | 0
3 | PACKING | 1 | 1 | 1
3.1 | Packing Inspection | 1 | 1 | 1
4 | IRN | 1 | 1 | 1
4.1 | Release Note | 1 | 1 | 1
5 | FINAL DATA BOOK | 3 | 3 | 3
5.1 | Final Document Preparation | 3 | 1 | 1
6 | IC | 1 | 1 | 1
6.1 | Inspection Certificate | 1 | 1 | 1
7 | SITE ACCEPTANCE TEST | 1 | 1 | 1
7.1 | SAT | 1 | 1 | 1

## Cover
NISOC |  |  |  | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
Work Breakdown Structure (WBS)
| شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 3
| 9184 – 073 - 053 |  |  | BK |  | GCS | IGK | 120 |  | PM | WB | 0001 | V 01
طرح نگهداشت و افزایش تولید 27 مخزن
WBS (Work Breakdown Structure) نگهداشت و افزایش تولید میدان نفتی بینک
| V01 |  | APR.2025 |  | AFC |  |  |  | IGK |  |  | M.Fakharian |  | S.Faramarzpour
| V00 |  | MAR.2025 |  | IFA |  |  |  | IGK |  |  | M.Fakharian |  | S.Faramarzpour
| Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
[5 empty] | CLIENT Doc. Number: |  |  |  | -
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
NISOC |  |  |  | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
Work Breakdown Structure (WBS)
| شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 3
| 9184 – 073 - 053 |  |  | BK | GCS |  | IGK | 120 | PM | WB | 0001 |  | V 01
REVISION RECORD SHEET
Page |  | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 |  | X | [7 empty] | 61
2 |  | X | [7 empty] | 62
3 |  | X | X | [6 empty] | 63
4 | [9 empty] | 64
5 | [9 empty] | 65
6 | [9 empty] | 66
7 | [9 empty] | 67
8 | [9 empty] | 68
9 | [9 empty] | 69
10 | [9 empty] | 70
11 | [9 empty] | 71
12 | [9 empty] | 72
13 | [9 empty] | 73
14 | [9 empty] | 74
15 | [9 empty] | 75
16 | [9 empty] | 76
17 | [9 empty] | 77
18 | [9 empty] | 78
19 | [9 empty] | 79
20 | [9 empty] | 80
21 | [9 empty] | 81
22 | [9 empty] | 82
23 | [9 empty] | 83
24 | [9 empty] | 84
25 | [9 empty] | 85
26 | [9 empty] | 86
27 | [9 empty] | 87
28 | [9 empty] | 88
29 | [9 empty] | 89
30 | [9 empty] | 90
31 | [9 empty] | 91
32 | [9 empty] | 92
33 | [9 empty] | 93
34 | [9 empty] | 94
35 | [9 empty] | 95
36 | [9 empty] | 96
37 | [9 empty] | 97
38 | [9 empty] | 98
39 | [9 empty] | 99
40 | [9 empty] | 100
41 | [9 empty] | 101
42 | [9 empty] | 102
43 | [9 empty] | 103
44 | [9 empty] | 104
45 | [9 empty] | 105
46 | [9 empty] | 106
47 | [9 empty] | 107
48 | [9 empty] | 108
49 | [9 empty] | 109
50 | [9 empty] | 110
51 | [9 empty] | 111
52 | [9 empty] | 112
53 | [9 empty] | 113
54 | [9 empty] | 114
55 | [9 empty] | 115
56 | [9 empty] | 116
57 | [9 empty] | 117
58 | [9 empty] | 118
59 | [9 empty] | 119
60 | [9 empty] | 120

## WBS
WBS | Task Name | WF | Actual Progress Last Period (%) | Actual Progress This Period (%) | Cumulative Actual Progress (%)
0 | Commissioning DCE/ESD System for Binak Gas Station | 100% | 0% | 0% | 0%
1 | Documents | 4.995% | 0% | 0% | 0%
1.1 | Hardware | 2.995% | 0% | 0% | 0%
1.1.1 | General Documents | 0.995% | 0% | 0% | 0%
1.1.1.1 | Vendor Print Index & Schedule (VPIS) | 0.06% | 0% | 0% | 0%
1.1.1.2 | Work Breakdown Structure (WBS) | 0.047% | 0% | 0% | 0%
1.1.1.3 | Time Schedule | 0.047% | 0% | 0% | 0%
1.1.1.4 | Inspection & Test Plan (ITP) | 0.047% | 0% | 0% | 0%
1.1.1.5 | Sub Vendor List | 0.03% | 0% | 0% | 0%
1.1.1.6 | Functional Design Specification-DCS/ESD Hardware | 0.06% | 0% | 0% | 0%
1.1.1.7 | Functional Design Specification-DCS/ESD Software | 0.06% | 0% | 0% | 0%
1.1.1.8 | HMI Graphic Functional Design Specification | 0.06% | 0% | 0% | 0%
1.1.1.9 | Packing, Marking And Shipping Procedure | 0.047% | 0% | 0% | 0%
1.1.1.10 | DCS/ESD FAT Procedure | 0.06% | 0% | 0% | 0%
1.1.1.11 | DCS/ESD SAT Procedure | 0.06% | 0% | 0% | 0%
1.1.1.12 | Power consumption & Heat Dissipation Calculation | 0.04% | 0% | 0% | 0%
1.1.1.13 | Grounding Plan & Earthing Diagram Principle | 0.04% | 0% | 0% | 0%
1.1.1.14 | DCS/ESD Typical Loop Diagram | 0.04% | 0% | 0% | 0%
1.1.1.15 | Architecture Diagram | 0.06% | 0% | 0% | 0%
1.1.1.16 | Auxiliary Console & Desk Layout, Arrangement/wiring Diagram | 0.06% | 0% | 0% | 0%
1.1.1.17 | HMI Graphic Pages | 0.04% | 0% | 0% | 0%
1.1.1.18 | Manual/Catalogue | 0.03% | 0% | 0% | 0%
1.1.1.19 | Spare part list for commissioning and two years operation | 0.047% | 0% | 0% | 0%
1.1.1.20 | Packing List | 0.03% | 0% | 0% | 0%
1.1.1.21 | FAT Report | 0.03% | 0% | 0% | 0%
1.1.2 | DCS System Documents | 1% | 0% | 0% | 0%
1.1.2.1 | DCS IO Allocation | 0.23% | 0% | 0% | 0%
1.1.2.2 | DCS Cabinets Layout/wiring Diagram | 0.23% | 0% | 0% | 0%
1.1.2.3 | DCS Bill of Material/License LIST | 0.18% | 0% | 0% | 0%
1.1.2.4 | DCS Loop Diagram Printout | 0.18% | 0% | 0% | 0%
1.1.2.5 | DCS Application Software Printout | 0.18% | 0% | 0% | 0%
1.1.3 | ESD System Documents | 1% | 0% | 0% | 0%
1.1.3.1 | ESD IO Allocation | 0.18% | 0% | 0% | 0%
1.1.3.2 | ESD Cabinets Layout/wiring Diagram | 0.18% | 0% | 0% | 0%
1.1.3.3 | ESD Bill of Material/LICENS LIST | 0.16% | 0% | 0% | 0%
1.1.3.4 | ESD Loop Diagram Printout | 0.16% | 0% | 0% | 0%
1.1.3.5 | ESD Application Software Printout | 0.16% | 0% | 0% | 0%
1.1.3.6 | ESD Modbus Mapping list | 0.16% | 0% | 0% | 0%
1.2 | Software | 2% | 0% | 0% | 0%
1.2.1 | DCS System Logic | 0.75% | 0% | 0% | 0%
1.2.3 | ESD System Logic | 0.75% | 0% | 0% | 0%
1.2.4 | HMI | 0.5% | 0% | 0% | 0%
2 | Procutement and Supply Row Material | 50% | 0% | 0% | 0%
2.1 | DCS Cabinets | 20% | 0% | 0% | 0%
2.1.1 | Main Equipment (Card Module,CPU,Power Supply,Barrier,Relay,…) | 15% | 0% | 0% | 0%
2.1.6 | Bulk Mterial (Terminal,Wire,Fan,Fuse…) | 2.5% | 0% | 0% | 0%
2.1.7 | Body of Cabinets | 2.5% | 0% | 0% | 0%
2.2 | ESD Cabinets | 15% | 0% | 0% | 0%
2.2.1 | Main Equipment (Card Module,CPU,Power Supply,Barrier,Relay,Logic Solver,…) | 10% | 0% | 0% | 0%
2.2.2 | Body of Cabinets | 2.5% | 0% | 0% | 0%
2.2.3 | Bulk Mterial (Terminal,Wire,Fan,Fuse,…) | 2.5% | 0% | 0% | 0%
2.3 | Network and Supervisor | 15% | 0% | 0% | 0%
2.3.1 | Auxiliary Console For ESD System | 2% | 0% | 0% | 0%
2.3.2 | Station and Server | 5% | 0% | 0% | 0%
2.3.3 | Desk and Furniture | 2% | 0% | 0% | 0%
2.3.4 | Switch and Firewall | 2% | 0% | 0% | 0%
2.3.5 | Body of Network Cabinets with Rack 42U | 2% | 0% | 0% | 0%
2.3.6 | Laptop for DCS ans ESD System and Printer | 1% | 0% | 0% | 0%
2.3.7 | Large Screen Manitor (62") and Manitor | 1% | 0% | 0% | 0%
3 | Fabrication and Assemble | 20% | 0% | 0% | 0%
3.1 | DCS Cabinets | 8.5% | 0% | 0% | 0%
3.1.1 | DCS Systen Cabinets | 5.5% | 0% | 0% | 0%
3.1.2 | DCS Marshalling Cabinets | 3% | 0% | 0% | 0%
3.2 | ESD Cabients | 7% | 0% | 0% | 0%
3.2.1 | ESD System Cabinets | 5.5% | 0% | 0% | 0%
3.2.2 | ESD Marshalling Cabinets | 1.5% | 0% | 0% | 0%
3.3 | Network Cabinet | 3% | 0% | 0% | 0%
3.3.1 | Network Cabinet | 3% | 0% | 0% | 0%
3.4 | Desk and Auxiliary Console | 1.5% | 0% | 0% | 0%
3.4.4 | Desk and Auxiliary Console | 1.5% | 0% | 0% | 0%
4 | PreFAT | 1% | 0% | 0% | 0%
4.1 | PreFAT for DCS and ESD System Integrated (Software and Hardware PreFAT) | 1% | 0% | 0% | 0%
5 | FAT | 10% | 0% | 0% | 0%
5.1 | FAT DCS and ESD System Integrated (Software and Hardware FAT) | 10% | 0% | 0% | 0%
6 | Delivery | 5% | 0% | 0% | 0%
6.1 | Packing and Delivery to Site (all of Packages) | 5% | 0% | 0% | 0%
7 | SAT | 4% | 0% | 0% | 0%
7.1 | SAT | 4% | 0% | 0% | 0%
8 | Final Data Book | 5% | 0% | 0% | 0%
8.1 | Vendor Final Data Book Index | 0.2% | 0% | 0% | 0%
8.2 | Final Data Book Preparation | 4.8% | 0% | 0% | 0%

## Note 1 (hidden)
NISOC | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید سیستم های DCS و ESD ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0031_01)
XXXXXXXXXXXXXXXXXXXX
شماره پیمان: | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه | شماره صفحه: 3 از 3
9184 – 073 - 053 | BK | GCS | IGK | 120 | PM | WB | 0001 |  | V 01
فایل اکسل مدرک درج گردد