## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 3
9184 – 073 - 053 |  |  | BK |  | GCS | IDR | 120 |  | PM | LI | 0001 | V01
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V01 |  | JAN. 2025 |  | IFI |  |  |  | iDrill M.E. |  |  | M.Fakharian |  | S.Faramarzpour
V00 |  | OCT. 2024 |  | IFI |  |  |  | iDrill M.E. |  |  | M.Fakharian |  | M.Sadeghian
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 3
9184 – 073 - 053 |  |  | BK | GCS |  | IDR | 120 | PM | LI | 0001 |  | V01
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | [6 empty] | 65
2 | X | X | [6 empty] | 66
3 | X | X | [6 empty] | 67
4 | [8 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: 3 از 3
9184 – 073 - 053 |  | BK | GCS | IDR | 120 | PM | LI | 0001 | V01
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-IDR-120-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | IFI
1.1.2 | BK-GCS-IDR-120-PM-WB-0001 | WORK BEAKDOWN STRUCTURE | [7 empty] | IFA/AFC
1.1.3 | BK-GCS-IDR-120-GE-SH-0001 | TIME SCHEDULE | [7 empty] | IFI
1.1.4 | BK-GCS-IDR-120-GE-LI-0002 | FINAL VENDOR DATA BOOK INDEX | [7 empty] | IFI
1.1.5 | BK-GCS-IDR-120-GE-VL-0001 | SUB VENDOR LIST | [7 empty] | IFI
1.1.6 | BK-GCS-IDR-120-GE-LI-0003 | SPARE PART LIST | [7 empty] | IFI
1.2 | Reports
1.2.1 | BK-GCS-IDR-120-GE-DO-0001 | FINAL VENDOR DATA BOOK | [7 empty] | IFA/AFC
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-IDR-120-QC-PR-0001 | INSPECTION & TEST PLAN (ITP) | [7 empty] | IFA/AFC
2.1.2 | BK-GCS-IDR-120-QC-PR-0002 | FABRICATION PROCEDURE | [7 empty] | IFI
2.1.3 | BK-GCS-IDR-120-QC-PR-0003 | WPS & PQR | [7 empty] | IFA/AFC
2.1.4 | BK-GCS-IDR-120-QC-PR-0004 | NDT PROCEDURE | [7 empty] | IFA/AFC
2.1.5 | BK-GCS-IDR-120-QC-PR-0005 | WELDING REPAIR PROCEDURE | [7 empty] | IFA/AFC
2.1.6 | BK-GCS-IDR-120-QC-PR-0006 | VACUUM & OIL LEAK TEST PROCEDURE | [7 empty] | IFA/AFC
2.1.7 | BK-GCS-IDR-120-QC-PR-0007 | HYDROSTATIC TEST PROCEDURE | [7 empty] | IFA/AFC
2.1.8 | BK-GCS-IDR-120-QC-PR-0008 | BLASTING, PAINTING AND LINING PROCEDURE | [7 empty] | IFA/AFC
3 | Elevated Potable Water Tank (TK-2209)
3.1 | Calculation
3.1.1 | BK-GCS-IDR-120-ME-CN-0001 | MECHANICAL CALCULATION BOOK FOR ELEVATED POTABLE WATER TANK (TK-2209) | [7 empty] | IFI
3.2 | Drawing
3.2.1 | BK-GCS-IDR-120-ME-DW-0001 | GENERAL ARRANGEMENT FOR ELEVATED POTABLE WATER TANK (TK-2209) | [7 empty] | IFA/AFC
3.2.2 | BK-GCS-IDR-120-ME-DW-0002 | DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | [7 empty] | IFI
3.2.3 | BK-GCS-IDR-120-ME-DW-0003 | NAME PLATE DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | [7 empty] | IFA/AFC
4 | Lean Glycol Storage Tank (TK-2102)
4.1 | Calculation
4.1.1 | BK-GCS-IDR-120-ME-CN-0002 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL STORAGE TANK (TK-2102) | [7 empty] | IFI
4.1.2 | BK-GCS-IDR-120-ST-CN-0001 | ROOF STRUCTURE CALCULATION FOR LEAN GLYCOL STORAGE TANK (TK-2102) | [7 empty] | IFI
4.2 | Drawing
4.2.1 | BK-GCS-IDR-120-ME-DW-0004 | GENERAL ARRANGEMENT FOR FLEAN GLYCOL STORAGE TANK (TK-2102) | [7 empty] | IFA/AFC
4.2.2 | BK-GCS-IDR-120-ME-DW-0005 | DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | [7 empty] | IFI
4.2.3 | BK-GCS-IDR-120-ME-DW-0006 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | [7 empty] | IFA/AFC
5 | Fire Water Tanks (TK-2301 A/B)
5.1 | Calculation
5.1.1 | BK-GCS-IDR-120-ME-CN-0003 | MECHANICAL CALCULATION BOOK FOR FIRE WATER TANKS (TK-2301 A/B) | [7 empty] | IFI
5.1.2 | BK-GCS-IDR-120-ST-CN-0002 | ROOF STRUCTURE CALCULATION FOR FIRE WATER TANKS (TK-2301 A/B) | [7 empty] | IFI
5.2 | Drawing
5.2.1 | BK-GCS-IDR-120-ME-DW-0007 | GENERAL ARRANGEMENT FOR FIRE WATER TANKS (TK-2301 A/B) | [7 empty] | IFA/AFC
5.2.2 | BK-GCS-IDR-120-ME-DW-0008 | DETAIL DRAWINGS FOR FIRE WATER TANKS (TK-2301 A/B) | [7 empty] | IFI
5.2.3 | BK-GCS-IDR-120-ME-DW-0009 | NAME PLATE DETAIL DRAWING FOR FIRE WATER TANKS (TK-2301 A/B) | [7 empty] | IFA/AFC
V01