## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: -BK-GCS-IDR-120-PM-LI-0001_V00 |  |  |  |  | Vendor Tr. No.: BK-HD-PEDCO-SVTR-IDR-0001 |  |  | Transmital Date: 2025/01/04
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | Client Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-IDR-120-PM-LI-0001_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | QA/QC: مدرك زير اضافه گردد. |  | BK-SUR-ENG-MEC-03-09685 | 2024-11-12
| Packing,Marking,Shipping Procedure |  |  |  | دستورالعمل ضمیمه MR و نیز استاندارد مربوطه IPS ملاک عمل قرار می گیرد و نیازی به ارائه مدرک مجزا (که سبب تطویل کار میگردد) نمیباشد
| PWHT Procedure |  |  |  | N/A
| Material Traceability |  |  |  | در بازرسی ها بررسی میشود و لزومی به ارائه مدرک فنی در VPIS نمیباشد
| NDE Personnel Qualification List |  |  |  | در بازرسی ها بررسی میشود و لزومی به ارائه مدرک فنی در VPIS نمیباشد
| Welder Certificates List |  |  |  | در بازرسی ها بررسی میشود و لزومی به ارائه مدرک فنی در VPIS نمیباشد
2 | در بخش Drwing مدارک زیر اضافه گردد: |  | BK-SUR-ENG-MEC-03-09685 | 2024-11-12 | در قالب نقشه Details Drawing (که سامل شیت ها و عناوین مختلف است) کلیه جزئیات موردنیاز ارائه میگردد
3 | Internal Welded Attachments Drawing Lean Glycol Storage Tank
4 | Internal Welded Attachments Drawing For Fire Water Tanks
Internal Welded Attachments Drawing Elevated Potable Water Tank
External Attachment Drawing For Lean Glycol Storage Tank
External Attachment Drawing For Fire Water Tanks
5 | External Attachment Drawing Elevated Potable Water Tank
Nozzle & Manhole Detail Drawing for Lean Glycol Storage Tank
Nozzle & Manhole Detail Drawing for Fire Water Tanks
Nozzle & Manhole Detail Drawing for Elevated Potable Water Tank
Welding and NDT Map Drawing Lean Glycol Storage Tank
Welding and NDT Map Drawing Fire Water Tanks
Welding and NDT Map Drawing Elevated Potable Water Tank
Platform & Ladder Detail Drawing For All Tank.
6 | Foundation Load For All Tank.
3 | لیست لوازم یدکی دو سالانه به مدرک اضافه گردد. |  | BK-SUR-ENG-MEC-03-09685 | 2024-11-12 | ارائه شده است (List of Spare parts)
4 | Please find the attached comment. |  | BK-SUR-ENG-MEC-03-09685 | 2024-11-12 | توضیحات مربوطه موارد مندرج در پیوست ارائه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 11/12/2024 |  |  |  |  | Date: