## مشخصات پروژه (hidden)
مشخصات پروژه مخازن ذخیره ایستگاه تقویت فشار گاز بینک
ردیف | نام تجهیز | وزن تجهیز | درصد وزنی |  | نوع مخزن | تعداد کورسهای بدنه | ضخامت |  |  | قطر | ارتفاع | لدر پلتفرم | نصب | رنگ داخلی | توضیحات
[7 empty] | کف | بدنه | سقف
1 | TK-2209 | 6000 | 5.43% | 4.887% | Elevated Potable Water Tank (TK-2209) | [6 empty] | دارد / ندارد | دارد / ندارد | دارد / ندارد | ساخت در شرکت
2 | TK-2102 | 8500 | 7.692% | 6.923% | Lean Glycol Storage Tank (TK-2102) | [6 empty] | دارد / ندارد | دارد / ندارد | دارد / ندارد
3 | TK-2301A | 48000 | 43.44% | 39.1% | Fire Water Tanks (TK-2301 A) | [6 empty] | دارد / ندارد | دارد / ندارد | دارد / ندارد
4 | TK-2301A | 48000 | 43.44% | 39.1% | Fire Water Tanks (TK-2301 B) | [6 empty] | دارد / ندارد | دارد / ندارد | دارد / ندارد
|  | 110500 | 100%
90%
1 | زمان کل پروژه | 6 ماه
2 | زمان مهندسی
3 | زمان تامین
4 | زمان نصب

## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_002)
WORK BREAKDOWN STRUCTURE
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از5
9184 – 073 - 053 |  |  | BK |  | GCS | IDR | 120 |  | PM | WB | 0001 | V01
طرح نگهداشت و افزایش تولید 27 مخزن
WORK BREAKDOWN STRUCTURE نگهداشت و افزایش تولید میدان نفتی بینک
V01 |  | JAN02025 |  | AFC |  |  |  | iDrill M.E. |  |  | M.Fakharian |  | S.Faramarzpour
V00 |  | OCT. 2024 |  | IFA |  |  |  | iDrill M.E. |  |  | M.Fakharian |  | M.Sadeghian
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
CLIENT Doc. Number:
status:
IFR: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
Work Breakdown Structure
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از5
9184 – 073 - 053 |  |  | BK | GCS |  | IDR | 120 | PM | WB | 0001 |  | V01
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | [7 empty] | 65
2 | X | [7 empty] | 66
3 | X | [7 empty] | 67
4 | X | [7 empty] | 68
5 | X | [7 empty] | 69 | [8 empty] | BK-GCS-IDR-120-PM-WB-0001
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## WBS (hidden)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: | BK-GCS-AA-120-PM-WB-0001_V00 | شماره صفحه: از 4
9184 – 073 - 053
|  | Total Weight Factor | Weight Factor Sub-Level
WBS |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100 | 100
1.1 | Before Manufacturing | 10 |  | 10
1.1.1 | Pre-Inspection Meeting (PIM) | 1 |  |  | 10
1.1.2 | Documentation | 8.8 |  |  | 88
1.1.2.1 | Vendor Print Index & Schedule (VPIS) | 0.88 |  |  |  | 10
1.1.2.2 | Work Breakdown Structure | 0.88 |  |  |  | 10
1.1.2.3 | Sub-vendor List | 0.44 |  |  |  | 5
1.1.2.4 | Time Schedule | 0.616 |  |  |  | 7
1.1.2.5 | Spare Part List | 0.088 |  |  |  | 1
1.1.2.6 | Final Data Book Index | 0.088 |  |  |  | 1
1.1.2.7 | Name Plate Drawing | 0.088 |  |  |  | 1
1.1.2.8 | Final Data Book | 0.088 |  |  |  | 1
1.1.2.9 | Inspection & Test Plan (ITP) | 0.88 |  |  |  | 10
1.1.2.10 | Quality Control Plan (QCP) | 0.088 |  |  |  | 1
1.1.2.11 | W.P.S & P.Q.R | 0.088 |  |  |  | 1
1.1.2.12 | Surface Preparation and Painting Procedure (w/ Paint Datasheet) | 0.088 |  |  |  | 1
1.1.2.13 | NDE Procedure | 0.088 |  |  |  | 1
1.1.2.14 | Hydrostatic Test Procedure | 0.088 |  |  |  | 1
1.1.2.15 | SAT (Performance Test) Procedure | 0.44 |  |  |  | 5
1.1.2.16 | Installation, Operation & Maintenance Manual | 0.44 |  |  |  | 5
1.1.2.17 | Thermal/Mechanical Calculation Books | 0.44 |  |  |  | 5
1.1.2.18 | Process Data Sheet for AE-2101 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.19 | Process Data Sheet for AE-2102 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.20 | P&ID | 0.44 |  |  |  | 5
1.1.2.21 | Utility Consumption List | 0.44 |  |  |  | 5
1.1.2.22 | General Arrangement Drawings | 0.88 |  |  |  | 10
1.1.2.23 | Fan Data Sheets | 0.088 |  |  |  | 1
1.1.2.24 | Pulley Data Sheets | 0.088 |  |  |  | 1
1.1.2.25 | Vibration Switch Data Sheets and Catalogue | 0.088 |  |  |  | 1
1.1.2.26 | Motor Data Sheets | 0.088 |  |  |  | 1
1.1.2.27 | Electrical Load List | 0.176 |  |  |  | 2
1.1.2.28 | Steel Structure Calculation Books | 0.176 |  |  |  | 2
1.1.2.29 | Steel Structure Drawings | 0.176 |  |  |  | 2
1.1.2.30 | Foundation Drawings | 0.176 |  |  |  | 2
1.1.3 | Measuring & Test Equipment Calibration | 0.1 |  |  | 1
1.1.4 | NDT Personal Qualification for Air Coolers | 0.1 |  |  | 1
1.2 | Material Inspection | 40 |  | 40
1.2.1 | Verification of Raw Material (Including plate , tube , pipe) | 20 |  |  | 50
1.2.2 | Verification of Raw Material (Including flange, gasket , plug , bolt/ nut , ...) | 18 |  |  | 45
1.2.3 | Verification of Consumables Material (Including Welding Consumables, Abbrasive , paint.) | 1.6 |  |  | 4
1.2.4 | Storage of materials & welding consumable | 0.4 |  |  | 1
1.3 | During Manufacturing | 25 |  | 25
1.3.1 | Material Identification and Traceability and TRANSFER OF MATERIAL IDENTIFICATION BEFORE CUTTING | 5 |  |  | 20
1.3.2 | Visual & dimensional Inspection of joint Preparation (Beveling Inspection). | 1.25 |  |  | 5
1.3.3 | PT Examination for , beveling, | 1.25 |  |  | 5
1.3.4 | Fit-up and welding | 1.25 |  |  | 5
1.3.5 | PT root pass and back gouging | 1.25 |  |  | 5
1.3.6 | Ferrite number measurement | 1.25 |  |  | 5
1.3.7 | PT of Welds | 0.25 |  |  | 1
1.3.8 | Ultrasonic Examination | 0.25 |  |  | 1
1.3.9 | Radiographic Examination & film interpretation | 0.25 |  |  | 1
1.3.10 | Welding Major Repair | 0.25 |  |  | 1
1.3.11 | Visual and Dimensional Inspection of Header Boxes & alignment check (Nozzle to flange and header) | 1 |  |  | 4
1.3.12 | PMI of welding stainless steel | 1.25 |  |  | 5
1.3.13 | Drilling & machining | 1.25 |  |  | 5
1.3.14 | Visual & Dimensional Inspection after drilling & machining | 0.25 |  |  | 1
1.3.15 | Pickling and passivation | 1.25 |  |  | 5
1.3.16 | Visual & Dimensional assembly side frame | 1.25 |  |  | 5
1.3.17 | Tube to tube sheet welding | 1.25 |  |  | 5
1.3.18 | Finned Tube Inspection Visual and dimensional check | 3.75 |  |  | 15
1.3.19 | Tube expanding | 1.25 |  |  | 5
1.3.20 | PT for tube to tube sheet joint | 0.25 |  |  | 1
1.4 | Final Inspection | 10 |  | 10
1.4.1 | Inspection for Completed Tube Bundle | 5 |  |  | 50
1.4.1.1 | Visual & Dimensional Inspection | 2.5 |  |  |  | 50
1.4.1.2 | Hydro Test | 2.25 |  |  |  | 45
1.4.1.3 | Drying , N2 purging | 0.25 |  |  |  | 5
1.4.2 | Fan and driver assembly inspection | 0.5 |  |  | 5
1.4.2.1 | Visual & Dimensional Inspection | 0.25 |  |  |  | 50
1.4.2.2 | Balance test for pulley& belt | 0.1 |  |  |  | 20
1.4.2.3 | Assembly of rotating parts inspection | 0.05 |  |  |  | 10
1.4.2.4 | Balance test for fan blades and hubs and Shaft | 0.05 |  |  |  | 10
1.4.2.5 | Louver visual and dimentional & coating check | 0.05 |  |  |  | 10
1.4.3 | Electric Motor Inspection | 0.5 |  |  | 5
1.4.3.1 | Type test | 0.2 |  |  |  | 40
1.4.3.2 | Routine test | 0.2 |  |  |  | 40
1.4.3.3 | IP & ExX certificate rewiew | 0.1 |  |  |  | 20
1.4.4 | Instruments | 0.5 |  |  | 5
1.4.4.1 | I/P Convertor | 0.25 |  |  |  | 50
1.4.4.1.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.1.2 | Calibration | 0.025 |  |  |  |  | 10
1.4.4.1.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.4.2 | Vibration Switch | 0.25 |  |  |  | 50
1.4.4.2.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.2.2 | Test certificate | 0.025 |  |  |  |  | 10
1.4.4.2.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.5 | Steel Structure Inspection | 3.5 |  |  | 35
1.4.5.1 | Material certificate check | 1.75 |  |  |  | 50
1.4.5.2 | Steel member visual & Dimensional Inspection | 0.7 |  |  |  | 20
1.4.5.3 | Welding of steel structure | 0.7 |  |  |  | 20
1.4.5.4 | NDT after welding if any | 0.175 |  |  |  | 5
1.4.5.5 | Surface Preparation and Painting Inspection (including Side frame, fan ring, plenum, …) | 0.175 |  |  |  | 5
1.5 | Spare part Inspection | 5 |  | 5
1.5.1 | Material certificate review | 2.5 |  |  | 50
1.5.2 | VT, DT, Quantities and packing | 2.5 |  |  | 50
1.6 | Pre shippment Inspection | 10 |  | 10
1.6.1 | Prepration for shippment ( shipping mark Check) | 4 |  |  | 40
1.6.2 | Packing and Marking check (Including Packing Condition and Quantity and spare part check) | 1 |  |  | 10
1.6.3 | Touch up and Name plate stamping ( befor attaching) | 1 |  |  | 10
1.6.4 | manufacturer certificate of compliance | 0.5 |  |  | 5
1.6.5 | Issue Inspection Release Note (IRN) / Shipping Release Note by TPA | 1.5 |  |  | 15
1.6.6 | Final data book | 1 |  |  | 10
1.6.7 | IC | 0.5 |  |  | 5
1.6.8 | SAT | 0.5 |  |  | 5

## W.B.S REV 00 (hidden)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
Work Breakdown Structure
| شماره پیمان: | BK-GCS-IDR-120-PM-WB-0001 | شماره صفحه: 3 از36
| 053-073-9184 |  | Total Weight Factor
| WBS | Task Name |  | Weight Factor Sub-Level
|  |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7
1 | 1 | Overall Project | 100% | 100% | [6 empty] | 1000000000
2 | 1.1 | Start | 0% | [7 empty] | 0
3 | 1.2 | Advanced Payment Date | 0% | [7 empty] | 0
4 | 1.3 | Effective Date(Engineering) | 0% | [7 empty] | 0
5 | 1.4 | Engineering Documents | 10% |  | 10% | [5 empty] | 100000000
6 | 1.4.1 | General/ Management | 2.5% |  |  | 25% |  |  |  |  | 25000000
7 | 1.4.1.1 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
8 | 1.4.1.2 | WORK BEAKDOWN STRUCTURE | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
9 | 1.4.1.3 | TIME SCHEDULE | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
10 | 1.4.1.4 | FINAL VENDOR DATA BOOK INDEX | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
11 | 1.4.1.5 | SUB VENDOR LIST | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
12 | 1.4.1.6 | SPARE PART LIST | 0.4167% |  |  |  | 16.67% |  |  |  | 4166666.6667
13 | 1.4.2 | QA/QC(Procedure/Plan) | 2.5% |  |  | 25% |  |  |  |  | 25000000
14 | 1.4.2.1 | INSPECTION & TEST PLAN (ITP) | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
15 | 1.4.2.1.1 | Documents | 0.03125% |  |  |  |  | 10% |  |  | 312500
16 | 1.4.2.1.2 | Test and Inspection Activities | 0.2344% |  |  |  |  | 75% |  |  | 2343750
17 | 1.4.2.1.3 | INSPECTION RELEASE NOTE | 0.01563% |  |  |  |  | 5% |  |  | 156250
18 | 1.4.2.1.4 | INSPECTION CERTIFICATE | 0.03125% |  |  |  |  | 10% |  |  | 312500
19 | 1.4.2.2 | FABRICATION PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
20 | 1.4.2.3 | WPS & PQR | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
21 | 1.4.2.4 | NDT PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
22 | 1.4.2.5 | WELDING REPAIR PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
23 | 1.4.2.6 | VACUUM & OIL LEAK TEST PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
24 | 1.4.2.7 | HYDROSTATIC TEST PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
25 | 1.4.2.8 | BLASTING, PAINTING AND LINING PROCEDURE | 0.3125% |  |  |  | 12.5% |  |  |  | 3125000
26 | 1.4.3 | Calculation | 3% |  |  | 30% |  |  |  |  | 30000000
27 | 1.4.3.1 | TK-2209 | 0.1629% |  |  |  | 5.43% |  |  |  | 1628959.276
28 | 1.4.3.1.1 | MECHANICAL CALCULATION BOOK FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.1629% |  |  |  |  | 100% |  |  | 1628959.276
29 | 1.4.3.2 | TK-2102 | 0.2308% |  |  |  | 7.692% |  |  |  | 2307692.3077
30 | 1.4.3.2.1 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.1154% |  |  |  |  | 50% |  |  | 1153846.1538
31 | 1.4.3.2.2 | ROOF STRUCTURE CALCULATION FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.1154% |  |  |  |  | 50% |  |  | 1153846.1538
32 | 1.4.3.3 | TK-2301 A/B | 2.606% |  |  |  | 86.88% |  |  |  | 26063348.4163
33 | 1.4.3.3.1 | MECHANICAL CALCULATION BOOK FOR FIRE WATER TANKS (TK-2301 A/B) | 1.303% |  |  |  |  | 50% |  |  | 13031674.2081
34 | 1.4.3.3.2 | ROOF STRUCTURE CALCULATION FOR FIRE WATER TANKS (TK-2301 A/B) | 1.303% |  |  |  |  | 50% |  |  | 13031674.2081
35 | 1.4.4 | Drawing | 2% |  |  | 20% |  |  |  |  | 20000000
36 | 1.4.4.1 | TK-2209 | 0.1086% |  |  |  | 5.43% |  |  |  | 1085972.8507
37 | 1.4.4.1.1 | GENERAL ARRANGEMENT FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.07602% |  |  |  |  | 70% |  |  | 760180.9955
38 | 1.4.4.1.2 | DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.02715% |  |  |  |  | 25% |  |  | 271493.2127
39 | 1.4.4.1.3 | NAME PLATE DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.00543% |  |  |  |  | 5% |  |  | 54298.6425
40 | 1.4.4.2 | TK-2102 | 0.1538% |  |  |  | 7.692% |  |  |  | 1538461.5385
41 | 1.4.4.2.1 | GENERAL ARRANGEMENT FOR FLEAN GLYCOL STORAGE TANK (TK-2102) | 0.1077% |  |  |  |  | 70% |  |  | 1076923.0769
42 | 1.4.4.2.2 | DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.03846% |  |  |  |  | 25% |  |  | 384615.3846
43 | 1.4.4.2.3 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.007692% |  |  |  |  | 5% |  |  | 76923.0769
44 | 1.4.4.3 | TK-2301 A/B | 1.738% |  |  |  | 86.88% |  |  |  | 17375565.6109
45 | 1.4.4.3.1 | GENERAL ARRANGEMENT FOR FIRE WATER TANKS (TK-2301 A/B) | 1.216% |  |  |  |  | 70% |  |  | 12162895.9276
46 | 1.4.4.3.2 | DETAIL DRAWINGS FOR FIRE WATER TANKS (TK-2301 A/B) | 0.4344% |  |  |  |  | 25% |  |  | 4343891.4027
47 | 1.4.4.3.3 | NAME PLATE DETAIL DRAWING FOR FIRE WATER TANKS (TK-2301 A/B) | 0.08688% |  |  |  |  | 5% |  |  | 868778.2805
48 | 1.5 | Procurement | 50% |  | 50% | [5 empty] | 500000000
49 | 1.5.1 | Main Sub -Order Placed | 15% |  |  | 30% |  |  |  |  | 150000000
50 | 1.5.1.1 | Plate | 12% |  |  |  | 80% |  |  |  | 120000000
51 | 1.5.1.2 | Flange | 0.75% |  |  |  | 5% |  |  |  | 7500000
52 | 1.5.1.3 | Pipe & Fitting | 0.75% |  |  |  | 5% |  |  |  | 7500000
53 | 1.5.1.4 | Profile | 0.45% |  |  |  | 3% |  |  |  | 4500000
54 | 1.5.1.5 | Bolt & Nut | 0.15% |  |  |  | 1% |  |  |  | 1500000
55 | 1.5.1.6 | Gasket | 0.15% |  |  |  | 1% |  |  |  | 1500000
56 | 1.5.1.7 | Paint | 0.75% |  |  |  | 5% |  |  |  | 7500000
57 | 1.5.2 | Supply of Material | 35% |  |  | 70% |  |  |  |  | 350000000
58 | 1.5.2.1 | Plate | 28% |  |  |  | 80% |  |  |  | 280000000
59 | 1.5.2.2 | Flange | 1.75% |  |  |  | 5% |  |  |  | 17500000
60 | 1.5.2.3 | Pipe & Fitting | 1.75% |  |  |  | 5% |  |  |  | 17500000
61 | 1.5.2.4 | Profile | 1.05% |  |  |  | 3% |  |  |  | 10500000
62 | 1.5.2.5 | Bolt & Nut | 0.35% |  |  |  | 1% |  |  |  | 3500000
63 | 1.5.2.6 | Gasket | 0.35% |  |  |  | 1% |  |  |  | 3500000
64 | 1.5.2.7 | Paint | 1.75% |  |  |  | 5% |  |  |  | 17500000
65 | 1.6 | Manufacturing | 24% |  | 24% | [5 empty] | 240000000
66 | 1.6.1 | Elevated Potable Water Tank (TK-2209) | 1.303% |  |  | 5.43% |  |  |  |  | 13031674.2081
67 | 1.6.1.1 | Bottom plate | 0.2867% |  |  |  | 22% |  |  |  | 2866968.3258
68 | 1.6.1.1.1 | Marking & Cutting | 0.2724% |  |  |  |  | 95% |  |  | 2723619.9095
69 | 1.6.1.1.2 | Inspection | 0.01433% |  |  |  |  | 5% |  |  | 143348.4163
70 | 1.6.1.2 | Shell Plate | 0.4691% |  |  |  | 36% |  |  |  | 4691402.7149
71 | 1.6.1.2.1 | Marking & Cutting | 0.3753% |  |  |  |  | 80% |  |  | 3753122.1719
72 | 1.6.1.2.2 | rolling | 0.07037% |  |  |  |  | 15% |  |  | 703710.4072
73 | 1.6.1.2.3 | Inspection | 0.02346% |  |  |  |  | 5% |  |  | 234570.1357
74 | 1.6.1.3 | Roof Plate | 0.1564% |  |  |  | 12% |  |  |  | 1563800.905
75 | 1.6.1.3.1 | Marking & Cutting | 0.1486% |  |  |  |  | 95% |  |  | 1485610.8597
76 | 1.6.1.3.2 | Inspection | 0.007819% |  |  |  |  | 5% |  |  | 78190.0452
77 | 1.6.1.4 | ladder | 0.06516% |  |  |  | 5% |  |  |  | 651583.7104
78 | 1.6.1.4.1 | Marking & Cutting | 0.03584% |  |  |  |  | 55% |  |  | 358371.0407
79 | 1.6.1.4.2 | rolling | 0.009774% |  |  |  |  | 15% |  |  | 97737.5566
80 | 1.6.1.4.3 | Welding | 0.01629% |  |  |  |  | 25% |  |  | 162895.9276
81 | 1.6.1.4.4 | Inspection | 0.003258% |  |  |  |  | 5% |  |  | 32579.1855
82 | 1.6.1.5 | Shell Nozzle | 0.02606% |  |  |  | 2% |  |  |  | 260633.4842
83 | 1.6.1.5.1 | Marking & Cutting | 0.01433% |  |  |  |  | 55% |  |  | 143348.4163
84 | 1.6.1.5.2 | rolling | 0.00391% |  |  |  |  | 15% |  |  | 39095.0226
85 | 1.6.1.5.3 | Welding | 0.006516% |  |  |  |  | 25% |  |  | 65158.371
86 | 1.6.1.5.4 | Inspection | 0.001303% |  |  |  |  | 5% |  |  | 13031.6742
87 | 1.6.1.6 | Roof Nozzle | 0.02606% |  |  |  | 2% |  |  |  | 260633.4842
88 | 1.6.1.6.1 | Marking & Cutting | 0.01433% |  |  |  |  | 55% |  |  | 143348.4163
89 | 1.6.1.6.2 | rolling | 0.00391% |  |  |  |  | 15% |  |  | 39095.0226
90 | 1.6.1.6.3 | Welding | 0.006516% |  |  |  |  | 25% |  |  | 65158.371
91 | 1.6.1.6.4 | Inspection | 0.001303% |  |  |  |  | 5% |  |  | 13031.6742
92 | 1.6.1.7 | Channel | 0.02606% |  |  |  | 2% |  |  |  | 260633.4842
93 | 1.6.1.7.1 | Marking & Cutting | 0.01433% |  |  |  |  | 55% |  |  | 143348.4163
94 | 1.6.1.7.2 | rolling | 0.00391% |  |  |  |  | 15% |  |  | 39095.0226
95 | 1.6.1.7.3 | Welding | 0.006516% |  |  |  |  | 25% |  |  | 65158.371
96 | 1.6.1.7.4 | Inspection | 0.001303% |  |  |  |  | 5% |  |  | 13031.6742
97 | 1.6.1.8 | Insulation | 0.02606% |  |  |  | 2% |  |  |  | 260633.4842
98 | 1.6.1.8.1 | Marking & Cutting | 0.02476% |  |  |  |  | 95% |  |  | 247601.81
99 | 1.6.1.8.2 | Inspection | 0.001303% |  |  |  |  | 5% |  |  | 13031.6742
100 | 1.6.1.9 | Structure | 0.1824% |  |  |  | 14% |  |  |  | 1824434.3891
101 | 1.6.1.9.1 | Marking & Cutting | 0.146% |  |  |  |  | 80% |  |  | 1459547.5113
102 | 1.6.1.9.2 | Welding | 0.02737% |  |  |  |  | 15% |  |  | 273665.1584
103 | 1.6.1.9.3 | Inspection | 0.009122% |  |  |  |  | 5% |  |  | 91221.7195
104 | 1.6.1.10 | Pipe Support Clip | 0.01303% |  |  |  | 1% |  |  |  | 130316.7421
105 | 1.6.1.10.1 | Cutting | 0.01238% |  |  |  |  | 95% |  |  | 123800.905
106 | 1.6.1.10.2 | Inspection | 0.0006516% |  |  |  |  | 5% |  |  | 6515.8371
107 | 1.6.1.11 | Earth Lug | 0.01303% |  |  |  | 1% |  |  |  | 130316.7421
108 | 1.6.1.11.1 | Cutting | 0.01238% |  |  |  |  | 95% |  |  | 123800.905
109 | 1.6.1.11.2 | Inspection | 0.0006516% |  |  |  |  | 5% |  |  | 6515.8371
110 | 1.6.1.12 | Name Plate | 0.01303% |  |  |  | 1% |  |  |  | 130316.7421
111 | 1.6.1.12.1 | Cutting | 0.01238% |  |  |  |  | 95% |  |  | 123800.905
112 | 1.6.1.12.2 | Inspection | 0.0006516% |  |  |  |  | 5% |  |  | 6515.8371
113 | 1.6.2 | Lean Glycol Storage Tank (TK-2102) | 1.846% |  |  | 7.692% |  |  |  |  | 18461538.4615
114 | 1.6.2.1 | Bottom plate | 0.3877% |  |  |  | 21% |  |  |  | 3876923.0769
115 | 1.6.2.1.1 | Marking & Cutting | 0.3683% |  |  |  |  | 95% |  |  | 3683076.9231
116 | 1.6.2.1.2 | Inspection | 0.01938% |  |  |  |  | 5% |  |  | 193846.1538
117 | 1.6.2.2 | Drain Sump | 0.1108% |  |  |  | 6% |  |  |  | 1107692.3077
118 | 1.6.2.2.1 | Marking & Cutting | 0.06092% |  |  |  |  | 55% |  |  | 609230.7692
119 | 1.6.2.2.2 | rolling | 0.01662% |  |  |  |  | 15% |  |  | 166153.8462
120 | 1.6.2.2.3 | Welding | 0.02769% |  |  |  |  | 25% |  |  | 276923.0769
121 | 1.6.2.2.4 | Inspection | 0.005538% |  |  |  |  | 5% |  |  | 55384.6154
122 | 1.6.2.3 | Shell Plate | 0.6646% |  |  |  | 36% |  |  |  | 6646153.8462
123 | 1.6.2.3.1 | Marking & Cutting | 0.5317% |  |  |  |  | 80% |  |  | 5316923.0769
124 | 1.6.2.3.2 | rolling | 0.09969% |  |  |  |  | 15% |  |  | 996923.0769
125 | 1.6.2.3.3 | Inspection | 0.03323% |  |  |  |  | 5% |  |  | 332307.6923
126 | 1.6.2.4 | Roof Plate | 0.2215% |  |  |  | 12% |  |  |  | 2215384.6154
127 | 1.6.2.4.1 | Marking & Cutting | 0.2105% |  |  |  |  | 95% |  |  | 2104615.3846
128 | 1.6.2.4.2 | Inspection | 0.01108% |  |  |  |  | 5% |  |  | 110769.2308
129 | 1.6.2.5 | Anchor Chair | 0.09231% |  |  |  | 5% |  |  |  | 923076.9231
130 | 1.6.2.5.1 | Marking & Cutting | 0.07385% |  |  |  |  | 80% |  |  | 738461.5385
131 | 1.6.2.5.2 | rolling | 0.01385% |  |  |  |  | 15% |  |  | 138461.5385
132 | 1.6.2.5.3 | Inspection | 0.004615% |  |  |  |  | 5% |  |  | 46153.8462
133 | 1.6.2.6 | ladder&platform | 0.1292% |  |  |  | 7% |  |  |  | 1292307.6923
134 | 1.6.2.6.1 | Marking & Cutting | 0.07108% |  |  |  |  | 55% |  |  | 710769.2308
135 | 1.6.2.6.2 | rolling | 0.01938% |  |  |  |  | 15% |  |  | 193846.1538
136 | 1.6.2.6.3 | Welding | 0.03231% |  |  |  |  | 25% |  |  | 323076.9231
137 | 1.6.2.6.4 | Inspection | 0.006462% |  |  |  |  | 5% |  |  | 64615.3846
138 | 1.6.2.7 | shell Nozzle | 0.03692% |  |  |  | 2% |  |  |  | 369230.7692
139 | 1.6.2.7.1 | Marking & Cutting | 0.02031% |  |  |  |  | 55% |  |  | 203076.9231
140 | 1.6.2.7.2 | rolling | 0.005538% |  |  |  |  | 15% |  |  | 55384.6154
141 | 1.6.2.7.3 | Welding | 0.009231% |  |  |  |  | 25% |  |  | 92307.6923
142 | 1.6.2.7.4 | Inspection | 0.001846% |  |  |  |  | 5% |  |  | 18461.5385
143 | 1.6.2.8 | Roof Nozzle | 0.03692% |  |  |  | 2% |  |  |  | 369230.7692
144 | 1.6.2.8.1 | Marking & Cutting | 0.02031% |  |  |  |  | 55% |  |  | 203076.9231
145 | 1.6.2.8.2 | rolling | 0.005538% |  |  |  |  | 15% |  |  | 55384.6154
146 | 1.6.2.8.3 | Welding | 0.009231% |  |  |  |  | 25% |  |  | 92307.6923
147 | 1.6.2.8.4 | Inspection | 0.001846% |  |  |  |  | 5% |  |  | 18461.5385
148 | 1.6.2.9 | Shell manhole | 0.03692% |  |  |  | 2% |  |  |  | 369230.7692
149 | 1.6.2.9.1 | Marking & Cutting | 0.02031% |  |  |  |  | 55% |  |  | 203076.9231
150 | 1.6.2.9.2 | rolling | 0.005538% |  |  |  |  | 15% |  |  | 55384.6154
151 | 1.6.2.9.3 | Welding | 0.009231% |  |  |  |  | 25% |  |  | 92307.6923
152 | 1.6.2.9.4 | Inspection | 0.001846% |  |  |  |  | 5% |  |  | 18461.5385
153 | 1.6.2.10 | Roof manhole | 0.07385% |  |  |  | 4% |  |  |  | 738461.5385
154 | 1.6.2.10.1 | Marking & Cutting | 0.04062% |  |  |  |  | 55% |  |  | 406153.8462
155 | 1.6.2.10.2 | rolling | 0.01108% |  |  |  |  | 15% |  |  | 110769.2308
156 | 1.6.2.10.3 | Welding | 0.01846% |  |  |  |  | 25% |  |  | 184615.3846
157 | 1.6.2.10.4 | Inspection | 0.003692% |  |  |  |  | 5% |  |  | 36923.0769
158 | 1.6.2.11 | Pipe Support Clip | 0.01846% |  |  |  | 1% |  |  |  | 184615.3846
159 | 1.6.2.11.1 | Cutting | 0.01754% |  |  |  |  | 95% |  |  | 175384.6154
160 | 1.6.2.11.2 | Inspection | 0.0009231% |  |  |  |  | 5% |  |  | 9230.7692
161 | 1.6.2.12 | Earth Lug | 0.01846% |  |  |  | 1% |  |  |  | 184615.3846
162 | 1.6.2.12.1 | Cutting | 0.01754% |  |  |  |  | 95% |  |  | 175384.6154
163 | 1.6.2.12.2 | Inspection | 0.0009231% |  |  |  |  | 5% |  |  | 9230.7692
164 | 1.6.2.13 | Name Plate | 0.01846% |  |  |  | 1% |  |  |  | 184615.3846
165 | 1.6.2.13.1 | Cutting | 0.01754% |  |  |  |  | 95% |  |  | 175384.6154
166 | 1.6.2.13.2 | Inspection | 0.0009231% |  |  |  |  | 5% |  |  | 9230.7692
167 | 1.6.3 | Fire Water Tanks (TK-2301 A) | 10.43% |  |  | 43.44% |  |  |  |  | 104253393.6652
168 | 1.6.3.1 | Bottom plate | 2.085% |  |  |  | 20% |  |  |  | 20850678.733
169 | 1.6.3.1.1 | Marking & Cutting | 1.981% |  |  |  |  | 95% |  |  | 19808144.7964
170 | 1.6.3.1.2 | Inspection | 0.1043% |  |  |  |  | 5% |  |  | 1042533.9367
171 | 1.6.3.2 | Drain Sump | 0.6255% |  |  |  | 6% |  |  |  | 6255203.6199
172 | 1.6.3.2.1 | Marking & Cutting | 0.344% |  |  |  |  | 55% |  |  | 3440361.991
173 | 1.6.3.2.2 | rolling | 0.09383% |  |  |  |  | 15% |  |  | 938280.543
174 | 1.6.3.2.3 | Welding | 0.1564% |  |  |  |  | 25% |  |  | 1563800.905
175 | 1.6.3.2.4 | Inspection | 0.03128% |  |  |  |  | 5% |  |  | 312760.181
176 | 1.6.3.3 | Shell Plate | 3.128% |  |  |  | 30% |  |  |  | 31276018.0995
177 | 1.6.3.3.1 | Marking & Cutting | 2.502% |  |  |  |  | 80% |  |  | 25020814.4796
178 | 1.6.3.3.2 | rolling | 0.4691% |  |  |  |  | 15% |  |  | 4691402.7149
179 | 1.6.3.3.3 | Inspection | 0.1564% |  |  |  |  | 5% |  |  | 1563800.905
180 | 1.6.3.4 | Roof Plate | 1.251% |  |  |  | 12% |  |  |  | 12510407.2398
181 | 1.6.3.4.1 | Marking & Cutting | 1.188% |  |  |  |  | 95% |  |  | 11884886.8778
182 | 1.6.3.4.2 | Inspection | 0.06255% |  |  |  |  | 5% |  |  | 625520.362
183 | 1.6.3.5 | Anchor Chair | 0.5213% |  |  |  | 5% |  |  |  | 5212669.6833
184 | 1.6.3.5.1 | Marking & Cutting | 0.417% |  |  |  |  | 80% |  |  | 4170135.7466
185 | 1.6.3.5.2 | rolling | 0.07819% |  |  |  |  | 15% |  |  | 781900.4525
186 | 1.6.3.5.3 | Inspection | 0.02606% |  |  |  |  | 5% |  |  | 260633.4842
187 | 1.6.3.6 | ladder&platform | 0.6255% |  |  |  | 6% |  |  |  | 6255203.6199
188 | 1.6.3.6.1 | Marking & Cutting | 0.344% |  |  |  |  | 55% |  |  | 3440361.991
189 | 1.6.3.6.2 | rolling | 0.09383% |  |  |  |  | 15% |  |  | 938280.543
190 | 1.6.3.6.3 | Welding | 0.1564% |  |  |  |  | 25% |  |  | 1563800.905
191 | 1.6.3.6.4 | Inspection | 0.03128% |  |  |  |  | 5% |  |  | 312760.181
192 | 1.6.3.7 | Shell Nozzle | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
193 | 1.6.3.7.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
194 | 1.6.3.7.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
195 | 1.6.3.7.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
196 | 1.6.3.7.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
197 | 1.6.3.8 | Roof Nozzle | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
198 | 1.6.3.8.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
199 | 1.6.3.8.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
200 | 1.6.3.8.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
201 | 1.6.3.8.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
202 | 1.6.3.9 | Shell manhole | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
203 | 1.6.3.9.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
204 | 1.6.3.9.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
205 | 1.6.3.9.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
206 | 1.6.3.9.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
207 | 1.6.3.10 | Roof manhole | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
208 | 1.6.3.10.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
209 | 1.6.3.10.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
210 | 1.6.3.10.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
211 | 1.6.3.10.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
212 | 1.6.3.11 | Roof Structure | 1.043% |  |  |  | 10% |  |  |  | 10425339.3665
213 | 1.6.3.11.1 | Marking & Cutting | 0.834% |  |  |  |  | 80% |  |  | 8340271.4932
214 | 1.6.3.11.2 | Welding | 0.1564% |  |  |  |  | 15% |  |  | 1563800.905
215 | 1.6.3.11.3 | Inspection | 0.05213% |  |  |  |  | 5% |  |  | 521266.9683
216 | 1.6.3.12 | Pipe Support Clip | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
217 | 1.6.3.12.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
218 | 1.6.3.12.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
219 | 1.6.3.13 | Earth Lug | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
220 | 1.6.3.13.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
221 | 1.6.3.13.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
222 | 1.6.3.14 | Name Plate | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
223 | 1.6.3.14.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
224 | 1.6.3.14.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
225 | 1.6.4 | Fire Water Tanks (TK-2301 B) | 10.43% |  |  | 43.44% |  |  |  |  | 104253393.6652
226 | 1.6.4.1 | Bottom plate | 2.085% |  |  |  | 20% |  |  |  | 20850678.733
227 | 1.6.4.1.1 | Marking & Cutting | 1.981% |  |  |  |  | 95% |  |  | 19808144.7964
228 | 1.6.4.1.2 | Inspection | 0.1043% |  |  |  |  | 5% |  |  | 1042533.9367
229 | 1.6.4.2 | Drain Sump | 0.6255% |  |  |  | 6% |  |  |  | 6255203.6199
230 | 1.6.4.2.1 | Marking & Cutting | 0.344% |  |  |  |  | 55% |  |  | 3440361.991
231 | 1.6.4.2.2 | rolling | 0.09383% |  |  |  |  | 15% |  |  | 938280.543
232 | 1.6.4.2.3 | Welding | 0.1564% |  |  |  |  | 25% |  |  | 1563800.905
233 | 1.6.4.2.4 | Inspection | 0.03128% |  |  |  |  | 5% |  |  | 312760.181
234 | 1.6.4.3 | Shell Plate | 3.128% |  |  |  | 30% |  |  |  | 31276018.0995
235 | 1.6.4.3.1 | Marking & Cutting | 2.502% |  |  |  |  | 80% |  |  | 25020814.4796
236 | 1.6.4.3.2 | rolling | 0.4691% |  |  |  |  | 15% |  |  | 4691402.7149
237 | 1.6.4.3.3 | Inspection | 0.1564% |  |  |  |  | 5% |  |  | 1563800.905
238 | 1.6.4.4 | Roof Plate | 1.251% |  |  |  | 12% |  |  |  | 12510407.2398
239 | 1.6.4.4.1 | Marking & Cutting | 1.188% |  |  |  |  | 95% |  |  | 11884886.8778
240 | 1.6.4.4.2 | Inspection | 0.06255% |  |  |  |  | 5% |  |  | 625520.362
241 | 1.6.4.5 | Anchor Chair | 0.5213% |  |  |  | 5% |  |  |  | 5212669.6833
242 | 1.6.4.5.1 | Marking & Cutting | 0.417% |  |  |  |  | 80% |  |  | 4170135.7466
243 | 1.6.4.5.2 | rolling | 0.07819% |  |  |  |  | 15% |  |  | 781900.4525
244 | 1.6.4.5.3 | Inspection | 0.02606% |  |  |  |  | 5% |  |  | 260633.4842
245 | 1.6.4.6 | ladder&platform | 0.6255% |  |  |  | 6% |  |  |  | 6255203.6199
246 | 1.6.4.6.1 | Marking & Cutting | 0.344% |  |  |  |  | 55% |  |  | 3440361.991
247 | 1.6.4.6.2 | rolling | 0.09383% |  |  |  |  | 15% |  |  | 938280.543
248 | 1.6.4.6.3 | Welding | 0.1564% |  |  |  |  | 25% |  |  | 1563800.905
249 | 1.6.4.6.4 | Inspection | 0.03128% |  |  |  |  | 5% |  |  | 312760.181
250 | 1.6.4.7 | Shell Nozzle | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
251 | 1.6.4.7.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
252 | 1.6.4.7.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
253 | 1.6.4.7.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
254 | 1.6.4.7.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
255 | 1.6.4.8 | Roof Nozzle | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
256 | 1.6.4.8.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
257 | 1.6.4.8.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
258 | 1.6.4.8.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
259 | 1.6.4.8.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
260 | 1.6.4.9 | Shell manhole | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
261 | 1.6.4.9.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
262 | 1.6.4.9.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
263 | 1.6.4.9.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
264 | 1.6.4.9.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
265 | 1.6.4.10 | Roof manhole | 0.2085% |  |  |  | 2% |  |  |  | 2085067.8733
266 | 1.6.4.10.1 | Marking & Cutting | 0.1147% |  |  |  |  | 55% |  |  | 1146787.3303
267 | 1.6.4.10.2 | rolling | 0.03128% |  |  |  |  | 15% |  |  | 312760.181
268 | 1.6.4.10.3 | Welding | 0.05213% |  |  |  |  | 25% |  |  | 521266.9683
269 | 1.6.4.10.4 | Inspection | 0.01043% |  |  |  |  | 5% |  |  | 104253.3937
270 | 1.6.4.11 | Roof Structure | 1.043% |  |  |  | 10% |  |  |  | 10425339.3665
271 | 1.6.4.11.1 | Marking & Cutting | 0.834% |  |  |  |  | 80% |  |  | 8340271.4932
272 | 1.6.4.11.2 | Welding | 0.1564% |  |  |  |  | 15% |  |  | 1563800.905
273 | 1.6.4.11.3 | Inspection | 0.05213% |  |  |  |  | 5% |  |  | 521266.9683
274 | 1.6.4.12 | Pipe Support Clip | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
275 | 1.6.4.12.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
276 | 1.6.4.12.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
277 | 1.6.4.13 | Earth Lug | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
278 | 1.6.4.13.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
279 | 1.6.4.13.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
280 | 1.6.4.14 | Name Plate | 0.1043% |  |  |  | 1% |  |  |  | 1042533.9367
281 | 1.6.4.14.1 | Cutting | 0.09904% |  |  |  |  | 95% |  |  | 990407.2398
282 | 1.6.4.14.2 | Inspection | 0.005213% |  |  |  |  | 5% |  |  | 52126.6968
283 | 1.7 | packing | 1% |  | 1% | [5 empty] | 10000000
284 | 1.7.1 | Elevated Potable Water Tank (TK-2209) | 0.0543% |  |  | 5.43% |  |  |  |  | 542986.4253
285 | 1.7.1.1 | Structure | 0.0543% |  |  |  | 100% |  |  |  | 542986.4253
286 | 1.7.2 | Lean Glycol Storage Tank (TK-2102) | 0.07692% |  |  | 7.692% |  |  |  |  | 769230.7692
287 | 1.7.2.1 | Bottom plate | 0.01615% |  |  |  | 21% |  |  |  | 161538.4615
288 | 1.7.2.2 | Drain Sump | 0.004615% |  |  |  | 6% |  |  |  | 46153.8462
289 | 1.7.2.3 | Shell Plate | 0.02769% |  |  |  | 36% |  |  |  | 276923.0769
290 | 1.7.2.4 | Roof Plate | 0.009231% |  |  |  | 12% |  |  |  | 92307.6923
291 | 1.7.2.5 | Anchor Chair | 0.003846% |  |  |  | 5% |  |  |  | 38461.5385
292 | 1.7.2.6 | ladder&platform | 0.005385% |  |  |  | 7% |  |  |  | 53846.1538
293 | 1.7.2.7 | Shell Nozzle | 0.001538% |  |  |  | 2% |  |  |  | 15384.6154
294 | 1.7.2.8 | Roof Nozzle | 0.001538% |  |  |  | 2% |  |  |  | 15384.6154
295 | 1.7.2.9 | Shell manhole | 0.001538% |  |  |  | 2% |  |  |  | 15384.6154
296 | 1.7.2.10 | Roof manhole | 0.003077% |  |  |  | 4% |  |  |  | 30769.2308
297 | 1.7.2.11 | Pipe Support Clip | 0.0007692% |  |  |  | 1% |  |  |  | 7692.3077
298 | 1.7.2.12 | Earth Lug | 0.0007692% |  |  |  | 1% |  |  |  | 7692.3077
299 | 1.7.2.13 | Name Plate | 0.0007692% |  |  |  | 1% |  |  |  | 7692.3077
300 | 1.7.3 | Fire Water Tanks (TK-2301 A) | 0.4344% |  |  | 43.44% |  |  |  |  | 4343891.4027
301 | 1.7.3.1 | Bottom plate | 0.08688% |  |  |  | 20% |  |  |  | 868778.2805
302 | 1.7.3.2 | Drain Sump | 0.02606% |  |  |  | 6% |  |  |  | 260633.4842
303 | 1.7.3.3 | Shell Plate | 0.1303% |  |  |  | 30% |  |  |  | 1303167.4208
304 | 1.7.3.4 | Roof Plate | 0.05213% |  |  |  | 12% |  |  |  | 521266.9683
305 | 1.7.3.5 | Anchor Chair | 0.02172% |  |  |  | 5% |  |  |  | 217194.5701
306 | 1.7.3.6 | ladder&platform | 0.02606% |  |  |  | 6% |  |  |  | 260633.4842
307 | 1.7.3.7 | Shell Nozzle | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
308 | 1.7.3.8 | Roof Nozzle | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
309 | 1.7.3.9 | Shell manhole | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
310 | 1.7.3.10 | Roof manhole | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
311 | 1.7.3.11 | Roof Structure | 0.04344% |  |  |  | 10% |  |  |  | 434389.1403
312 | 1.7.3.12 | Pipe Support Clip | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
313 | 1.7.3.13 | Earth Lug | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
314 | 1.7.3.14 | Name Plate | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
315 | 1.7.4 | Fire Water Tanks (TK-2301 B) | 0.4344% |  |  | 43.44% |  |  |  |  | 4343891.4027
316 | 1.7.4.1 | Bottom plate | 0.08688% |  |  |  | 20% |  |  |  | 868778.2805
317 | 1.7.4.2 | Drain Sump | 0.02606% |  |  |  | 6% |  |  |  | 260633.4842
318 | 1.7.4.3 | Shell Plate | 0.1303% |  |  |  | 30% |  |  |  | 1303167.4208
319 | 1.7.4.4 | Roof Plate | 0.05213% |  |  |  | 12% |  |  |  | 521266.9683
320 | 1.7.4.5 | Anchor Chair | 0.02172% |  |  |  | 5% |  |  |  | 217194.5701
321 | 1.7.4.6 | ladder&platform | 0.02606% |  |  |  | 6% |  |  |  | 260633.4842
322 | 1.7.4.7 | Shell Nozzle | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
323 | 1.7.4.8 | Roof Nozzle | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
324 | 1.7.4.9 | Shell manhole | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
325 | 1.7.4.10 | Roof manhole | 0.008688% |  |  |  | 2% |  |  |  | 86877.8281
326 | 1.7.4.11 | Roof Structure | 0.04344% |  |  |  | 10% |  |  |  | 434389.1403
327 | 1.7.4.12 | Pipe Support Clip | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
328 | 1.7.4.13 | Earth Lug | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
329 | 1.7.4.14 | Name Plate | 0.004344% |  |  |  | 1% |  |  |  | 43438.914
330 | 1.8 | Erection | 14% |  | 14% | [5 empty] | 140000000
331 | 1.8.1 | Elevated Potable Water Tank (TK-2209) | 0.7602% |  |  | 5.43% |  |  |  |  | 7601809.9548
332 | 1.8.1.1 | Foundation | 0% | [7 empty] | 0
333 | 1.8.1.2 | Erection | 0.7222% |  |  |  | 95% |  |  |  | 7221719.457
334 | 1.8.1.2.1 | Bottom plate | 0.1589% |  |  |  |  | 22% |  |  | 1588778.2805
335 | 1.8.1.2.1.1 | Annular | 0.03178% | [5 empty] | 20% |  | 317755.6561
336 | 1.8.1.2.1.1.1 | Assembling | 0.01112% | [6 empty] | 35% | 111214.4796
337 | 1.8.1.2.1.1.2 | Welding | 0.02065% | [6 empty] | 65% | 206541.1765
338 | 1.8.1.2.1.2 | Bottom plate | 0.1271% | [5 empty] | 80% |  | 1271022.6244
339 | 1.8.1.2.1.2.1 | Assembling | 0.04449% | [6 empty] | 35% | 444857.9186
340 | 1.8.1.2.1.2.2 | Welding | 0.08262% | [6 empty] | 65% | 826164.7059
341 | 1.8.1.2.2 | Shell Plate | 0.26% |  |  |  |  | 36% |  |  | 2599819.0045
342 | 1.8.1.2.2.1 | Assembling | 0.09099% | [5 empty] | 35% |  | 909936.6516
343 | 1.8.1.2.2.2 | Welding | 0.169% | [5 empty] | 65% |  | 1689882.3529
344 | 1.8.1.2.3 | Roof Plate | 0.08666% |  |  |  |  | 12% |  |  | 866606.3348
345 | 1.8.1.2.3.1 | Assembling | 0.03033% | [5 empty] | 35% |  | 303312.2172
346 | 1.8.1.2.3.2 | Welding | 0.05633% | [5 empty] | 65% |  | 563294.1176
347 | 1.8.1.2.4 | ladder | 0.03611% |  |  |  |  | 5% |  |  | 361085.9729
348 | 1.8.1.2.4.1 | Assembling | 0.01264% | [5 empty] | 35% |  | 126380.0905
349 | 1.8.1.2.4.2 | Welding | 0.02347% | [5 empty] | 65% |  | 234705.8824
350 | 1.8.1.2.5 | Shell Nozzle | 0.01444% |  |  |  |  | 2% |  |  | 144434.3891
351 | 1.8.1.2.5.1 | Marking & Opening | 0.003611% | [5 empty] | 25% |  | 36108.5973
352 | 1.8.1.2.5.2 | Assembling | 0.004333% | [5 empty] | 30% |  | 43330.3167
353 | 1.8.1.2.5.3 | Welding | 0.0065% | [5 empty] | 45% |  | 64995.4751
354 | 1.8.1.2.6 | Roof Nozzle | 0.01444% |  |  |  |  | 2% |  |  | 144434.3891
355 | 1.8.1.2.6.1 | Marking & Opening | 0.003611% | [5 empty] | 25% |  | 36108.5973
356 | 1.8.1.2.6.2 | Assembling | 0.004333% | [5 empty] | 30% |  | 43330.3167
357 | 1.8.1.2.6.3 | Welding | 0.0065% | [5 empty] | 45% |  | 64995.4751
358 | 1.8.1.2.7 | Channle | 0.01444% |  |  |  |  | 2% |  |  | 144434.3891
359 | 1.8.1.2.7.1 | Marking & Opening | 0.003611% | [5 empty] | 25% |  | 36108.5973
360 | 1.8.1.2.7.2 | Assembling | 0.004333% | [5 empty] | 30% |  | 43330.3167
361 | 1.8.1.2.7.3 | Welding | 0.0065% | [5 empty] | 45% |  | 64995.4751
362 | 1.8.1.2.8 | Insulation | 0.01444% |  |  |  |  | 2% |  |  | 144434.3891
363 | 1.8.1.2.8.1 | Marking & Opening | 0.003611% | [5 empty] | 25% |  | 36108.5973
364 | 1.8.1.2.8.2 | Assembling | 0.004333% | [5 empty] | 30% |  | 43330.3167
365 | 1.8.1.2.8.3 | Welding | 0.0065% | [5 empty] | 45% |  | 64995.4751
366 | 1.8.1.2.9 | Structure | 0.1011% |  |  |  |  | 14% |  |  | 1011040.724
367 | 1.8.1.2.9.1 | Assembling | 0.03539% | [5 empty] | 35% |  | 353864.2534
368 | 1.8.1.2.9.2 | Welding | 0.06572% | [5 empty] | 65% |  | 657176.4706
369 | 1.8.1.2.10 | Pipe Support Clip | 0.007222% |  |  |  |  | 1% |  |  | 72217.1946
370 | 1.8.1.2.10.1 | Assembling | 0.002528% | [5 empty] | 35% |  | 25276.0181
371 | 1.8.1.2.10.2 | Welding | 0.004694% | [5 empty] | 65% |  | 46941.1765
372 | 1.8.1.2.11 | Earth Lug | 0.007222% |  |  |  |  | 1% |  |  | 72217.1946
373 | 1.8.1.2.11.1 | Assembling | 0.002528% | [5 empty] | 35% |  | 25276.0181
374 | 1.8.1.2.11.2 | Welding | 0.004694% | [5 empty] | 65% |  | 46941.1765
375 | 1.8.1.2.12 | Name Plate | 0.007222% |  |  |  |  | 1% |  |  | 72217.1946
376 | 1.8.1.2.12.1 | Assembling | 0.002528% | [5 empty] | 35% |  | 25276.0181
377 | 1.8.1.2.12.2 | Welding | 0.004694% | [5 empty] | 65% |  | 46941.1765
378 | 1.8.1.3 | Inspection | 0.03801% |  |  |  | 5% |  |  |  | 380090.4977
379 | 1.8.1.3.1 | Final NDT Test | 0.0019% |  |  |  |  | 5% |  |  | 19004.5249
380 | 1.8.1.3.2 | Bottom Plate Vacume Test | 0.007602% |  |  |  |  | 20% |  |  | 76018.0995
381 | 1.8.1.3.3 | Hydro Test | 0.0114% |  |  |  |  | 30% |  |  | 114027.1493
382 | 1.8.1.3.4 | Sandblast & Painting | 0.0152% |  |  |  |  | 40% |  |  | 152036.1991
383 | 1.8.1.3.5 | packing | 0.0019% |  |  |  |  | 5% |  |  | 19004.5249
384 | 1.8.2 | Lean Glycol Storage Tank (TK-2102) | 1.077% |  |  | 7.692% |  |  |  |  | 10769230.7692
385 | 1.8.2.1 | Foundation | 0% | [7 empty] | 0
386 | 1.8.2.2 | Erection | 1.023% |  |  |  | 95% |  |  |  | 10230769.2308
387 | 1.8.2.2.1 | Bottom plate | 0.2148% |  |  |  |  | 21% |  |  | 2148461.5385
388 | 1.8.2.2.1.1 | Annular | 0.04297% | [5 empty] | 20% |  | 429692.3077
389 | 1.8.2.2.1.1.1 | Assembling | 0.01504% | [6 empty] | 35% | 150392.3077
390 | 1.8.2.2.1.1.2 | Welding | 0.02793% | [6 empty] | 65% | 279300
391 | 1.8.2.2.1.2 | Bottom plate | 0.1719% | [5 empty] | 80% |  | 1718769.2308
392 | 1.8.2.2.1.2.1 | Assembling | 0.06016% | [6 empty] | 35% | 601569.2308
393 | 1.8.2.2.1.2.2 | Welding | 0.1117% | [6 empty] | 65% | 1117200
394 | 1.8.2.2.2 | Drain Sump | 0.06138% |  |  |  |  | 6% |  |  | 613846.1538
395 | 1.8.2.2.2.1 | Assembling | 0.02148% | [5 empty] | 35% |  | 214846.1538
396 | 1.8.2.2.2.2 | Welding | 0.0399% | [5 empty] | 65% |  | 399000
397 | 1.8.2.2.3 | Shell Plate | 0.3683% |  |  |  |  | 36% |  |  | 3683076.9231
398 | 1.8.2.2.3.1 | Assembling | 0.1289% | [5 empty] | 35% |  | 1289076.9231
399 | 1.8.2.2.3.2 | Welding | 0.2394% | [5 empty] | 65% |  | 2394000
400 | 1.8.2.2.4 | Roof Plate | 0.1228% |  |  |  |  | 12% |  |  | 1227692.3077
401 | 1.8.2.2.4.1 | Assembling | 0.04297% | [5 empty] | 35% |  | 429692.3077
402 | 1.8.2.2.4.2 | Welding | 0.0798% | [5 empty] | 65% |  | 798000
403 | 1.8.2.2.5 | Anchor Chair | 0.05115% |  |  |  |  | 5% |  |  | 511538.4615
404 | 1.8.2.2.5.1 | Assembling | 0.0179% | [5 empty] | 35% |  | 179038.4615
405 | 1.8.2.2.5.2 | Welding | 0.03325% | [5 empty] | 65% |  | 332500
406 | 1.8.2.2.6 | Stair Way | 0.07162% |  |  |  |  | 7% |  |  | 716153.8462
407 | 1.8.2.2.6.1 | Assembling | 0.02507% | [5 empty] | 35% |  | 250653.8462
408 | 1.8.2.2.6.2 | Welding | 0.04655% | [5 empty] | 65% |  | 465500
409 | 1.8.2.2.7 | Shell Nozzle | 0.02046% |  |  |  |  | 2% |  |  | 204615.3846
410 | 1.8.2.2.7.1 | Marking & Opening | 0.005115% | [5 empty] | 25% |  | 51153.8462
411 | 1.8.2.2.7.2 | Assembling | 0.006138% | [5 empty] | 30% |  | 61384.6154
412 | 1.8.2.2.7.3 | Welding | 0.009208% | [5 empty] | 45% |  | 92076.9231
413 | 1.8.2.2.8 | Roof Nozzle | 0.02046% |  |  |  |  | 2% |  |  | 204615.3846
414 | 1.8.2.2.8.1 | Marking & Opening | 0.005115% | [5 empty] | 25% |  | 51153.8462
415 | 1.8.2.2.8.2 | Assembling | 0.006138% | [5 empty] | 30% |  | 61384.6154
416 | 1.8.2.2.8.3 | Welding | 0.009208% | [5 empty] | 45% |  | 92076.9231
417 | 1.8.2.2.9 | Shell manhole | 0.02046% |  |  |  |  | 2% |  |  | 204615.3846
418 | 1.8.2.2.9.1 | Marking & Opening | 0.005115% | [5 empty] | 25% |  | 51153.8462
419 | 1.8.2.2.9.2 | Assembling | 0.006138% | [5 empty] | 30% |  | 61384.6154
420 | 1.8.2.2.9.3 | Welding | 0.009208% | [5 empty] | 45% |  | 92076.9231
421 | 1.8.2.2.10 | Roof manhole | 0.04092% |  |  |  |  | 4% |  |  | 409230.7692
422 | 1.8.2.2.10.1 | Marking & Opening | 0.01023% | [5 empty] | 25% |  | 102307.6923
423 | 1.8.2.2.10.2 | Assembling | 0.01228% | [5 empty] | 30% |  | 122769.2308
424 | 1.8.2.2.10.3 | Welding | 0.01842% | [5 empty] | 45% |  | 184153.8462
425 | 1.8.2.2.11 | Pipe Support Clip | 0.01023% |  |  |  |  | 1% |  |  | 102307.6923
426 | 1.8.2.2.11.1 | Assembling | 0.003581% | [5 empty] | 35% |  | 35807.6923
427 | 1.8.2.2.11.2 | Welding | 0.00665% | [5 empty] | 65% |  | 66500
428 | 1.8.2.2.12 | Earth Lug | 0.01023% |  |  |  |  | 1% |  |  | 102307.6923
429 | 1.8.2.2.12.1 | Assembling | 0.003581% | [5 empty] | 35% |  | 35807.6923
430 | 1.8.2.2.12.2 | Welding | 0.00665% | [5 empty] | 65% |  | 66500
431 | 1.8.2.2.13 | Name Plate | 0.01023% |  |  |  |  | 1% |  |  | 102307.6923
432 | 1.8.2.2.13.1 | Assembling | 0.003581% | [5 empty] | 35% |  | 35807.6923
433 | 1.8.2.2.13.2 | Welding | 0.00665% | [5 empty] | 65% |  | 66500
434 | 1.8.2.3 | Inspection | 0.05385% |  |  |  | 5% |  |  |  | 538461.5385
435 | 1.8.2.3.1 | Final NDT Test | 0.002692% |  |  |  |  | 5% |  |  | 26923.0769
436 | 1.8.2.3.2 | Bottom Plate Vacume Test | 0.01077% |  |  |  |  | 20% |  |  | 107692.3077
437 | 1.8.2.3.3 | Hydro Test | 0.01615% |  |  |  |  | 30% |  |  | 161538.4615
438 | 1.8.2.3.4 | Sandblast & Painting | 0.02154% |  |  |  |  | 40% |  |  | 215384.6154
439 | 1.8.3 | Fire Water Tanks (TK-2301 A) | 6.081% |  |  | 43.44% |  |  |  |  | 60814479.638
440 | 1.8.3.1 | Foundation | 0% | [7 empty] | 0
441 | 1.8.3.2 | Erection | 5.777% |  |  |  | 95% |  |  |  | 57773755.6561
442 | 1.8.3.2.1 | Bottom plate | 1.04% |  |  |  |  | 18% |  |  | 10399276.0181
443 | 1.8.3.2.1.1 | Annular | 0.208% | [5 empty] | 20% |  | 2079855.2036
444 | 1.8.3.2.1.1.1 | Assembling | 0.07279% | [6 empty] | 35% | 727949.3213
445 | 1.8.3.2.1.1.2 | Welding | 0.1352% | [6 empty] | 65% | 1351905.8824
446 | 1.8.3.2.1.2 | Bottom plate | 0.8319% | [5 empty] | 80% |  | 8319420.8145
447 | 1.8.3.2.1.2.1 | Assembling | 0.2912% | [6 empty] | 35% | 2911797.2851
448 | 1.8.3.2.1.2.2 | Welding | 0.5408% | [6 empty] | 65% | 5407623.5294
449 | 1.8.3.2.2 | Sandblast & Painting | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
450 | 1.8.3.2.3 | Drain Sump | 0.3466% |  |  |  |  | 6% |  |  | 3466425.3394
451 | 1.8.3.2.3.1 | Assembling | 0.1213% | [5 empty] | 35% |  | 1213248.8688
452 | 1.8.3.2.3.2 | Welding | 0.2253% | [5 empty] | 65% |  | 2253176.4706
453 | 1.8.3.2.4 | Shell Plate | 1.733% |  |  |  |  | 30% |  |  | 17332126.6968
454 | 1.8.3.2.4.1 | Assembling | 0.6066% | [5 empty] | 35% |  | 6066244.3439
455 | 1.8.3.2.4.2 | Welding | 1.127% | [5 empty] | 65% |  | 11265882.3529
456 | 1.8.3.2.5 | Roof Plate | 0.6933% |  |  |  |  | 12% |  |  | 6932850.6787
457 | 1.8.3.2.5.1 | Assembling | 0.2426% | [5 empty] | 35% |  | 2426497.7376
458 | 1.8.3.2.5.2 | Welding | 0.4506% | [5 empty] | 65% |  | 4506352.9412
459 | 1.8.3.2.6 | Anchor Chair | 0.2889% |  |  |  |  | 5% |  |  | 2888687.7828
460 | 1.8.3.2.6.1 | Assembling | 0.1011% | [5 empty] | 35% |  | 1011040.724
461 | 1.8.3.2.6.2 | Welding | 0.1878% | [5 empty] | 65% |  | 1877647.0588
462 | 1.8.3.2.7 | Stair Way | 0.3466% |  |  |  |  | 6% |  |  | 3466425.3394
463 | 1.8.3.2.7.1 | Assembling | 0.1213% | [5 empty] | 35% |  | 1213248.8688
464 | 1.8.3.2.7.2 | Welding | 0.2253% | [5 empty] | 65% |  | 2253176.4706
465 | 1.8.3.2.8 | Shell Nozzle | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
466 | 1.8.3.2.8.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
467 | 1.8.3.2.8.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
468 | 1.8.3.2.8.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
469 | 1.8.3.2.9 | Roof Nozzle | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
470 | 1.8.3.2.9.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
471 | 1.8.3.2.9.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
472 | 1.8.3.2.9.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
473 | 1.8.3.2.10 | Shell manhole | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
474 | 1.8.3.2.10.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
475 | 1.8.3.2.10.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
476 | 1.8.3.2.10.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
477 | 1.8.3.2.11 | Roof manhole | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
478 | 1.8.3.2.11.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
479 | 1.8.3.2.11.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
480 | 1.8.3.2.11.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
481 | 1.8.3.2.12 | Roof Structure | 0.5777% |  |  |  |  | 10% |  |  | 5777375.5656
482 | 1.8.3.2.12.1 | Assembling | 0.2022% | [5 empty] | 35% |  | 2022081.448
483 | 1.8.3.2.12.2 | Welding | 0.3755% | [5 empty] | 65% |  | 3755294.1176
484 | 1.8.3.2.13 | Pipe Support Clip | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
485 | 1.8.3.2.13.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
486 | 1.8.3.2.13.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
487 | 1.8.3.2.14 | Earth Lug | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
488 | 1.8.3.2.14.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
489 | 1.8.3.2.14.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
490 | 1.8.3.2.15 | Name Plate | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
491 | 1.8.3.2.15.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
492 | 1.8.3.2.15.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
493 | 1.8.3.3 | Inspection | 0.3041% |  |  |  | 5% |  |  |  | 3040723.9819
494 | 1.8.3.3.1 | Final NDT Test | 0.0152% |  |  |  |  | 5% |  |  | 152036.1991
495 | 1.8.3.3.2 | Bottom Plate Vacume Test | 0.06081% |  |  |  |  | 20% |  |  | 608144.7964
496 | 1.8.3.3.3 | Hydro Test | 0.1064% |  |  |  |  | 35% |  |  | 1064253.3937
497 | 1.8.3.3.4 | Sandblast & Painting | 0.1216% |  |  |  |  | 40% |  |  | 1216289.5928
498 | 1.8.4 | Fire Water Tanks (TK-2301 B) | 6.081% |  |  | 43.44% |  |  |  |  | 60814479.638
499 | 1.8.4.1 | Foundation | 0% | [7 empty] | 0
500 | 1.8.4.2 | Erection | 5.777% |  |  |  | 95% |  |  |  | 57773755.6561
501 | 1.8.4.2.1 | Bottom plate | 1.04% |  |  |  |  | 18% |  |  | 10399276.0181
502 | 1.8.4.2.1.1 | Annular | 0.208% | [5 empty] | 20% |  | 2079855.2036
503 | 1.8.4.2.1.1.1 | Assembling | 0.07279% | [6 empty] | 35% | 727949.3213
504 | 1.8.4.2.1.1.2 | Welding | 0.1352% | [6 empty] | 65% | 1351905.8824
505 | 1.8.4.2.1.2 | Bottom plate | 0.8319% | [5 empty] | 80% |  | 8319420.8145
506 | 1.8.4.2.1.2.1 | Assembling | 0.2912% | [6 empty] | 35% | 2911797.2851
507 | 1.8.4.2.1.2.2 | Welding | 0.5408% | [6 empty] | 65% | 5407623.5294
508 | 1.8.4.2.2 | Sandblast & Painting | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
509 | 1.8.4.2.3 | Drain Sump | 0.3466% |  |  |  |  | 6% |  |  | 3466425.3394
510 | 1.8.4.2.3.1 | Assembling | 0.1213% | [5 empty] | 35% |  | 1213248.8688
511 | 1.8.4.2.3.2 | Welding | 0.2253% | [5 empty] | 65% |  | 2253176.4706
512 | 1.8.4.2.4 | Shell Plate | 1.733% |  |  |  |  | 30% |  |  | 17332126.6968
513 | 1.8.4.2.4.1 | Assembling | 0.6066% | [5 empty] | 35% |  | 6066244.3439
514 | 1.8.4.2.4.2 | Welding | 1.127% | [5 empty] | 65% |  | 11265882.3529
515 | 1.8.4.2.5 | Roof Plate | 0.6933% |  |  |  |  | 12% |  |  | 6932850.6787
516 | 1.8.4.2.5.1 | Assembling | 0.2426% | [5 empty] | 35% |  | 2426497.7376
517 | 1.8.4.2.5.2 | Welding | 0.4506% | [5 empty] | 65% |  | 4506352.9412
518 | 1.8.4.2.6 | Anchor Chair | 0.2889% |  |  |  |  | 5% |  |  | 2888687.7828
519 | 1.8.4.2.6.1 | Assembling | 0.1011% | [5 empty] | 35% |  | 1011040.724
520 | 1.8.4.2.6.2 | Welding | 0.1878% | [5 empty] | 65% |  | 1877647.0588
521 | 1.8.4.2.7 | Stair Way | 0.3466% |  |  |  |  | 6% |  |  | 3466425.3394
522 | 1.8.4.2.7.1 | Assembling | 0.1213% | [5 empty] | 35% |  | 1213248.8688
523 | 1.8.4.2.7.2 | Welding | 0.2253% | [5 empty] | 65% |  | 2253176.4706
524 | 1.8.4.2.8 | Shell Nozzle | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
525 | 1.8.4.2.8.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
526 | 1.8.4.2.8.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
527 | 1.8.4.2.8.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
528 | 1.8.4.2.9 | Roof Nozzle | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
529 | 1.8.4.2.9.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
530 | 1.8.4.2.9.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
531 | 1.8.4.2.9.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
532 | 1.8.4.2.10 | Shell manhole | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
533 | 1.8.4.2.10.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
534 | 1.8.4.2.10.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
535 | 1.8.4.2.10.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
536 | 1.8.4.2.11 | Roof manhole | 0.1155% |  |  |  |  | 2% |  |  | 1155475.1131
537 | 1.8.4.2.11.1 | Marking & Opening | 0.02889% | [5 empty] | 25% |  | 288868.7783
538 | 1.8.4.2.11.2 | Assembling | 0.03466% | [5 empty] | 30% |  | 346642.5339
539 | 1.8.4.2.11.3 | Welding | 0.052% | [5 empty] | 45% |  | 519963.8009
540 | 1.8.4.2.12 | Roof Structure | 0.5777% |  |  |  |  | 10% |  |  | 5777375.5656
541 | 1.8.4.2.12.1 | Assembling | 0.2022% | [5 empty] | 35% |  | 2022081.448
542 | 1.8.4.2.12.2 | Welding | 0.3755% | [5 empty] | 65% |  | 3755294.1176
543 | 1.8.4.2.13 | Pipe Support Clip | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
544 | 1.8.4.2.13.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
545 | 1.8.4.2.13.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
546 | 1.8.4.2.14 | Earth Lug | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
547 | 1.8.4.2.14.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
548 | 1.8.4.2.14.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
549 | 1.8.4.2.15 | Name Plate | 0.05777% |  |  |  |  | 1% |  |  | 577737.5566
550 | 1.8.4.2.15.1 | Assembling | 0.02022% | [5 empty] | 35% |  | 202208.1448
551 | 1.8.4.2.15.2 | Welding | 0.03755% | [5 empty] | 65% |  | 375529.4118
552 | 1.8.4.3 | Inspection | 0.3041% |  |  |  | 5% |  |  |  | 3040723.9819
553 | 1.8.4.3.1 | Final NDT Test | 0.0152% |  |  |  |  | 5% |  |  | 152036.1991
554 | 1.8.4.3.2 | Bottom Plate Vacume Test | 0.06081% |  |  |  |  | 20% |  |  | 608144.7964
555 | 1.8.4.3.3 | Hydro Test | 0.1064% |  |  |  |  | 35% |  |  | 1064253.3937
556 | 1.8.4.3.4 | Sandblast & Painting | 0.1216% |  |  |  |  | 40% |  |  | 1216289.5928
557 | 1.9 | Final book | 1% |  | 1% | [5 empty] | 10000000
558 | 1.9.1 | Elevated Potable Water Tank (TK-2209) | 0.0543% |  |  | 5.43% |  |  |  |  | 542986.4253
559 | 1.9.2 | Lean Glycol Storage Tank (TK-2102) | 0.07692% |  |  | 7.692% |  |  |  |  | 769230.7692
560 | 1.9.3 | Fire Water Tanks (TK-2301 A) | 0.4344% |  |  | 43.44% |  |  |  |  | 4343891.4027
561 | 1.9.4 | Fire Water Tanks (TK-2301 B) | 0.4344% |  |  | 43.44% |  |  |  |  | 4343891.4027
562 | 1.1 | Finish | 0%

## W.B.S (ITP) (hidden)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
Work Breakdown Structure
| شماره پیمان: | BK-GCS-IDR-120-PM-WB-0001 | شماره صفحه: 3 از5
| 053-073-9184 |  | Total Weight Factor
| WBS | Task Name |  | Weight Factor Sub-Level
|  |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6
1 | 1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100% | 100% | [5 empty] | 1000000000 | 1.8
| 1.1 | Advanced Payment Date | [7 empty] | 0
| 1.2 | Effective Date | [7 empty] | 0
2 | 1.3 | PIM | 0% |  | 0% |  |  |  |  | 0
3 | 1.4 | Documentation | 5% |  | 5% |  |  |  |  | 50000000
4 | 1.4.1 | Documentation according to VPIS | 1% |  |  | 20% |  |  |  | 10000000
| 1.4.1.1 | General/ Management | 0.05% |  |  |  | 5% |  |  | 500000
| 1.4.1.1.1 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.2 | WORK BEAKDOWN STRUCTURE | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.3 | TIME SCHEDULE | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.4 | FINAL VENDOR DATA BOOK INDEX | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.5 | SUB VENDOR LIST | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.6 | SPARE PART LIST | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.1.7 | FINAL VENDOR DATA BOOK | 0.007143% |  |  |  |  | 14.29% |  | 71428.5714
| 1.4.1.2 | Procedure/Plan | 0.05% |  |  |  | 5% |  |  | 500000
| 1.4.1.2.1 | INSPECTION & TEST PLAN (ITP) | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.2 | FABRICATION PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.3 | WPS & PQR | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.4 | NDT PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.5 | WELDING REPAIR PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.6 | VACUUM & OIL LEAK TEST PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.7 | HYDROSTATIC TEST PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.2.8 | BLASTING, PAINTING AND LINING PROCEDURE | 0.00625% |  |  |  |  | 12.5% |  | 62500
| 1.4.1.3 | Elevated Potable Water Tank (TK-2209) | 0.08% |  |  |  | 8% |  |  | 800000
| 1.4.1.3.1 | Calculation | 0.048% |  |  |  |  | 60% |  | 480000
| 1.4.1.3.1.1 | MECHANICAL CALCULATION BOOK FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.048% | [5 empty] | 100% | 480000
| 1.4.1.3.2 | Drawing | 0.032% |  |  |  |  | 40% |  | 320000
| 1.4.1.3.2.1 | GENERAL ARRANGEMENT FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.016% | [5 empty] | 50% | 160000
| 1.4.1.3.2.2 | DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.0144% | [5 empty] | 45% | 144000
| 1.4.1.3.2.3 | NAME PLATE DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.0016% | [5 empty] | 5% | 16000
| 1.4.1.4 | Lean Glycol Storage Tank (TK-2102) | 0.12% |  |  |  | 12% |  |  | 1200000
| 1.4.1.4.1 | Calculation | 0.072% |  |  |  |  | 60% |  | 720000
| 1.4.1.4.1.1 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.072% | [5 empty] | 100% | 720000
| 1.4.1.4.2 | Drawing | 0.048% |  |  |  |  | 40% |  | 480000
| 1.4.1.4.2.1 | GENERAL ARRANGEMENT FOR FLEAN GLYCOL STORAGE TANK (TK-2102) | 0.024% | [5 empty] | 50% | 240000
| 1.4.1.4.2.2 | DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.0216% | [5 empty] | 45% | 216000
| 1.4.1.4.2.3 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.0024% | [5 empty] | 5% | 24000
| 1.4.1.5 | Fire Water Tanks (TK-2301 A/B) | 0.7% |  |  |  | 70% |  |  | 7000000
| 1.4.1.5.1 | Calculation | 0.42% |  |  |  |  | 60% |  | 4200000
| 1.4.1.5.1.1 | MECHANICAL CALCULATION BOOK FOR FIRE WATER TANKS (TK-2301 A/B) | 0.21% | [5 empty] | 50% | 2100000
| 1.4.1.5.1.2 | ROOF STRUCTURE CALCULATION FOR FIRE WATER TANKS (TK-2301 A/B) | 0.21% | [5 empty] | 50% | 2100000
| 1.4.1.5.2 | Drawing | 0.28% |  |  |  |  | 40% |  | 2800000
| 1.4.1.5.2.1 | GENERAL ARRANGEMENT FOR FIRE WATER TANKS (TK-2301 A/B) | 0.14% | [5 empty] | 50% | 1400000
| 1.4.1.5.2.2 | DETAIL DRAWINGS FOR FIRE WATER TANKS (TK-2301 A/B) | 0.126% | [5 empty] | 45% | 1260000
| 1.4.1.5.2.3 | NAME PLATE DETAIL DRAWING FOR FIRE WATER TANKS (TK-2301 A/B) | 0.014% | [5 empty] | 5% | 140000
5 | 1.4.2 | Welder Qualification Test (WQT) | 1% |  |  | 20% |  |  |  | 10000000
6 | 1.4.3 | PQR | 1% |  |  | 20% |  |  |  | 10000000
7 | 1.4.4 | NDT Personnel Qualification | 1% |  |  | 20% |  |  |  | 10000000
8 | 1.4.5 | Verification of Calibration Certificate | 1% |  |  | 20% |  |  |  | 10000000
9 | 1.5 | Test and Inspection Activities | 90% |  | 90% |  |  |  |  | 900000000
10 | 1.5.1 | Storage Tank (TK-2102(Glycol Storage Tank), TK-2301A, TK-2301B (Fire Water Tank)) | 85.11% |  |  | 94.57% |  |  |  | 851131221.7195
11 | 1.5.1.1 | Material Inspection | 42.56% |  |  |  | 50% |  |  | 425565610.8597
12 | 1.5.1.1.1 | Raw Material Inspection | 29.79% |  |  |  |  | 70% |  | 297895927.6018
13 | 1.5.1.1.2 | Welding Consumable | 12.77% |  |  |  |  | 30% |  | 127669683.2579
14 | 1.5.1.2 | Inspection of Shop Fabrication | 16.17% |  |  |  | 19% |  |  | 161714932.1267
15 | 1.5.1.2.1 | Marking, Cutting, Edge Preparation | 4.043% |  |  |  |  | 25% |  | 40428733.0317
16 | 1.5.1.2.2 | Welding | 6.469% |  |  |  |  | 40% |  | 64685972.8507
17 | 1.5.1.2.3 | NDT Tests (MT, PT, RT, UT) | 0.8086% |  |  |  |  | 5% |  | 8085746.6063
18 | 1.5.1.2.4 | Rolling, Saddle & Support Settlement | 4.851% |  |  |  |  | 30% |  | 48514479.638
19 | 1.5.1.3 | Loading & Shipping from Shop to Site | 4.256% |  |  |  | 5% |  |  | 42556561.086
20 | 1.5.1.3.1 | Packing & shipping Inspection | 4.256% |  |  |  |  | 100% |  | 42556561.086
21 | 1.5.1.4 | Erection | 12.77% |  |  |  | 15% |  |  | 127669683.2579
22 | 1.5.1.4.1 | Fit Up((Annular, Shell, Roof) ) | 1.915% |  |  |  |  | 15% |  | 19150452.4887
23 | 1.5.1.4.2 | Sand Blast for Bottom Plate | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
24 | 1.5.1.4.3 | Marking & Cutting of Nozzles / Manholes Locations | 1.277% |  |  |  |  | 10% |  | 12766968.3258
25 | 1.5.1.4.4 | Fit Up Nozzles / Manholes to Shell &Roof | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
26 | 1.5.1.4.5 | Fit Up Roof Structure | 1.277% |  |  |  |  | 10% |  | 12766968.3258
27 | 1.5.1.4.6 | Fit Up External / Internal Attachments | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
28 | 1.5.1.4.7 | Welding | 3.83% |  |  |  |  | 30% |  | 38300904.9774
29 | 1.5.1.4.8 | Final Inspection | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
30 | 1.5.1.4.9 | NDT (RT, PT, MT, UT, VT) | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
31 | 1.5.1.4.10 | Oil Leak Test | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
32 | 1.5.1.4.11 | Vacuum & Pad Test | 0.6383% |  |  |  |  | 5% |  | 6383484.1629
33 | 1.5.1.5 | Hydrostatic Test | 4.256% |  |  |  | 5% |  |  | 42556561.086
34 | 1.5.1.5.1 | Calibration certificate | 0.2128% |  |  |  |  | 5% |  | 2127828.0543
35 | 1.5.1.5.2 | Hydrostatic test | 4.043% |  |  |  |  | 95% |  | 40428733.0317
36 | 1.5.1.6 | Surface Preparation & painting inspection | 4.256% |  |  |  | 5% |  |  | 42556561.086
37 | 1.5.1.6.1 | Paint Material Insp. | 1.277% |  |  |  |  | 30% |  | 12766968.3258
38 | 1.5.1.6.2 | Surface Preparation | 1.277% |  |  |  |  | 30% |  | 12766968.3258
39 | 1.5.1.6.3 | Painting Inspection | 1.277% |  |  |  |  | 30% |  | 12766968.3258
40 | 1.5.1.6.4 | Final Inspection | 0.4256% |  |  |  |  | 10% |  | 4255656.1086
41 | 1.5.1.7 | Name plate | 0.8511% |  |  |  | 1% |  |  | 8511312.2172
42 | 1.5.1.7.1 | Name Plate | 0.8511% |  |  |  |  | 100% |  | 8511312.2172
43 | 1.5.2 | Potable Tank (TK-2209) | 4.887% |  |  | 5.43% |  |  |  | 48868778.2805
44 | 1.5.2.1 | Material Inspection | 2.443% |  |  |  | 50% |  |  | 24434389.1403
45 | 1.5.2.1.1 | Raw Material Inspection | 1.71% |  |  |  |  | 70% |  | 17104072.3982
46 | 1.5.2.1.2 | Welding Consumable | 0.733% |  |  |  |  | 30% |  | 7330316.7421
47 | 1.5.2.2 | Inspection During Fabrication | 1.662% |  |  |  | 34% |  |  | 16615384.6154
48 | 1.5.2.2.1 | Marking, Cutting, Edge Preparation | 0.3323% |  |  |  |  | 20% |  | 3323076.9231
49 | 1.5.2.2.2 | Rolling | 0.1662% |  |  |  |  | 10% |  | 1661538.4615
50 | 1.5.2.2.3 | Structure part Fabrication | 0.2492% |  |  |  |  | 15% |  | 2492307.6923
51 | 1.5.2.2.4 | Fit up | 0.3323% |  |  |  |  | 20% |  | 3323076.9231
52 | 1.5.2.2.5 | Welding | 0.4985% |  |  |  |  | 30% |  | 4984615.3846
53 | 1.5.2.2.6 | NDT after welding | 0.08308% |  |  |  |  | 5% |  | 830769.2308
54 | 1.5.2.3 | Final Visual & Dimensional | 0.2443% |  |  |  | 5% |  |  | 2443438.914
55 | 1.5.2.3.1 | Final Visual and Dimensional Inspection | 0.2443% |  |  |  |  | 100% |  | 2443438.914
56 | 1.5.2.4 | Hydrostatic Test | 0.2443% |  |  |  | 5% |  |  | 2443438.914
57 | 1.5.2.4.1 | Calibration certificate | 0.02443% |  |  |  |  | 10% |  | 244343.8914
58 | 1.5.2.4.2 | Hydrostatic test | 0.1955% |  |  |  |  | 80% |  | 1954751.1312
59 | 1.5.2.4.3 | Draining & Drying | 0.02443% |  |  |  |  | 10% |  | 244343.8914
60 | 1.5.2.5 | Surface Preparation & painting inspection | 0.2443% |  |  |  | 5% |  |  | 2443438.914
61 | 1.5.2.5.1 | Paint Material Insp. | 0.0733% |  |  |  |  | 30% |  | 733031.6742
62 | 1.5.2.5.2 | Surface Preparation | 0.0733% |  |  |  |  | 30% |  | 733031.6742
63 | 1.5.2.5.3 | Painting Inspection | 0.0733% |  |  |  |  | 30% |  | 733031.6742
64 | 1.5.2.5.4 | Final Inspection | 0.02443% |  |  |  |  | 10% |  | 244343.8914
65 | 1.5.2.6 | Name plate | 0.04887% |  |  |  | 1% |  |  | 488687.7828
66 | 1.5.2.6.1 | Name Plate Check | 0.02443% |  |  |  |  | 50% |  | 244343.8914
67 | 1.5.2.6.2 | Packing & Shipping Inspection | 0.02443% |  |  |  |  | 50% |  | 244343.8914
68 | 1.6 | INSPECTION RELEASE NOTE | 0% |  | 0% |  |  |  |  | 0
69 | 1.6.1 | Release Note | 0% |  |  | 100% |  |  |  | 0
70 | 1.7 | INSPECTION CERTIFICATE | 0% |  | 0% |  |  |  |  | 0
71 | 1.7.1 | Inspection Certificate | 0% |  |  | 100% |  |  |  | 0
72 | 1.8 | FINAL DATA BOOK | 5% |  | 5% |  |  |  |  | 50000000
73 | 1.8.1 | Final Document Preparation | 5% |  |  | 100% |  |  |  | 50000000

## W.B.S (ITP) (2)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
Work Breakdown Structure
| شماره پیمان: | BK-GCS-IDR-120-PM-WB-0001-V01 | شماره صفحه: 3 از5
| 053-073-9184 |  | Total Weight Factor
| WBS | Task Name |  | Weight Factor Sub-Level
|  |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6
1 | 1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100% | 100% | [5 empty] | 1000000000000 | 9
| 1.1 | Advanced Payment Date | [7 empty] | 0
| 1.2 | Effective Date | [7 empty] | 0
2 | 1.3 | PIM | 1% |  | 1% |  |  |  |  | 10000000
3 | 1.4 | Documentation | 5% |  | 5% |  |  |  |  | 50000000
4 | 1.4.1 | Documentation according to VPIS | 5% |  |  | 100% |  |  |  | 50000000
| 1.4.1.1 | General/ Management | 0.25% |  |  |  | 5% |  |  | 2500000
| 1.4.1.1.1 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.2 | WORK BEAKDOWN STRUCTURE | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.3 | TIME SCHEDULE | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.4 | FINAL VENDOR DATA BOOK INDEX | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.5 | SUB VENDOR LIST | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.6 | SPARE PART LIST | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.1.7 | FINAL VENDOR DATA BOOK | 0.03571% |  |  |  |  | 14.29% |  | 357142.8571
| 1.4.1.2 | Procedure/Plan | 0.25% |  |  |  | 5% |  |  | 2500000
| 1.4.1.2.1 | INSPECTION & TEST PLAN (ITP) | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.2 | FABRICATION PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.3 | WPS & PQR | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.4 | NDT PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.5 | WELDING REPAIR PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.6 | VACUUM & OIL LEAK TEST PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.7 | HYDROSTATIC TEST PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.2.8 | BLASTING, PAINTING AND LINING PROCEDURE | 0.03125% |  |  |  |  | 12.5% |  | 312500
| 1.4.1.3 | Elevated Potable Water Tank (TK-2209) | 0.5% |  |  |  | 10% |  |  | 5000000
| 1.4.1.3.1 | Calculation | 0.3% |  |  |  |  | 60% |  | 3000000
| 1.4.1.3.1.1 | MECHANICAL CALCULATION BOOK FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.3% | [5 empty] | 100% | 3000000
| 1.4.1.3.2 | Drawing | 0.2% |  |  |  |  | 40% |  | 2000000
| 1.4.1.3.2.1 | GENERAL ARRANGEMENT FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.12% | [5 empty] | 60% | 1200000
| 1.4.1.3.2.2 | DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.04% | [5 empty] | 20% | 400000
| 1.4.1.3.2.3 | NAME PLATE DETAIL DRAWING FOR ELEVATED POTABLE WATER TANK (TK-2209) | 0.04% | [5 empty] | 20% | 400000
| 1.4.1.4 | Lean Glycol Storage Tank (TK-2102) | 0.6% |  |  |  | 12% |  |  | 6000000
| 1.4.1.4.1 | Calculation | 0.36% |  |  |  |  | 60% |  | 3600000
| 1.4.1.4.1.1 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.36% | [5 empty] | 100% | 3600000
| 1.4.1.4.2 | Drawing | 0.24% |  |  |  |  | 40% |  | 2400000
| 1.4.1.4.2.1 | GENERAL ARRANGEMENT FOR FLEAN GLYCOL STORAGE TANK (TK-2102) | 0.144% | [5 empty] | 60% | 1440000
| 1.4.1.4.2.2 | DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.048% | [5 empty] | 20% | 480000
| 1.4.1.4.2.3 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL STORAGE TANK (TK-2102) | 0.048% | [5 empty] | 20% | 480000
| 1.4.1.5 | Fire Water Tanks (TK-2301 A/B) | 3.4% |  |  |  | 68% |  |  | 34000000
| 1.4.1.5.1 | Calculation | 2.04% |  |  |  |  | 60% |  | 20400000
| 1.4.1.5.1.1 | MECHANICAL CALCULATION BOOK FOR FIRE WATER TANKS (TK-2301 A/B) | 1.224% | [5 empty] | 60% | 12240000
| 1.4.1.5.1.2 | ROOF STRUCTURE CALCULATION FOR FIRE WATER TANKS (TK-2301 A/B) | 0.816% | [5 empty] | 40% | 8160000
| 1.4.1.5.2 | Drawing | 1.36% |  |  |  |  | 40% |  | 13600000
| 1.4.1.5.2.1 | GENERAL ARRANGEMENT FOR FIRE WATER TANKS (TK-2301 A/B) | 0.816% | [5 empty] | 60% | 8160000
| 1.4.1.5.2.2 | DETAIL DRAWINGS FOR FIRE WATER TANKS (TK-2301 A/B) | 0.272% | [5 empty] | 20% | 2720000
| 1.4.1.5.2.3 | NAME PLATE DETAIL DRAWING FOR FIRE WATER TANKS (TK-2301 A/B) | 0.272% | [5 empty] | 20% | 2720000
9 | 1.5 | Fabrication | 87% |  | 87% |  |  |  |  | 870000000
10 | 1.5.1 | Storage Tank (TK-2102(Glycol Storage Tank), TK-2301A, TK-2301B (Fire Water Tank)) | 78.3% |  |  | 90% |  |  |  | 783000000
11 | 1.5.1.1 | Material Inspection | 39.15% |  |  |  | 50% |  |  | 391500000
12 | 1.5.1.1.1 | Raw Material Inspection | 38.37% |  |  |  |  | 98% |  | 383670000
| 1.5.1.1.1.1 | Plate | 30.69% | [5 empty] | 80% | 306936000
| 1.5.1.1.1.2 | pipe & Profile | 3.837% | [5 empty] | 10% | 38367000
| 1.5.1.1.1.3 | Flange | 1.727% | [5 empty] | 4.5% | 17265150
| 1.5.1.1.1.4 | Paint | 1.727% | [5 empty] | 4.5% | 17265150
| 1.5.1.1.1.5 | etc. | 0.3837% | [5 empty] | 1% | 3836700
13 | 1.5.1.1.2 | Welding Consumable | 0.783% |  |  |  |  | 2% |  | 7830000
14 | 1.5.1.2 | Inspection of Shop Fabrication | 15.66% |  |  |  | 20% |  |  | 156600000
15 | 1.5.1.2.1 | Marking, Cutting, Edge Preparation | 8.613% |  |  |  |  | 55% |  | 86130000
| 1.5.1.2.1.1 | Body | 7.752% | [5 empty] | 90% | 77517000
| 1.5.1.2.1.2 | Nozzle | 0.2584% | [5 empty] | 3% | 2583900
| 1.5.1.2.1.3 | structure | 0.6029% | [5 empty] | 7% | 6029100
16 | 1.5.1.2.2 | Welding | 1.566% |  |  |  |  | 10% |  | 15660000
| 1.5.1.2.2.1 | Body | 1.409% | [5 empty] | 90% | 14094000
| 1.5.1.2.2.2 | Nozzle | 0.04698% | [5 empty] | 3% | 469800
| 1.5.1.2.2.3 | structure | 0.1096% | [5 empty] | 7% | 1096200
17 | 1.5.1.2.3 | NDT Tests (MT, PT, RT, UT) | 0.783% |  |  |  |  | 5% |  | 7830000
| 1.5.1.2.3.1 | Body | 0.7282% | [5 empty] | 93% | 7281900
| 1.5.1.2.3.2 | Nozzle | 0.05481% | [5 empty] | 7% | 548100
18 | 1.5.1.2.4 | Rolling, Saddle & Support Settlement | 4.698% |  |  |  |  | 30% |  | 46980000
19 | 1.5.1.3 | Loading & Shipping from Shop to Site | 1.566% |  |  |  | 2% |  |  | 15660000
20 | 1.5.1.3.1 | Packing & shipping Inspection | 1.566% |  |  |  |  | 100% |  | 15660000
21 | 1.5.1.4 | Erection | 15.66% |  |  |  | 20% |  |  | 156600000
22 | 1.5.1.4.1 | Fit Up((Annular, Shell, Roof) ) | 2.662% |  |  |  |  | 17% |  | 26622000
23 | 1.5.1.4.2 | Sand Blast for Bottom Plate | 0.6264% |  |  |  |  | 4% |  | 6264000
24 | 1.5.1.4.3 | Marking & Cutting of Nozzles / Manholes Locations | 1.566% |  |  |  |  | 10% |  | 15660000
25 | 1.5.1.4.4 | Fit Up Nozzles / Manholes to Shell &Roof | 0.6264% |  |  |  |  | 4% |  | 6264000
26 | 1.5.1.4.5 | Fit Up Roof Structure | 1.096% |  |  |  |  | 7% |  | 10962000
27 | 1.5.1.4.6 | Fit Up External / Internal Attachments | 0.6264% |  |  |  |  | 4% |  | 6264000
28 | 1.5.1.4.7 | Welding | 6.264% |  |  |  |  | 40% |  | 62640000
29 | 1.5.1.4.8 | Final Inspection | 0.5481% |  |  |  |  | 3.5% |  | 5481000
30 | 1.5.1.4.9 | NDT (RT, PT, MT, UT, VT) | 0.5481% |  |  |  |  | 3.5% |  | 5481000
31 | 1.5.1.4.10 | Oil Leak Test | 0.5481% |  |  |  |  | 3.5% |  | 5481000
32 | 1.5.1.4.11 | Vacuum & Pad Test | 0.5481% |  |  |  |  | 3.5% |  | 5481000
33 | 1.5.1.5 | Hydrostatic Test | 2.741% |  |  |  | 3.5% |  |  | 27405000
34 | 1.5.1.5.1 | Calibration certificate | 0.137% |  |  |  |  | 5% |  | 1370250
35 | 1.5.1.5.2 | Hydrostatic test | 2.603% |  |  |  |  | 95% |  | 26034750
36 | 1.5.1.6 | Surface Preparation & painting inspection | 2.741% |  |  |  | 3.5% |  |  | 27405000
37 | 1.5.1.6.1 | Paint Material Insp. | 0.8221% |  |  |  |  | 30% |  | 8221500
38 | 1.5.1.6.2 | Surface Preparation | 0.8221% |  |  |  |  | 30% |  | 8221500
39 | 1.5.1.6.3 | Painting Inspection | 0.8221% |  |  |  |  | 30% |  | 8221500
40 | 1.5.1.6.4 | Final Inspection | 0.2741% |  |  |  |  | 10% |  | 2740500
41 | 1.5.1.7 | Name plate | 0.783% |  |  |  | 1% |  |  | 7830000
42 | 1.5.1.7.1 | Name Plate check | 0.783% |  |  |  |  | 100% |  | 7830000
43 | 1.5.2 | Potable Tank (TK-2209) | 8.7% |  |  | 10% |  |  |  | 87000000
44 | 1.5.2.1 | Material Inspection | 4.35% |  |  |  | 50% |  |  | 43500000
45 | 1.5.2.1.1 | Raw Material Inspection | 4.263% |  |  |  |  | 98% |  | 42630000
| 1.5.1.1.1.1 | Plate | 3.41% | [5 empty] | 80% | 34104000
| 1.5.1.1.1.2 | pipe & Profile | 0.4263% | [5 empty] | 10% | 4263000
| 1.5.1.1.1.3 | Flange | 0.1918% | [5 empty] | 4.5% | 1918350
| 1.5.1.1.1.4 | Paint | 0.1918% | [5 empty] | 4.5% | 1918350
| 1.5.1.1.1.5 | etc. | 0.04263% | [5 empty] | 1% | 426300
46 | 1.5.2.1.2 | Welding Consumable | 0.087% |  |  |  |  | 2% |  | 870000
47 | 1.5.2.2 | Inspection During Fabrication | 2.958% |  |  |  | 34% |  |  | 29580000
48 | 1.5.2.2.1 | Marking, Cutting, Edge Preparation | 0.8874% |  |  |  |  | 30% |  | 8874000
| 1.5.1.2.1.1 | Body | 0.7543% | [5 empty] | 85% | 7542900
| 1.5.1.2.1.2 | Nozzle | 0.02662% | [5 empty] | 3% | 266220
| 1.5.1.2.1.3 | structure | 0.1065% | [5 empty] | 12% | 1064880
49 | 1.5.2.2.2 | Rolling | 0.2958% |  |  |  |  | 10% |  | 2958000
50 | 1.5.2.2.3 | Structure part Fabrication | 0.4437% |  |  |  |  | 15% |  | 4437000
51 | 1.5.2.2.4 | Fit up | 0.5916% |  |  |  |  | 20% |  | 5916000
| 1.5.1.2.1.1 | Body | 0.5502% | [5 empty] | 93% | 5501880
| 1.5.1.2.1.2 | Nozzle | 0.04141% | [5 empty] | 7% | 414120
52 | 1.5.2.2.5 | Welding | 0.5916% |  |  |  |  | 20% |  | 5916000
| 1.5.1.2.1.1 | Body | 8.01% | [5 empty] | 93% | 80100900
| 1.5.1.2.1.2 | Nozzle | 0.6029% | [5 empty] | 7% | 6029100
53 | 1.5.2.2.6 | NDT after welding | 0.1479% |  |  |  |  | 5% |  | 1479000
| 1.5.1.2.1.1 | Body | 0.1375% | [5 empty] | 93% | 1375470
| 1.5.1.2.1.2 | Nozzle | 0.01035% | [5 empty] | 7% | 103530
54 | 1.5.2.3 | Final Visual & Dimensional | 0.435% |  |  |  | 5% |  |  | 4350000
55 | 1.5.2.3.1 | Final Visual and Dimensional Inspection | 0.435% |  |  |  |  | 100% |  | 4350000
56 | 1.5.2.4 | Hydrostatic Test | 0.435% |  |  |  | 5% |  |  | 4350000
57 | 1.5.2.4.1 | Calibration certificate | 0.0435% |  |  |  |  | 10% |  | 435000
58 | 1.5.2.4.2 | Hydrostatic test | 0.348% |  |  |  |  | 80% |  | 3480000
59 | 1.5.2.4.3 | Draining & Drying | 0.0435% |  |  |  |  | 10% |  | 435000
60 | 1.5.2.5 | Surface Preparation & painting inspection | 0.435% |  |  |  | 5% |  |  | 4350000
61 | 1.5.2.5.1 | Paint Material Insp. | 0.1305% |  |  |  |  | 30% |  | 1305000
62 | 1.5.2.5.2 | Surface Preparation | 0.1305% |  |  |  |  | 30% |  | 1305000
63 | 1.5.2.5.3 | Painting Inspection | 0.1305% |  |  |  |  | 30% |  | 1305000
64 | 1.5.2.5.4 | Final Inspection | 0.0435% |  |  |  |  | 10% |  | 435000
65 | 1.5.2.6 | Name plate | 0.0435% |  |  |  | 0.5% |  |  | 435000
66 | 1.5.2.6.1 | Name Plate Check | 0.0435% |  |  |  |  | 100% |  | 435000
67 | 1.5.2.6.2 | Packing & Shipping Inspection | 0.0435% |  |  |  | 0.5% |  |  | 435000
20 | 1.5.2.6.2.1 | Packing & shipping Inspection | 0.0435% |  |  |  |  | 100% |  | 435000
68 | 1.6 | INSPECTION RELEASE NOTE | 1% |  | 1% |  |  |  |  | 10000000
69 | 1.6.1 | Release Note | 1% |  |  | 100% |  |  |  | 10000000
70 | 1.7 | INSPECTION CERTIFICATE | 1% |  | 1% |  |  |  |  | 10000000
71 | 1.7.1 | Inspection Certificate | 1% |  |  | 100% |  |  |  | 10000000
72 | 1.8 | FINAL DATA BOOK | 5% |  | 5% |  |  |  |  | 50000000
73 | 1.8.1 | Final Document Preparation | 5% |  |  | 100% |  |  |  | 50000000

## Sheet1 (hidden)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید مخازن ذخیره ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0026_00)
Time Schedule

## WBS (2) (hidden)
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: | BK-GCS-AA-120-PM-WB-0001_V00 | شماره صفحه: از 4
9184 – 073 - 053
|  | Total Weight Factor | Weight Factor Sub-Level
WBS |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100 | 100
1.1 | Before Manufacturing | 10 |  | 10
1.1.1 | Pre-Inspection Meeting (PIM) | 1 |  |  | 10
1.1.2 | Documentation | 8.8 |  |  | 88
1.1.2.1 | Documentation according to VPIS | 0.88 |  |  |  | 10
1.1.2.2 | Welder Qualification Test (WQT) | 0.88 |  |  |  | 10
1.1.2.3 | PQR | 0.44 |  |  |  | 5
1.1.2.4 | NDT Personnel Qualification | 0.616 |  |  |  | 7
1.1.2.5 | Verification of Calibration Certificate | 0.088 |  |  |  | 1
1.1.2.6 |  | 0.088 |  |  |  | 1
1.1.2.7 |  | 0.088 |  |  |  | 1
1.1.2.8 |  | 0.088 |  |  |  | 1
1.1.2.9 |  | 0.88 |  |  |  | 10
1.1.2.10 | Quality Control Plan (QCP) | 0.088 |  |  |  | 1
1.1.2.11 | W.P.S & P.Q.R | 0.088 |  |  |  | 1
1.1.2.12 | Surface Preparation and Painting Procedure (w/ Paint Datasheet) | 0.088 |  |  |  | 1
1.1.2.13 | NDE Procedure | 0.088 |  |  |  | 1
1.1.2.14 | Hydrostatic Test Procedure | 0.088 |  |  |  | 1
1.1.2.15 | SAT (Performance Test) Procedure | 0.44 |  |  |  | 5
1.1.2.16 | Installation, Operation & Maintenance Manual | 0.44 |  |  |  | 5
1.1.2.17 | Thermal/Mechanical Calculation Books | 0.44 |  |  |  | 5
1.1.2.18 | Process Data Sheet for AE-2101 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.19 | Process Data Sheet for AE-2102 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.20 | P&ID | 0.44 |  |  |  | 5
1.1.2.21 | Utility Consumption List | 0.44 |  |  |  | 5
1.1.2.22 | General Arrangement Drawings | 0.88 |  |  |  | 10
1.1.2.23 | Fan Data Sheets | 0.088 |  |  |  | 1
1.1.2.24 | Pulley Data Sheets | 0.088 |  |  |  | 1
1.1.2.25 | Vibration Switch Data Sheets and Catalogue | 0.088 |  |  |  | 1
1.1.2.26 | Motor Data Sheets | 0.088 |  |  |  | 1
1.1.2.27 | Electrical Load List | 0.176 |  |  |  | 2
1.1.2.28 | Steel Structure Calculation Books | 0.176 |  |  |  | 2
1.1.2.29 | Steel Structure Drawings | 0.176 |  |  |  | 2
1.1.2.30 | Foundation Drawings | 0.176 |  |  |  | 2
1.1.3 | Measuring & Test Equipment Calibration | 0.1 |  |  | 1
1.1.4 | NDT Personal Qualification for Air Coolers | 0.1 |  |  | 1
1.2 | Material Inspection | 40 |  | 40
1.2.1 | Verification of Raw Material (Including plate , tube , pipe) | 20 |  |  | 50
1.2.2 | Verification of Raw Material (Including flange, gasket , plug , bolt/ nut , ...) | 18 |  |  | 45
1.2.3 | Verification of Consumables Material (Including Welding Consumables, Abbrasive , paint.) | 1.6 |  |  | 4
1.2.4 | Storage of materials & welding consumable | 0.4 |  |  | 1
1.3 | During Manufacturing | 25 |  | 25
1.3.1 | Material Identification and Traceability and TRANSFER OF MATERIAL IDENTIFICATION BEFORE CUTTING | 5 |  |  | 20
1.3.2 | Visual & dimensional Inspection of joint Preparation (Beveling Inspection). | 1.25 |  |  | 5
1.3.3 | PT Examination for , beveling, | 1.25 |  |  | 5
1.3.4 | Fit-up and welding | 1.25 |  |  | 5
1.3.5 | PT root pass and back gouging | 1.25 |  |  | 5
1.3.6 | Ferrite number measurement | 1.25 |  |  | 5
1.3.7 | PT of Welds | 0.25 |  |  | 1
1.3.8 | Ultrasonic Examination | 0.25 |  |  | 1
1.3.9 | Radiographic Examination & film interpretation | 0.25 |  |  | 1
1.3.10 | Welding Major Repair | 0.25 |  |  | 1
1.3.11 | Visual and Dimensional Inspection of Header Boxes & alignment check (Nozzle to flange and header) | 1 |  |  | 4
1.3.12 | PMI of welding stainless steel | 1.25 |  |  | 5
1.3.13 | Drilling & machining | 1.25 |  |  | 5
1.3.14 | Visual & Dimensional Inspection after drilling & machining | 0.25 |  |  | 1
1.3.15 | Pickling and passivation | 1.25 |  |  | 5
1.3.16 | Visual & Dimensional assembly side frame | 1.25 |  |  | 5
1.3.17 | Tube to tube sheet welding | 1.25 |  |  | 5
1.3.18 | Finned Tube Inspection Visual and dimensional check | 3.75 |  |  | 15
1.3.19 | Tube expanding | 1.25 |  |  | 5
1.3.20 | PT for tube to tube sheet joint | 0.25 |  |  | 1
1.4 | Final Inspection | 10 |  | 10
1.4.1 | Inspection for Completed Tube Bundle | 5 |  |  | 50
1.4.1.1 | Visual & Dimensional Inspection | 2.5 |  |  |  | 50
1.4.1.2 | Hydro Test | 2.25 |  |  |  | 45
1.4.1.3 | Drying , N2 purging | 0.25 |  |  |  | 5
1.4.2 | Fan and driver assembly inspection | 0.5 |  |  | 5
1.4.2.1 | Visual & Dimensional Inspection | 0.25 |  |  |  | 50
1.4.2.2 | Balance test for pulley& belt | 0.1 |  |  |  | 20
1.4.2.3 | Assembly of rotating parts inspection | 0.05 |  |  |  | 10
1.4.2.4 | Balance test for fan blades and hubs and Shaft | 0.05 |  |  |  | 10
1.4.2.5 | Louver visual and dimentional & coating check | 0.05 |  |  |  | 10
1.4.3 | Electric Motor Inspection | 0.5 |  |  | 5
1.4.3.1 | Type test | 0.2 |  |  |  | 40
1.4.3.2 | Routine test | 0.2 |  |  |  | 40
1.4.3.3 | IP & ExX certificate rewiew | 0.1 |  |  |  | 20
1.4.4 | Instruments | 0.5 |  |  | 5
1.4.4.1 | I/P Convertor | 0.25 |  |  |  | 50
1.4.4.1.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.1.2 | Calibration | 0.025 |  |  |  |  | 10
1.4.4.1.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.4.2 | Vibration Switch | 0.25 |  |  |  | 50
1.4.4.2.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.2.2 | Test certificate | 0.025 |  |  |  |  | 10
1.4.4.2.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.5 | Steel Structure Inspection | 3.5 |  |  | 35
1.4.5.1 | Material certificate check | 1.75 |  |  |  | 50
1.4.5.2 | Steel member visual & Dimensional Inspection | 0.7 |  |  |  | 20
1.4.5.3 | Welding of steel structure | 0.7 |  |  |  | 20
1.4.5.4 | NDT after welding if any | 0.175 |  |  |  | 5
1.4.5.5 | Surface Preparation and Painting Inspection (including Side frame, fan ring, plenum, …) | 0.175 |  |  |  | 5
1.5 | Spare part Inspection | 5 |  | 5
1.5.1 | Material certificate review | 2.5 |  |  | 50
1.5.2 | VT, DT, Quantities and packing | 2.5 |  |  | 50
1.6 | Pre shippment Inspection | 10 |  | 10
1.6.1 | Prepration for shippment ( shipping mark Check) | 4 |  |  | 40
1.6.2 | Packing and Marking check (Including Packing Condition and Quantity and spare part check) | 1 |  |  | 10
1.6.3 | Touch up and Name plate stamping ( befor attaching) | 1 |  |  | 10
1.6.4 | manufacturer certificate of compliance | 0.5 |  |  | 5
1.6.5 | Issue Inspection Release Note (IRN) / Shipping Release Note by TPA | 1.5 |  |  | 15
1.6.6 | Final data book | 1 |  |  | 10
1.6.7 | IC | 0.5 |  |  | 5
1.6.8 | SAT | 0.5 |  |  | 5