## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-IDR-120-QC-PR-0008-V00 |  |  |  |  | Vendor Tr. No.: BK-HD-PEDCO-SVTR-IDR-0011 |  |  | Transmital Date: 2025/03/02
Document Title: BLASTING,PAINTING AND LINING PROCEDURE |  |  |  |  | Client Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-IDR-120-QC-PR-0008_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند3.1 استانداردهای C-TP-102 و IPS-M-TP-790 به لیست استانداردها اضافه شود. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
2 | جداول موجود در صفحات 9 تا 13 حذف شده ولی استانداردهای ارزیابی رنگ بایستی در دستورالعمل درج گردد. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
3 | در بند3.1 استانداردهای C-TP-102 و IPS-M-TP-790 به لیست استانداردها اضافه شود. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
4 | در صفحه 16 بند 11 اموارد زیر اضافه شود: ابعاد مسباره بین 0.5 تا 1.68 میلیمتر جهت سندبلاست استفاده شود و جهت رنگ زینک سیلیکات سایز مسباره 0.2تا 0.5 و حداقل پروفیل ایجاد شده در سطح بایستی 20میکرون باشد. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
5 | در بند 24 مدت زمان گارانتی از یک سال به 2 سال افزایش یابد. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
6 | بندهای 13.1 و 13.2 حذف شود./ جدول بند 22 در صفحه 27 استانداردهای بازرسی مربوط به رنگهای اتیل سیلیکات/کلتار اپوکسی/پلی اورتان/به تفکیک درج گردد. |  | BK-SUR-ENG-QAC-03-09869 | 2024-12-30 | NOTED
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.SALIMI | Signature | S.FARAMARZPOUR |  |  | Clarified By: | Signature
| Date: 12/29/2024 |  |  |  |  | Date: