## Cover
NISOC |  |  |  | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشارگاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
WORK BREAKDOWN STRUCTURE
| شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 7
| 9184 – 073 - 053 |  |  | BK |  | GCS | KP | 120 |  | GE | WB | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
WORK BREAKDOWN STRUCTURE نگهداشت و افزایش تولید میدان نفتی بینک
| V00 |  | DEC.2024 |  | IFA |  |  |  | KP |  |  | M.Fakharian |  | M.Sadeghian
| Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
[5 empty] | CLIENT Doc. Number: |  |  |  | -
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
NISOC |  |  |  | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشارگاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
WORK BREAKDOWN STRUCTURE
| شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 7
| 9184 – 073 - 053 |  |  | BK | GCS |  | KP | 120 | GE | WB | 0001 |  | V00
REVISION RECORD SHEET
Page |  | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 |  | X | [7 empty] | 61
2 |  | X | [7 empty] | 62
3 |  | X | [7 empty] | 63
4 |  | X | [7 empty] | 64
5 |  | X | [7 empty] | 65
6 |  | X | [7 empty] | 66
7 |  | X | [7 empty] | 67
8 | [9 empty] | 68
9 | [9 empty] | 69
10 | [9 empty] | 70
11 | [9 empty] | 71
12 | [9 empty] | 72
13 | [9 empty] | 73
14 | [9 empty] | 74
15 | [9 empty] | 75
16 | [9 empty] | 76
17 | [9 empty] | 77
18 | [9 empty] | 78
19 | [9 empty] | 79
20 | [9 empty] | 80
21 | [9 empty] | 81
22 | [9 empty] | 82
23 | [9 empty] | 83
24 | [9 empty] | 84
25 | [9 empty] | 85
26 | [9 empty] | 86
27 | [9 empty] | 87
28 | [9 empty] | 88
29 | [9 empty] | 89
30 | [9 empty] | 90
31 | [9 empty] | 91
32 | [9 empty] | 92
33 | [9 empty] | 93
34 | [9 empty] | 94
35 | [9 empty] | 95
36 | [9 empty] | 96
37 | [9 empty] | 97
38 | [9 empty] | 98
39 | [9 empty] | 99
40 | [9 empty] | 100
41 | [9 empty] | 101
42 | [9 empty] | 102
43 | [9 empty] | 103
44 | [9 empty] | 104
45 | [9 empty] | 105
46 | [9 empty] | 106
47 | [9 empty] | 107
48 | [9 empty] | 108
49 | [9 empty] | 109
50 | [9 empty] | 110
51 | [9 empty] | 111
52 | [9 empty] | 112
53 | [9 empty] | 113
54 | [9 empty] | 114
55 | [9 empty] | 115
56 | [9 empty] | 116
57 | [9 empty] | 117
58 | [9 empty] | 118
59 | [9 empty] | 119
60 | [9 empty] | 120

## Note 1
NISOC |  | نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشارگاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
WORK BREAKDOWN STRUCTURE
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: 3 از 7
9184 – 073 - 053 |  | BK | GCS | KP | 120 | GE | WB | 0001 | V00
| WBS code | Activity Name | [7 empty] | W.F | W.V
| 1 | Fire Water Pumps | [7 empty] | 100% | 100%
| 1.1 | KOM & PIM | [7 empty] | 1% | 1%
| 1.2 | Engineering | [7 empty] | 5% | 5%
| 1.2.1 | General/Management | [7 empty] | 14% | 0.7%
| 1.2.1.1 | List | [7 empty] | 74.29% | 0.52%
| 1.2.1.1.1 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | 19.23% | 0.1%
| 1.2.1.1.2 | WORK BREAKDOWN STRUCTURE | [7 empty] | 19.23% | 0.1%
| 1.2.1.1.3 | SUB VENDOR LIST | [7 empty] | 15.38% | 0.08%
| 1.2.1.1.4 | TIME SCHEDULE | [7 empty] | 15.38% | 0.08%
| 1.2.1.1.5 | SPARE PART LIST | [7 empty] | 15.38% | 0.08%
| 1.2.1.1.6 | FINAL DATA BOOK INDEX | [7 empty] | 15.38% | 0.08%
| 1.2.1.2 | DWG/Diagram | [7 empty] | 25.71% | 0.18%
| 1.2.1.2.1 | NAME PLATE DWGS | [7 empty] | 100% | 0.18%
| 1.2.2 | QA/QC | [7 empty] | 21.4% | 1.07%
| 1.2.2.1 | Procedure/Plan | [7 empty] | 81.31% | 0.87%
| 1.2.2.1.1 | INSPECTION & TEST PLAN (ITP) | [7 empty] | 17.24% | 0.15%
| 1.2.2.1.2 | SURFACE PREPARATION AND PAINTING PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.3 | NDE PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.4 | BALANCE PROCEDURE (FOR IMPELLERS) | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.5 | HYDROSTATIC TEST PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.6 | MECHANICAL RUNNING TEST PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.7 | PERFORMANCE TEST PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.8 | PACKING, MARKING AND SHIPPING PROCEDURE FOR FIRE WATER PUMPS | [7 empty] | 10.34% | 0.09%
| 1.2.2.1.9 | SAT PROCEDURE | [7 empty] | 10.34% | 0.09%
| 1.2.2.2 | Manual | [7 empty] | 18.69% | 0.2%
| 1.2.2.2.1 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | [7 empty] | 100% | 0.2%
| 1.2.3 | Process/Safety | [7 empty] | 4.6% | 0.23%
| 1.2.3.1 | Philosophy | [7 empty] | 34.78% | 0.08%
| 1.2.3.1.1 | CONTROL PHILOSOPHY | [7 empty] | 100% | 0.08%
| 1.2.3.2 | DWG/Diagram | [7 empty] | 65.22% | 0.15%
| 1.2.3.2.1 | P&ID | [7 empty] | 100% | 0.15%
| 1.2.4 | Mechanical | [7 empty] | 35.8% | 1.79%
| 1.2.4.1 | Datasheet | [7 empty] | 27.93% | 0.5%
| 1.2.4.1.1 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | 30% | 0.15%
| 1.2.4.1.2 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | 30% | 0.15%
| 1.2.4.1.3 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER JOCKEY PUMPS | [7 empty] | 30% | 0.15%
| 1.2.4.1.4 | SPECIFICATION FOR DIESEL ENGINE | [7 empty] | 10% | 0.05%
| 1.2.4.2 | DWG/Diagram | [7 empty] | 72.07% | 1.29%
| 1.2.4.2.1 | GAD FOR FIRE WATER MAIN DIESEL PUMPS | [7 empty] | 11.63% | 0.15%
| 1.2.4.2.2 | GAD FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | 11.63% | 0.15%
| 1.2.4.2.3 | GAD FOR FIRE WATER JOCKEY PUMPS | [7 empty] | 11.63% | 0.15%
| 1.2.4.2.4 | GAD FOR DAILY TANK | [7 empty] | 11.63% | 0.15%
| 1.2.4.2.5 | CROSS SECTIONAL DWG FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.6 | CROSS SECTIONAL DWG FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.7 | CROSS SECTIONAL DWG FOR FIRE WATER JOCKEY PUMPS | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.8 | COUPLING ASSEMBLY DWG FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.9 | COUPLING ASSEMBLY DWG FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.10 | COUPLING ASSEMBLY DWG FOR FIRE WATER JOCKEY PUMPS | [7 empty] | 7.752% | 0.1%
| 1.2.4.2.11 | DWG FOR MECHANICAL SEAL | [7 empty] | 6.977% | 0.09%
| 1.2.5 | Instrument | [7 empty] | 15.2% | 0.76%
| 1.2.5.1 | Datasheet | [7 empty] | 31.58% | 0.24%
| 1.2.5.1.1 | AUTOMATIC AIR RELEASE VALVE SPECIFICATION & CATALOGUE | [7 empty] | 33.33% | 0.08%
| 1.2.5.1.2 | PRESSURE RELIEF VALVE SPECIFICATION | [7 empty] | 33.33% | 0.08%
| 1.2.5.1.3 | CIRCULATION RELIEF VALVE SPECIFICATION & DWG | [7 empty] | 33.33% | 0.08%
| 1.2.5.2 | List | [7 empty] | 21.05% | 0.16%
| 1.2.5.2.1 | INSTRUMENT LIST | [7 empty] | 50% | 0.08%
| 1.2.5.2.2 | I/O LIST | [7 empty] | 50% | 0.08%
| 1.2.5.3 | DWG/Diagram | [7 empty] | 47.37% | 0.36%
| 1.2.5.3.1 | GAD & WIRING DIAGRAM FOR DIESEL CONTROL PANEL | [7 empty] | 25% | 0.09%
| 1.2.5.3.2 | GAD & WIRING DIAGRAM FOR ELECTRICAL CONTROL PANEL | [7 empty] | 25% | 0.09%
| 1.2.5.3.3 | GAD & WIRING DIAGRAM FOR JOCKEY CONTROL PANEL | [7 empty] | 25% | 0.09%
| 1.2.5.3.4 | HOOK-UP DIAGRAM FOR FIRE WATER PUMPS | [7 empty] | 25% | 0.09%
| 1.2.6 | Electrical | [7 empty] | 9% | 0.45%
| 1.2.6.1 | Datasheet | [7 empty] | 40% | 0.18%
| 1.2.6.1.1 | MOTOR DATA SHEET FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | 50% | 0.09%
| 1.2.6.1.2 | MOTOR DATA SHEET FOR FIRE WATER MAIN JOCKEY PUMPS | [7 empty] | 50% | 0.09%
| 1.2.6.3 | DWG/Diagram | [7 empty] | 20% | 0.09%
| 1.2.6.3.1 | ELECTRICAL WIRING DIAGRAM | [7 empty] | 100% | 0.09%
| 1.2.6.2 | List | [7 empty] | 40% | 0.18%
| 1.2.6.2.1 | ELECTRICAL LOAD LIST | [7 empty] | 50% | 0.09%
| 1.2.6.2.2 | ELECTRICAL CABLE LIST | [7 empty] | 50% | 0.09%
| 1.3 | Raw Material Supply (Pump Casing, Impleller & Shaft) | [7 empty] | 38.29% | 38.29%
| 1.3.1 | P-2301A ( Electrical Pump) | [7 empty] | 31.08% | 11.9%
| 1.3.1.1 | Casing | [7 empty] | 64.71% | 7.7%
| 1.3.1.1.1 | Casting | [7 empty] | 90.91% | 7%
| 1.3.1.1.2 | Sampling | [7 empty] | 9.091% | 0.7%
| 1.3.1.2 | Impeller | [7 empty] | 27.73% | 3.3%
| 1.3.1.2.1 | Casting | [7 empty] | 90.91% | 3%
| 1.3.1.2.2 | Sampling | [7 empty] | 9.091% | 0.3%
| 1.3.1.3 | Shaft | [7 empty] | 7.563% | 0.9%
| 1.3.1.3.1 | Sampling | [7 empty] | 33.33% | 0.3%
| 1.3.1.3.2 | UT | [7 empty] | 66.67% | 0.6%
| 1.3.2 | P-2301B ( Diesel Pump) | [7 empty] | 40.22% | 15.4%
| 1.3.2.1 | Casing | [7 empty] | 64.29% | 9.9%
| 1.3.2.1.1 | Casting | [7 empty] | 90.91% | 9%
| 1.3.2.1.2 | Sampling | [7 empty] | 9.091% | 0.9%
| 1.3.2.2 | Impeller | [7 empty] | 28.57% | 4.4%
| 1.3.2.2.1 | Casting | [7 empty] | 90.91% | 4%
| 1.3.2.2.2 | Sampling | [7 empty] | 9.091% | 0.4%
| 1.3.2.3 | Shaft | [7 empty] | 7.143% | 1.1%
| 1.3.2.3.1 | Sampling | [7 empty] | 36.36% | 0.4%
| 1.3.2.3.2 | UT | [7 empty] | 63.64% | 0.7%
| 1.3.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 28.7% | 10.99%
| 1.3.3.1 | Casing | [7 empty] | 60.05% | 6.6%
| 1.3.3.1.1 | Casting | [7 empty] | 90.91% | 6%
| 1.3.3.1.2 | Sampling | [7 empty] | 9.091% | 0.6%
| 1.3.3.2 | Impeller | [7 empty] | 34.58% | 3.8%
| 1.3.3.2.1 | Casting | [7 empty] | 92.11% | 3.5%
| 1.3.3.2.2 | Sampling | [7 empty] | 7.895% | 0.3%
| 1.3.3.3 | Shaft | [7 empty] | 5.369% | 0.59%
| 1.3.3.3.1 | Sampling | [7 empty] | 33.9% | 0.2%
| 1.3.3.3.2 | UT | [7 empty] | 66.1% | 0.39%
| 1.4 | Other Equipment & Devices Supply | [7 empty] | 26.62% | 26.62%
| 1.4.1 | Electromotor | [7 empty] | 30.05% | 8%
| 1.4.1.1 | P-2301A ( Electrical Pump) | [7 empty] | 62.5% | 5%
| 1.4.1.1.1 | Supplier Documents (Type Test & Routine Test) | [7 empty] | 100% | 5%
| 1.4.1.2 | P-2302AB ( Jockey Pumps) | [7 empty] | 37.5% | 3%
| 1.4.1.2.1 | Supplier Documents (Type Test & Routine Test) | [7 empty] | 100% | 3%
| 1.4.2 | Diesel Engine | [7 empty] | 37.57% | 10%
| 1.4.3 | Control Panel | [7 empty] | 18.78% | 5%
| 1.4.3.1 | P-2301A ( Electrical Pump) | [7 empty] | 40% | 2%
| 1.4.3.1.1 | Control Panel FAT Test | [7 empty] | 50% | 1%
| 1.4.3.1.2 | IP Test | [7 empty] | 50% | 1%
| 1.4.3.2 | P-2301B ( Diesel Pump) | [7 empty] | 40% | 2%
| 1.4.3.2.1 | Control Panel FAT Test | [7 empty] | 50% | 1%
| 1.4.3.2.2 | IP Test | [7 empty] | 50% | 1%
| 1.4.3.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 111.1% | 1%
| 1.4.3.3.1 | Control Panel FAT Test | [7 empty] | 50% | 0.5%
| 1.4.3.3.2 | IP Test | [7 empty] | 50% | 0.5%
| 1.4.4 | Instrument | [7 empty] | 3.005% | 0.8%
| 1.4.5 | Bearing | [7 empty] | 3.005% | 0.8%
| 1.4.6 | PRV | [7 empty] | 2.066% | 0.55%
| 1.4.7 | CRV | [7 empty] | 2.066% | 0.55%
| 1.4.8 | Packing / Mechanical Seal | [7 empty] | 2.254% | 0.6%
| 1.4.9 | Bolt & Nut | [7 empty] | 0.7513% | 0.2%
| 1.4.10 | Consumable Material (Paint, Electrode, …) | [7 empty] | 0.4508% | 0.12%
| 1.5 | Manufacturing | [7 empty] | 21.59% | 21.59%
| 1.5.1 | Casing | [7 empty] | 9.819% | 2.12%
| 1.5.1.1 | P-2301A ( Electrical Pump) | [7 empty] | 33.02% | 0.7%
| 1.5.1.1.1 | Visual & Dimensional Inspection | [7 empty] | 35.71% | 0.25%
| 1.5.1.1.2 | Liquid Penetrant Test (Machining Part ) | [7 empty] | 21.43% | 0.15%
| 1.5.1.1.3 | Hydrostatic Test | [7 empty] | 42.86% | 0.3%
| 1.5.1.2 | P-2301B ( Diesel Pump) | [7 empty] | 47.17% | 1%
| 1.5.1.2.1 | Visual & Dimensional Inspection | [7 empty] | 35% | 0.35%
| 1.5.1.2.2 | Liquid Penetrant Test (Machining Part ) | [7 empty] | 20% | 0.2%
| 1.5.1.2.3 | Hydrostatic Test | [7 empty] | 45% | 0.45%
| 1.5.1.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 19.81% | 0.42%
| 1.5.1.3.1 | Visual & Dimensional Inspection | [7 empty] | 40.48% | 0.17%
| 1.5.1.3.2 | Liquid Penetrant Test (Machining Part ) | [7 empty] | 23.81% | 0.1%
| 1.5.1.3.3 | Hydrostatic Test | [7 empty] | 35.71% | 0.15%
| 1.5.2 | Impeller | [7 empty] | 14.36% | 3.1%
| 1.5.2.1 | P-2301A ( Electrical Pump) | [7 empty] | 30% | 0.93%
| 1.5.2.1.1 | Visual and Dimensional Check | [7 empty] | 80.65% | 0.75%
| 1.5.2.1.2 | Liquid Penetrant Test (Machining Part) | [7 empty] | 19.35% | 0.18%
| 1.5.2.2 | P-2301B ( Diesel Pump) | [7 empty] | 46.77% | 1.45%
| 1.5.2.2.1 | Visual and Dimensional Check | [7 empty] | 82.76% | 1.2%
| 1.5.2.2.2 | Liquid Penetrant Test (Machining Part) | [7 empty] | 17.24% | 0.25%
| 1.5.2.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 23.23% | 0.72%
| 1.5.2.3.1 | Visual and Dimensional Check | [7 empty] | 83.33% | 0.6%
| 1.5.2.3.2 | Liquid Penetrant Test (Machining Part) | [7 empty] | 16.67% | 0.12%
| 1.5.3 | Shaft | [7 empty] | 9.356% | 2.02%
| 1.5.3.1 | P-2301A ( Electrical Pump) | [7 empty] | 30.69% | 0.62%
| 1.5.3.1.1 | Visual and Dimensional Check | [7 empty] | 80.65% | 0.5%
| 1.5.3.1.2 | Balance Test Assembled Impeller and Shaft | [7 empty] | 14.52% | 0.09%
| 1.5.3.1.3 | PT | [7 empty] | 4.839% | 0.03%
| 1.5.3.2 | P-2301B ( Diesel Pump) | [7 empty] | 49.01% | 0.99%
| 1.5.3.2.1 | Visual and Dimensional Check | [7 empty] | 80.81% | 0.8%
| 1.5.3.2.2 | Balance Test Assembled Impeller and Shaft | [7 empty] | 15.15% | 0.15%
| 1.5.3.2.3 | PT | [7 empty] | 4.04% | 0.04%
| 1.5.3.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 20.3% | 0.41%
| 1.5.3.3.1 | Visual and Dimensional Check | [7 empty] | 85.37% | 0.35%
| 1.5.3.3.2 | Balance Test Assembled Impeller and Shaft | [7 empty] | 9.756% | 0.04%
| 1.5.3.3.3 | PT | [7 empty] | 4.878% | 0.02%
| 1.5.4 | Fuel Oil Daily Tank | [7 empty] | 3.937% | 0.85%
| 1.5.4.1 | Visual & Dimensional Check | [7 empty] | 52.94% | 0.45%
| 1.5.4.2 | Leakage Test | [7 empty] | 29.41% | 0.25%
| 1.5.4.3 | Liquid Penetrant Test | [7 empty] | 17.65% | 0.15%
| 1.5.5 | Pumps with Job Diesel & Pumps with Job Motors | [7 empty] | 62.53% | 13.5%
| 1.5.5.1 | P-2301A ( Electrical Pump) | [7 empty] | 37.04% | 5%
| 1.5.5.1.1 | Performance Test | [7 empty] | 70% | 3.5%
| 1.5.5.1.2 | Mechanical Running Test (Bearing Temperature Noise Level , Vibration Check) | [7 empty] | 30% | 1.5%
| 1.5.5.2 | P-2301B ( Diesel Pump) | [7 empty] | 37.04% | 5%
| 1.5.5.2.1 | Performance Test | [7 empty] | 70% | 3.5%
| 1.5.5.2.2 | Mechanical Running Test (Bearing Temperature Noise Level , Vibration Check) | [7 empty] | 30% | 1.5%
| 1.5.5.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 25.93% | 3.5%
| 1.5.5.3.1 | Performance Test | [7 empty] | 71.43% | 2.5%
| 1.5.5.3.2 | Mechanical Running Test (Bearing Temperature Noise Level , Vibration Check) | [7 empty] | 28.57% | 1%
| 1.6 | Final Inspection | [7 empty] | 2.498% | 2.498%
| 1.6.1 | P-2301A ( Electrical Pump) | [7 empty] | 34.43% | 0.86%
| 1.6.1.1 | Surface preparation prior to painting, coating, lining | [7 empty] | 13.08% | 0.1125%
| 1.6.1.2 | Painting (Final Layer) DFT & Ral & Adhesion | [7 empty] | 13.08% | 0.1125%
| 1.6.1.3 | Name Plate Check | [7 empty] | 26.16% | 0.225%
| 1.6.1.4 | Spare Parts | [7 empty] | 14.53% | 0.125%
| 1.6.1.5 | Packing & Marking | [7 empty] | 17.44% | 0.15%
| 1.6.1.6 | Final Inspection & Visual & Dimensional Check | [7 empty] | 10.47% | 0.09%
| 1.6.1.7 | Release Note | [7 empty] | 2.907% | 0.025%
| 1.6.1.8 | IC | [7 empty] | 2.326% | 0.02%
| 1.6.2 | P-2301B ( Diesel Pump) | [7 empty] | 53.55% | 1.337%
| 1.6.2.1 | Surface preparation prior to painting, coating, lining | [7 empty] | 16.82% | 0.225%
| 1.6.2.2 | Painting (Final Layer) DFT & Ral & Adhesion | [7 empty] | 19.44% | 0.26%
| 1.6.2.3 | Name Plate Check | [7 empty] | 22.43% | 0.3%
| 1.6.2.4 | Spare Parts | [7 empty] | 11.21% | 0.15%
| 1.6.2.5 | Packing & Marking | [7 empty] | 18.69% | 0.25%
| 1.6.2.6 | Final Inspection & Visual & Dimensional Check | [7 empty] | 7.477% | 0.1%
| 1.6.2.7 | Release Note | [7 empty] | 2.243% | 0.03%
| 1.6.2.8 | IC | [7 empty] | 1.682% | 0.0225%
| 1.6.3 | P-2302AB ( Jockey Pumps) | [7 empty] | 12.01% | 0.3%
| 1.6.3.1 | Surface preparation prior to painting, coating, lining | [7 empty] | 8.333% | 0.025%
| 1.6.3.2 | Painting (Final Layer) DFT & Ral & Adhesion | [7 empty] | 10% | 0.03%
| 1.6.3.3 | Name Plate Check | [7 empty] | 15% | 0.045%
| 1.6.3.4 | Spare Parts | [7 empty] | 30% | 0.09%
| 1.6.3.5 | Packing & Marking | [7 empty] | 13.33% | 0.04%
| 1.6.3.6 | Final Inspection & Visual & Dimensional Check | [7 empty] | 13.33% | 0.04%
| 1.6.3.7 | Release Note | [7 empty] | 5% | 0.015%
| 1.6.3.8 | IC | [7 empty] | 5% | 0.015%
| 1.7 | Final Data Book | [7 empty] | 5% | 5%
| 1.7.1 | Final Book Check | [7 empty] | 100% | 5%