## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 4
9184 – 073 - 053 |  |  | BK |  | GCS | KP | 120 |  | PM | LI | 0001 | V01
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V01 |  | DEC.2024 |  | AFC |  |  |  | Kalaye Pump Co. |  |  | M.Fakharian |  | M.Sadeghian
V00 |  | MAR.2024 |  | IFA |  |  |  | Kalaye Pump Co. |  |  | M.Fakharian |  | S.Faramarz Pour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 4
9184 – 073 - 053 |  |  | BK | GCS |  | HY | 120 | PM | LI | 0001 |  | V01
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | [6 empty] | 65
2 | X | X | [6 empty] | 66
3 | X | [7 empty] | 67
4 | X | [7 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج پمپ های آب آتشنشانی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0023_00)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: از 4
9184 – 073 - 053 |  | BK | GCS | KP | 120 | PM | LI | 0001 | V01
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-KP-120-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | IFA/AFC
1.1.2 | BK-GCS-KP-120-GE-WB-0001 | WORK BREAKDOWN STRUCTURE | [7 empty] | IFA/AFC
1.1.3 | BK-GCS-KP-120-GE-VL-0001 | SUB VENDOR LIST | [7 empty] | IFA/AFC
1.1.4 | BK-GCS-KP-120-GE-SH-0001 | TIME SCHEDULE | [7 empty] | IFI
1.1.5 | BK-GCS-KP-120-GE-LI-0001 | SPARE PART LIST | [7 empty] | IFA/AFC
1.1.6 | BK-GCS-KP-120-GE-LI-0002 | FINAL DATA BOOK INDEX | [7 empty] | IFA/AFC
1.2 | DWG/Diagram
1.2.1 | BK-GCS-KP-120-GE-DW-0001 | NAME PLATE DWGS | [7 empty] | IFA/AFC
1.3 | Reports
1.3.1 | BK-GCS-KP-120-GE-DO-0001 | FINAL DATA BOOK | [7 empty] | IFA/AFC
1.4 | Manual
1.4.1 | BK-GCS-KP-120-GE-ML-0001 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | [7 empty] | IFI
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-KP-120-QC-PR-0001 | INSPECTION & TEST PLAN (ITP) | [7 empty] | IFA/AFC
2.1.2 | BK-GCS-KP-120-QC-PR-0002 | SURFACE PREPARATION AND PAINTING PROCEDURE | [7 empty] | IFA/AFC
2.1.3 | BK-GCS-KP-120-QC-PR-0003 | NDE PROCEDURE | [7 empty] | IFA/AFC
2.1.6 | BK-GCS-KP-120-QC-PR-0004 | BALANCE PROCEDURE (FOR IMPELLERS) | [7 empty] | IFA/AFC
2.1.4 | BK-GCS-KP-120-QC-PR-0005 | HYDROSTATIC TEST PROCEDURE | [7 empty] | IFA/AFC
2.1.5 | BK-GCS-KP-120-QC-PR-0006 | MECHANICAL RUNNING TEST PROCEDURE | [7 empty] | IFA/AFC
2.1.5 | BK-GCS-KP-120-QC-PR-0007 | PERFORMANCE TEST PROCEDURE | [7 empty] | IFA/AFC
2.1.8 | BK-GCS-KP-120-QC-PR-0008 | PACKING, MARKING AND SHIPPING PROCEDURE FOR FIRE WATER PUMPS | [7 empty] | IFA/AFC
2.1.9 | BK-GCS-KP-120-QC-PR-0009 | SAT PROCEDURE | [7 empty] | IFA/AFC
3 | Process/Safety
3.1 | Philosophy
3.1.1 | BK-GCS-KP-120-PR-PH-0001 | CONTROL PHILOSOPHY | [7 empty] | IFA/AFC
3.2 | DWG/Diagram
3.2.1 | BK-GCS-KP-120-PR-PI-0001 | P&I D | [7 empty] | IFA/AFC
4 | Mechanical
4.2 | Datasheet
4.2.1 | BK-GCS-KP-120-ME-DS-0001 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | IFA/AFC
4.2.2 | BK-GCS-KP-120-ME-DS-0002 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | IFA/AFC
4.2.3 | BK-GCS-KP-120-ME-DS-0003 | DATA SHEETS (W/PERFORMANCE CURVE) FOR FIRE WATER JOCKEY PUMPS | [7 empty] | IFA/AFC
4.2.5 | BK-GCS-KP-120-ME-DS-0004 | DATA SHEETS FOR DIESEL ENGINE | [7 empty] | IFA/AFC
4.1 | DWG/Diagram
4.1.1 | BK-GCS-KP-120-ME-DW-0001 | GAD FOR FIRE WATER MAIN DIESEL PUMPS | [7 empty] | IFA/AFC
4.1.2 | BK-GCS-KP-120-ME-DW-0002 | GAD FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | IFA/AFC
4.1.3 | BK-GCS-KP-120-ME-DW-0003 | GAD FOR FIRE WATER JOCKEY PUMPS | [7 empty] | IFA/AFC
4.1.4 | BK-GCS-KP-120-ME-DW-0004 | GAD FOR DAILY TANK | [7 empty] | IFA/AFC
4.1.5 | BK-GCS-KP-120-ME-DW-0005 | CROSS SECTIONAL DWG FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | IFI
4.1.6 | BK-GCS-KP-120-ME-DW-0006 | CROSS SECTIONAL DWG FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | IFI
4.1.7 | BK-GCS-KP-120-ME-DW-0007 | CROSS SECTIONAL DWG FOR FIRE WATER JOCKEY PUMPS | [7 empty] | IFI
4.1.8 | BK-GCS-KP-120-ME-DW-0008 | COUPLING ASSEMBLY DWG FOR FIRE WATER MAIN DIESEL PUMP | [7 empty] | IFI
4.1.9 | BK-GCS-KP-120-ME-DW-0009 | COUPLING ASSEMBLY DWG FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | IFI
4.1.10 | BK-GCS-KP-120-ME-DW-0010 | COUPLING ASSEMBLY DWG FOR FIRE WATER JOCKEY PUMPS | [7 empty] | IFI
4.1.20 | BK-GCS-KP-120-ME-DW-0011 | DWG FOR MECHANICAL SEAL | [7 empty] | IFI
5 | Instrument
5.1 | Datasheet
5.1.1 | BK-GCS-KP-120-ME-DS-0001 | AUTOMATIC AIR RELEASE VALVE DATA SHEET & CATALOGUE | [7 empty] | IFA/AFC
5.1.2 | BK-GCS-KP-120-ME-DS-0002 | PRESSURE RELIEF VALVE DATA SHEET & DWG | [7 empty] | IFA/AFC
5.1.3 | BK-GCS-KP-120-ME-DS-0003 | CIRCULATION RELIEF VALVE DATA SHEET & DWG | [7 empty] | IFA/AFC
5.2 | List
5.2.1 | BK-GCS-KP-120-IN-LI-0001 | INSTRUMENT LIST | [7 empty] | IFI
5.2.2 | BK-GCS-KP-120-IN-LI-0002 | I/O LIST | [7 empty] | IFI
5.3 | DWG/Diagram
5.3.1 | BK-GCS-KP-120-IN-DW-0001 | GAD & WIRING DIAGRAM FOR DIESEL CONTROL PANEL | [7 empty] | IFA/AFC
5.3.2 | BK-GCS-KP-120-IN-DW-0002 | GAD & WIRING DIAGRAM FOR ELECTRICAL CONTROL PANEL | [7 empty] | IFA/AFC
5.3.3 | BK-GCS-KP-120-IN-DW-0003 | GAD & WIRING DIAGRAM FOR JOCKEY CONTROL PANEL | [7 empty] | IFA/AFC
5.3.4 | BK-GCS-KP-120-IN-DW-0004 | HOOK-UP DIAGRAM FOR FIRE WATER PUMPS | [7 empty] | IFI
6 | Electrical
6.1 | Datasheet
6.1.1 | BK-GCS-KP-120-EL-DS-0001 | MOTOR DATA SHEET FOR FIRE WATER MAIN ELECTRICAL PUMP | [7 empty] | IFA/AFC
6.1.2 | BK-GCS-KP-120-EL-DS-0002 | MOTOR DATA SHEET FOR FIRE WATER MAIN JOCKEY PUMPS | [7 empty] | IFA/AFC
6.2 | DWG/Diagram
6.2.1 | BK-GCS-KP-120-EL-DW-0001 | ELECTRICAL WIRING DIAGRAM | [7 empty] | IFI
6.3 | List
6.3.1 | BK-GCS-KP-120-EL-LI-0001 | ELECTRICAL LOAD LIST | [7 empty] | IFA/AFC
6.3.2 | BK-GCS-KP-120-EL-LI-0002 | ELECTRICAL CABLE LIST | [7 empty] | IFI