## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-PM-LI-0001-V00 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-KP-0001 |  |  | Transmital Date: 2024/12/21
[5 empty] | CRS No:PECO- CRS-BK-GCS-KP-120-PM-LI-0001_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments :
1 | Find attached file. |  | BK-SUR-ENG-MEC-03-09195 | 2024-04-03 | با توجه به تایید مدرک توسط NISOC و در راستای تسریع فرآیند طراحی/مهندسی و و ساخت تجهیزات مربوطه، با هماهنگی با سرپرست محترم مهندسی پروژه آن کارفرای محترم (با جایجایی رویه نصب/راه اندازی به بخش عمومی) مدرک AFC میگردد .
Electrical comments :
1 | Find attached file. |  | BK-SUR-ENG-MEC-03-09195 | 2024-04-03
Instrument comments :
1 | - دیتا شیت تمامی ادوات ابزاردقیق و کنترلی می بایست اضافه گردد. - در خصوص LCP و Control Panel دیتاشیت ارایه گردد. - Control System Configuration ارایه شود. - تایید گردد که Final Data book برای تمامی ادوات (شامل دیتاشیت،‌ کاتالوگ و گواهینامه ها)‌ارایه می گردد. لازم است که لوپ های Safety می بایست SIL Certify باشند. - FAT/SAT Procedure و FAT/SAT Report ارایه گردد، لازم به ذکر است که نتایج تست FAT برای سیستم کنترل می بایست در مدرک جداگانه یا مدرک جنرال بخش جداگانه ارایه گردد. - Logic Diagram ارایه گردد. - Loop Diagram ارایه گردد. - Cable route Drawing ارایه گردد. - Alarm and setpoint List ارایه گردد. |  | BK-SUR-ENG-MEC-03-09195 | 2024-04-06
QC comments :
| مدارک زیر اضافه گردد: 1- WPS & PQR 2- FAT Procedure for Control Panel 3- Leakage Test Procedure for Fuel Oil Daily Tank 4- NPSH Test Procedure |  | BK-SUR-ENG-MEC-03-09195 | 2024-04-03
| نام مدرک Balance Procedure (For Impellers) به Balance Test Procedure (For Impeller and Shaft) تغییر یابد. |  | BK-SUR-ENG-MEC-03-09195 | 2024-04-03
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 4/2/2024 |  |  |  |  | Date: