## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-ML-0001 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date: 2025/02/26
Document Title: INSTALLATION, OPERATION & MAINTENANCE MANUAL |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0308-ME-TR-KP-0015 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-ML-0001_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحه فهرست عناوين مطالب فاقد شماره سرفصل و ساير عناوين مطالب مي باشد.همچنين در متن اين دستورالعمل شماره هاي مطالب مذكور ارائه گردد |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-22 | اصلاح گردید.
2 | نسخه بعدي اين مدرك (بخش راه اندازي و بهره برداري )با ذكر Tag هاي نقشه P&ID تاييد شده و همينطور ساب وندورها بازنگري شود |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-22 | مربوط به مدرک P&ID .
3 | زمانهاي Periodical inspection و تعويضكليه قطعات اصلي و يدكي قيد شده در سيستم CMMS جدول بندي و به پيوست ارائه گردد |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-22 | زمان های لازم در داخل متن در جاهای مناسب اشاره شده و نیازی به جدول بندی نیست.
4 | در مورد نكات و مخاطرات ايمني پمپ مذكور در عمليات بهره برداري و نگهداري بخشي جداگانه (هم در فهرست مطالب و هم در متن اين مدرك)تدوين گردد. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-22 | نکات لازم در متن و در جای ضروری اشاره شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Noei Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:1/22/2025 |  |  |  |  | Date: