## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-PR-0002_V01 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date: 2025/02/26
Document Title: SURFACE PREPARATION AND PAINTING PROCEDURE |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0309-QC-TR-KP-0015 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-PR-0002_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Quality of adhetion shall be consider 4B |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | در روش X-Cut تنها 4A مورد تایید است |  |  | Noted
2 | Project painitng specification shall be refered here. |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | Confirm. |  |  | Noted
3 | Below item shall be expalined in procedure of painting : 1- PRELIMINARY PREPARATION 2-SURFACE PREPARATION BY SAND BLASTING 3-FINAL CLEANING 4- ENVIRONMENTAL CONDITION 5- REPAIR METHOD |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | Confirm. |  |  | Noted
V01
| Adhesion Tests shall be list of standard shall be added in first section of document such as ISO 4624,ISO 2409,ISO 6272. ASTM D4587.ISO 8501-1 |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Confirm.
| Aceptance test in section 8.0 , shall be mentioned based on which ASTM Project specification No. shall be added |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Confirm.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 1/19/2025 |  |  |  |  | Date: