## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-PR-0003_V01 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date:2025/02/26
Document Title: NDE PROCEDURE |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0309-QC-TR-KP-0015 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-PR-0003_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | International organization for standardization ISO ,ISO- 3452-1 NDT pt part 1 -part4 part 5 testing at temperature above 50C part 6 testing at temperature under10 C ISO-12706 ISO-23277 PT for weld shall be added |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | N/A.
2 | ASTM e 165 ASME e 1417 ASME e 1209 fluorescent water washable shall be added |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | N/A.
3 | Article 8 outlines the procedures and requirements for Visual Examination (VT), which is one of the most common and simplest forms of NDE used for inspecting materials and welds. Why it is not applicable. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Our instruction is sufficient.
4 | AS per standard, developer shall be consider 7 min for Steel Or Cast Iron |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | we test it harder.
5 | the other section of document have not well-organized, please check all the clause and consider in table of content in next revision. The comments will be provided in next revision. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Please clarify.
1
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:1/19/2025 |  |  |  |  | Date: