## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-PR-0004_V01 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date: 2025/02/26
Document Title: BALANCE PROCEDURE (FOR IMPELLERS) |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0309-QC-TR-KP-0015 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-PR-0004_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | According to ISO 1940-1, maximum residual unbalance for this rotor shall be less than 264 gr.mm. please add this sentence in your procedure |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | Please Clarify 264. |  |  | The value of 264 gr·mm is the permissible residual unbalance for a rotor when balancing to a defined quality grade , so The specific 264 gr·mm figure would depend on the rotor’s characteristics (e.g., mass and speed) as per the balance quality grade specified in the table or the formula within these clause 6. and Fig 2. generally the value is less than this specified valueto meet the grade of the balance (Gr2.5) as per project sepecification.
2 | Balancing Specifications shall be mentioned as per below: Assembled rotating components weight, Largest Diameter Balancing Speed Unbalance correction method |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | Only impeller is balancing according to diameter of impeller. Correction method is mentioned in 7-1-7, by trim. |  |  | Noted
3 | Sample Balancing Report FORM shall be added in this section |  | BK-SUR-ENG-QAC-03-09757 | 2024-12-10 | Confirm. |  |  | Noted
V01
1 | Repeated comment : According to ISO 1940-1, maximum residual unbalance for this rotor shall be less than 264 gr.mm. please add this sentence in your procedure |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | N/A. This item in Shahin Tanzim Sanat Co. calculated according to standard.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:1/19/2025 |  |  |  |  | Date: