## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-PR-0008_V01 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date: 2025/02/26
Document Title: PACKING, MARKING AND SHIPPING PROCEDURE FOR FIRE WATER PUMPS |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0309-QC-TR-KP-0015 |  |  | Transmital Date: 2025/02/26
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-PR-0008_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | proejct packing shipping procedure shall be followed and refereed in Clause 4.0 |  | BK-SUR-ENG-QAC-03-09757 |  | Confirm. |  |  | Noted, Document No. shall be added
2 | these items shall be considered in wooden box: Preliminary Shipping Information for Space Booking P.O Number Requisition No. Cargo Description Total Number of Packages Total Net Weight Total Gross Weight Total Measurement Port of Loading |  | BK-SUR-ENG-QAC-03-09757 |  | Confirm. |  |  | Noted, it shall be added in document.
V01
| Previous comment has not propoly applied and it will be checked in next revision |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Please clarify.
| to be added in the packaing procedure Inspection and Quality Assurance Pre-shipment Inspection: Conduct visual and dimensional checks to confirm the product meets specifications. Inspect packaging for integrity and durability. Testing Documentation: Provide results of functional and performance tests conducted before packing to reassure the client of the product's readiness. Photographic Evidence: Document the condition of the packed goods to serve as proof in case of transit-related claims. Third-party Certification: Engage external inspection agencies if specified by the client for independent verification. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Confirm.
| to be added in the packaing procedure Accompanying Documentation Operation Manuals: Provide detailed instructions for installation, operation, and troubleshooting. Test Certificates: Include factory acceptance test (FAT) reports and material test certificates (MTC) as applicable.or any relevant Certificate. Packing List: Ensure it itemizes all contents, including dimensions, weight, and part numbers for easy cross-reference.( same as pervious comment) |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Confirm.
| the wooden box only accepted, "Carton" word shall be removed totally from the this procedure. nylon and belt also is not acceptable, please remove it |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Confirm.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:1/19/2025 |  |  |  |  | Date: