## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-KP-120-QC-PR-0003_V01 |  |  |  |  | Vendor Tr. No. : BK-HD-PEDCO-SVTR-KP-0015 |  |  | Transmital Date:2025/04/23
Document Title: NDE PROCEDURE |  |  |  |  | PEDCO Tr No. : BK-PEDCO-NISOC-0309-QC-TR-KP-0015 |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-KP-120-QC-PR-0003_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | International organization for standardization ISO ,ISO- 3452-1 NDT pt part 1 -part4 part 5 testing at temperature above 50C part 6 testing at temperature under10 C ISO-12706 ISO-23277 PT for weld shall be added |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | N/A. |  |  | Not acceptable it shall be followed or need to be clarified why is it not NA
2 | ASTM e 165 ASME e 1417 ASME e 1209 fluorescent water washable shall be added |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | N/A. |  |  | Not acceptable it shall be followed or need to be clarified why is it not NA
3 | Article 8 outlines the procedures and requirements for Visual Examination (VT), which is one of the most common and simplest forms of NDE used for inspecting materials and welds. Why it is not applicable. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Our instruction is sufficient. |  |  | Client has right to define if the critria is sufficent or not? Be polit in replying the documents.
4 | AS per standard, developer shall be consider 7 min for Steel Or Cast Iron |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | we test it harder. |  |  | Noted, please add the restricted crite and hilighted in your document
5 | the other section of document have not well-organized, please check all the clause and consider in table of content in next revision. The comments will be provided in next revision. |  | BK-SUR-ENG-QAC-03-09950 | 2025-01-19 | Please clarify. |  |  | You need to do calrify for us, the document has not well-organized and there is no suitable table of content
V01(RP)
1 | in according to client conclusions column, Previous comments shall be considered |  | BK-SUR-ENG-QAC-03-10131 | 2025-03-12 | 1- According to the approved ITP, the relevant standard for NDT is ASME SECTION V and the specific standards you mentioned are not in the scope of our work unless they are specified in ITP. Additionally, you can refer to the table 15 - API (Material Inspection Standards). 2- Confirmed. Added to the PT section. 3- Probably you mean the Article 9 which is about Visual Testing. The article 9 is mentioned in PART IV - VT Procedure (page 46, SCOPE, line (c)). 4- According to the table T-672 (ASME BPVC SECTION V) and "Article 24 Table 2". 5- Confirmed. It was completely revised and modified. Please check the new version.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.EMSAEILI Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:3/9/2025 |  |  |  |  | Date: