## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 10
9184 – 073 - 053 |  |  | BK |  | GCS | MF | 120 |  | PM | LI | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V00 |  | 09.Jan. 2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 10
9184 – 073 - 053 |  |  | BK | GCS |  | MF | 120 | PM | LI | 0001 |  | V00
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | * | [7 empty] | 65
2 | * | [7 empty] | 66
3 | * | [7 empty] | 67
4 | * | [7 empty] | 68
5 | * | [7 empty] | 69
6 | * | [7 empty] | 70
7 | * | [7 empty] | 71
8 | * | [7 empty] | 72
9 | * | [7 empty] | 73
10 | * | [7 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: 3 از 10
9184 – 073 - 053 |  | BK | GCS | MF | 120 | PM | LI | 0001 | V00
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-MF-120-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | IFA
1.1.2 | BK-GCS-MF-120-PM-WB-0001 | Work Beakdown Structure for Gas Dehydration Package | [7 empty] | IFA
1.1.3 | BK-GCS-MF-120-GE-VL-0001 | TIME SCHEDULE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
1.1.4 | BK-GCS-MF-120-GE-SH-0001 | BIWEEKLY REPORT FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
1.1.5 | BK-GCS-MF-120-GE-LI-0002 | FINAL VENDOR DATA BOOK INDEX FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
1.2 | Reports
1.2.1 | BK-GCS-MF-120-GE-DO-0001 | FINAL VENDOR DATA BOOK FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-MF-120-QC-PR-0001 | INSPECTION AND TEST PLAN FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
2.1.2 | BK-GCS-MF-120-QC-PR-0002 | NDE PERSONNEL QUALIFICATION LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
2.1.3 | BK-GCS-MF-120-QC-PR-0003 | HARDNESS TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.4 | BK-GCS-MF-120-QC-PR-0004 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | [7 empty] | IFA
2.1.5 | BK-GCS-MF-120-QC-PR-0005 | PICKLING AND PASSIVATION PROCEDURE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
2.1.6 | BK-GCS-MF-120-QC-PR-0006 | POSTWELD HEAT TREATMENT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.7 | BK-GCS-MF-120-QC-PR-0007 | WPS & PQR FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.8 | BK-GCS-MF-120-QC-PR-0008 | PMI PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.9 | BK-GCS-MF-120-QC-PR-0009 | WELDER LIST FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.10 | BK-GCS-MF-120-QC-PR-0010 | NDT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA
2.1.11 | BK-GCS-MF-120-QC-PR-0011 | HYDROSTATIC TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | [7 empty] | IFA
2.1.12 | BK-GCS-MF-120-QC-PR-0012 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | [7 empty] | IFA
2.1.13 | BK-GCS-MF-120-QC-PR-0013 | WELD REPAIR PROCEDURE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
2.2 | Manual
2.2.1 | BK-GCS-MF-120-QC-ML-0001 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
2.2.2 | BK-GCS-MF-120-QC-ML-0002 | PUMPS INSTALLATION, OPERATION AND MAINTENANCE MANUAL FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFI
3 | Process
3.1 | Diagram
3.1.1 | BK-GCS-MF-120-PR-PI-0001 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.2 | BK-GCS-MF-120-PR-PI-0002 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.3 | BK-GCS-MF-120-PR-PI-0003 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.4 | BK-GCS-MF-120-PR-PI-0004 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.5 | BK-GCS-MF-120-PR-PI-0005 | UCP LOGIC DESCRIPTION FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.6 | BK-GCS-MF-120-PR-PI-0006 | BMS LOGIC DESCRIPTION FOR DEHYDRATION PACKAGE | [7 empty] | IFA
3.1.7 | BK-GCS-MF-120-PR-PI-0007 | PERFORMANCE TEST PROCEDURE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
3.2 | List
3.2.1 | BK-GCS-MF-120-PR-LI-0001 | EQUIPMENT LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
3.2.2 | BK-GCS-MF-120-PR-LI-0002 | ALARM & TRIP SET POINT LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
3.2.3 | BK-GCS-MF-120-PR-LI-0003 | UTILITY CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
3.2.4 | BK-GCS-MF-120-PR-LI-0004 | CHEMICAL CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
3.3 | Datasheet
3.3.1 | BK-GCS-MF-120-PR-DS-0001 | PROCESS DATA SHEET FOR DEHYDRATION COLUMN | [7 empty] | IFA
3.3.2 | BK-GCS-MF-120-PR-DS-0002 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | [7 empty] | IFA
3.3.3 | BK-GCS-MF-120-PR-DS-0003 | PROCESS DATA SHEET FOR GLYCOL SURGE VESSEL | [7 empty] | IFA
3.3.4 | BK-GCS-MF-120-PR-DS-0004 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | [7 empty] | IFA
3.3.5 | BK-GCS-MF-120-PR-DS-0005 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | [7 empty] | IFA
3.3.6 | BK-GCS-MF-120-PR-DS-0006 | PROCESS DATA SHEET FOR GLYCOL STRIPPING COLUMN | [7 empty] | IFA
3.3.7 | BK-GCS-MF-120-PR-DS-0007 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | [7 empty] | IFA
3.3.8 | BK-GCS-MF-120-PR-DS-0008 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA
3.3.9 | BK-GCS-MF-120-PR-DS-0009 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | [7 empty] | IFA
3.3.10 | BK-GCS-MF-120-PR-DS-0010 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | [7 empty] | IFA
3.3.11 | BK-GCS-MF-120-PR-DS-0011 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN CONDENSER | [7 empty] | IFA
3.3.12 | BK-GCS-MF-120-PR-DS-0012 | PROCESS DATA SHEET FOR GLYCOL REBOILER | [7 empty] | IFA
3.3.13 | BK-GCS-MF-120-PR-DS-0013 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | [7 empty] | IFA
3.3.14 | BK-GCS-MF-120-PR-DS-0014 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | [7 empty] | IFA
4 | Mechanical
4.1 | Drawing & Calculations
4.1.1 | Glycol Contactor (C-100)
4.1.1.1 | BK-GCS-MF-120-ME-DW-0001 | Mechanical Calculation Book for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.2 | BK-GCS-MF-120-ME-DW-0002 | Lifting Calculation Book for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.3 | BK-GCS-MF-120-GE-DW-0001 | General Arrangement Drawing for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.4 | BK-GCS-MF-120-GE-DW-0002 | Detail of Body for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.5 | BK-GCS-MF-120-GE-DW-0003 | NOZZLE & Manhole Detail Drawing for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.6 | BK-GCS-MF-120-GE-DW-0004 | External Attachment Drawing for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.7 | BK-GCS-MF-120-GE-DW-0005 | Internal Welded Attachments for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.8 | BK-GCS-MF-120-GE-DW-0006 | Name Plate Detail Drawing for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.9 | BK-GCS-MF-120-GE-DW-0007 | NDT Map for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.1.10 | BK-GCS-MF-120-GE-DW-0008 | Welding Map for Glycol Contactor (C-100) | [7 empty] | IFA
4.1.2 | Still Column (C-200)
4.1.2.1 | BK-GCS-MF-120-ME-DW-0003 | Mechanical Calculation Book for Still Column (C-200) | [7 empty] | IFA
4.1.2.2 | BK-GCS-MF-120-GE-DW-0009 | General Arrangement Drawing for Still Column (C-200) | [7 empty] | IFA
4.1.2.3 | BK-GCS-MF-120-GE-DW-0010 | Detail of Body & Nozzle drawing for Still Column (C-200) | [7 empty] | IFA
4.1.2.4 | BK-GCS-MF-120-GE-DW-0011 | Name Plate Detail Drawing for Still Column (C-200) | [7 empty] | IFA
4.1.2.5 | BK-GCS-MF-120-GE-DW-0012 | Internal Welded & External Attachments for Still Column (C-200) | [7 empty] | IFA
4.1.2.6 | BK-GCS-MF-120-GE-DW-0013 | NDT Map for Still Column (C-200) | [7 empty] | IFA
4.1.2.7 | BK-GCS-MF-120-GE-DW-0014 | Welding Map for Still Column (C-200) | [7 empty] | IFA
4.1.3 | Stripping Column (C-300)
4.1.3.1 | BK-GCS-MF-120-ME-DW-0004 | Mechanical Calculation Book for Stripping Column (C-300) | [7 empty] | IFA
4.1.3.2 | BK-GCS-MF-120-GE-DW-0015 | General Arrangement Drawing for Stripping Column (C-300) | [7 empty] | IFA
4.1.3.3 | BK-GCS-MF-120-GE-DW-0016 | Detail drawing for Stripping Column (C-300) | [7 empty] | IFA
4.1.3.4 | BK-GCS-MF-120-GE-DW-0017 | Name Plate Detail Drawing for Stripping Column (C-300) | [7 empty] | IFA
4.1.3.5 | BK-GCS-MF-120-GE-DW-0018 | NDT Map for Stripping Column (C-300) | [7 empty] | IFA
4.1.3.6 | BK-GCS-MF-120-GE-DW-0019 | Welding Map for Stripping Column (C-300) | [7 empty] | IFA
4.1.4 | Glycol Flash Drum (V-120)
4.1.4.1 | BK-GCS-MF-120-ME-DW-0005 | Mechanical & Lifting Calculation Book for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.2 | BK-GCS-MF-120-GE-DW-0020 | General Arrangement Drawing for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.3 | BK-GCS-MF-120-GE-DW-0021 | Detail of Body for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.4 | BK-GCS-MF-120-GE-DW-0022 | Nozzle & Manhole Detail Drawing for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.5 | BK-GCS-MF-120-GE-DW-0023 | External Attachments & Saddle drawing for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.6 | BK-GCS-MF-120-GE-DW-0024 | Name Plate Detail Drawing for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.7 | BK-GCS-MF-120-GE-DW-0025 | NDT Map for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.4.8 | BK-GCS-MF-120-GE-DW-0026 | Welding Map for Glycol Flash Drum (V-120) | [7 empty] | IFA
4.1.5 | Particle Glycol Filter (F-100 A/B)
4.1.5.1 | BK-GCS-MF-120-ME-DW-0006 | Mechanical Calculation Book for Particle Glycol Filter (F-100) | [7 empty] | IFA
4.1.5.2 | BK-GCS-MF-120-GE-DW-0027 | General Arrangement Drawing for Particle Glycol Filter (F-100) | [7 empty] | IFA
4.1.5.3 | BK-GCS-MF-120-GE-DW-0028 | Detail Drawing for Particle Glycol Filter (F-100) | [7 empty] | IFA
4.1.5.4 | BK-GCS-MF-120-GE-DW-0029 | Name Plate Detail Drawing for Particle Glycol Filter (F-100) | [7 empty] | IFA
4.1.6 | Glycol Filter (F-200)
4.1.6.1 | BK-GCS-MF-120-ME-DW-0007 | Mechanical Calculation Book for Glycol Filter (F-200) | [7 empty] | IFA
4.1.6.2 | BK-GCS-MF-120-GE-DW-0030 | General Arrangement Drawing for Glycol Filter (F-200) | [7 empty] | IFA
4.1.6.3 | BK-GCS-MF-120-GE-DW-0031 | Detail Drawing for Glycol Filter (F-200) | [7 empty] | IFA
4.1.6.4 | BK-GCS-MF-120-GE-DW-0032 | Name Plate Detail Drawing for Glycol Filter (F-200) | [7 empty] | IFA
4.1.7 | Glycol Reflux Condenser (E-100)
4.1.7.1 | BK-GCS-MF-120-ME-DW-0008 | Mechanical Calculation Book for Glycol Reflux Condenser (E-100) | [7 empty] | IFA
4.1.7.2 | BK-GCS-MF-120-GE-DW-0033 | General Arrangement Drawing for Glycol Reflux Condenser (E-100) | [7 empty] | IFA
4.1.7.3 | BK-GCS-MF-120-GE-DW-0034 | Detail Drawing for Glycol Reflux Condenser (E-100) | [7 empty] | IFA
4.1.7.4 | BK-GCS-MF-120-GE-DW-0035 | Name Plate Detail Drawing for Glycol Reflux Condenser (E-100) | [7 empty] | IFA
4.1.8 | Rich-Lean Glycol Heat Exchanger (E-200)
4.1.8.1 | BK-GCS-MF-120-ME-DW-0009 | Mechanical Calculation Book for Rich-Lean Glycol Heat Exchanger (E-200) | [7 empty] | IFA
4.1.8.2 | BK-GCS-MF-120-GE-DW-0036 | General Arrangement Drawing for Rich-Lean Glycol Heat Exchanger (E-200) | [7 empty] | IFA
4.1.8.3 | BK-GCS-MF-120-GE-DW-0037 | Detail Drawing for Rich-Lean Glycol Heat Exchanger (E-200) | [7 empty] | IFA
4.1.8.4 | BK-GCS-MF-120-GE-DW-0038 | Name Plate Detail Drawing for Rich-Lean Glycol Heat Exchanger (E-200) | [7 empty] | IFA
4.1.9 | Lean Glycol-Dry Gas Heat Exchanger (E-300)
4.1.9.1 | BK-GCS-MF-120-ME-DW-0010 | Mechanical Calculation Book for Lean Glycol-Dry Gas Heat Exchanger (E-300) | [7 empty] | IFA
4.1.9.2 | BK-GCS-MF-120-GE-DW-0039 | General Arrangement Drawing for Lean Glycol-Dry Gas Heat Exchanger (E-300) | [7 empty] | IFA
4.1.9.3 | BK-GCS-MF-120-GE-DW-0040 | Detail Drawing for Lean Glycol-Dry Gas Heat Exchanger (E-300) | [7 empty] | IFA
4.1.9.4 | BK-GCS-MF-120-GE-DW-0041 | Name Plate Detail Drawing for Lean Glycol-Dry Gas Heat Exchanger (E-300) | [7 empty] | IFA
4.1.10 | Reboiler (R-100)
4.1.10.1 | BK-GCS-MF-120-ME-DW-0011 | Mechanical & Lifting Calculation Book for Reboiler (R-100) | [7 empty] | IFA
4.1.10.2 | BK-GCS-MF-120-GE-DW-0042 | General Arrangement Drawing for Reboiler (R-100) | [7 empty] | IFA
4.1.10.3 | BK-GCS-MF-120-GE-DW-0043 | Detail of Body for Reboiler (R-100) | [7 empty] | IFA
4.1.10.4 | BK-GCS-MF-120-GE-DW-0044 | Nozzle & Manhole Detail Drawing for Reboiler (R-100) | [7 empty] | IFA
4.1.10.5 | BK-GCS-MF-120-GE-DW-0045 | Detail of Saddle drawing for Reboiler (R-100) | [7 empty] | IFA
4.1.10.6 | BK-GCS-MF-120-GE-DW-0046 | Internal & External Welded Attachments for Reboiler (R-100) | [7 empty] | IFA
4.1.10.7 | BK-GCS-MF-120-GE-DW-0047 | Name Plate Detail Drawing for Reboiler (R-100) | [7 empty] | IFA
4.1.10.8 | BK-GCS-MF-120-GE-DW-0048 | NDT Map for Reboiler (R-100) | [7 empty] | IFA
4.1.10.9 | BK-GCS-MF-120-GE-DW-0049 | Welding Map for Reboiler (R-100) | [7 empty] | IFA
4.1.11 | Surge Drum (V-130)
4.1.11.1 | BK-GCS-MF-120-ME-DW-0012 | Mechanical & Lifting Calculation Book for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.2 | BK-GCS-MF-120-GE-DW-0050 | General Arrangement Drawing for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.3 | BK-GCS-MF-120-GE-DW-0051 | Detail of Body for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.4 | BK-GCS-MF-120-GE-DW-0052 | Nozzle & Manhole Detail Drawing for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.5 | BK-GCS-MF-120-GE-DW-0053 | External Attachments & Saddle drawing for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.6 | BK-GCS-MF-120-GE-DW-0054 | Name Plate Detail Drawing for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.7 | BK-GCS-MF-120-GE-DW-0055 | NDT Map for Surge Drum (V-130) | [7 empty] | IFA
4.1.11.8 | BK-GCS-MF-120-GE-DW-0056 | Welding Map for Surge Drum (V-130) | [7 empty] | IFA
5 | Machinery
5.1 | Drawing
5.1.1 | BK-GCS-MF-120-MA-DW-0001 | BURNER DRAWING FOR GLYCOL REBOILER | [7 empty] | IFA
5.1.2 | BK-GCS-MF-120-MA-DW-0002 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA
5.1.3 | BK-GCS-MF-120-MA-DW-0003 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA
5.1.4 | BK-GCS-MF-120-MA-DW-0004 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA
5.2 | Datasheet
5.2.1 | BK-GCS-MF-120-MA-DS-0001 | BURNER DATA SHEET FOR GLYCOL REBOILER | [7 empty] | IFA
5.3 | List
5.3.1 | BK-GCS-MF-120-MA-LI-0001 | LUBRICATION LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
5.3.2 | BK-GCS-MF-120-MA-LI-0002 | TWO YEARS & COMMISSIONING SPARE PART LIST FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFI
6 | Piping
6.1 | Drawing
6.1.1 | BK-GCS-MF-120-PI-DW-0001 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (30%) FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.1.2 | BK-GCS-MF-120-PI-DW-0002 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (60%) FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.1.3 | BK-GCS-MF-120-PI-DW-0003 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (90%) FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.1.4 | BK-GCS-MF-120-PI-DW-0004 | PACKAGE PLOT PLAN FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.1.5 | BK-GCS-MF-120-PI-DW-0005 | PIPING GENERAL ARRANGEMENT DRAWING FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.1.6 | BK-GCS-MF-120-PI-DW-0006 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
6.2 | List
6.2.1 | BK-GCS-MF-120-PI-LI-0001 | LINE LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
6.2.2 | BK-GCS-MF-120-PI-LI-0002 | TIE-IN-LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
6.2.3 | BK-GCS-MF-120-PI-LI-0003 | SUPPORT LIST FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
6.3 | Reports
6.3.1 | BK-GCS-MF-120-PI-RT-0002 | STRESS ANALYSIS REPORT FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
7 | Instrument
7.1 | Drawing
7.1.1 | BK-GCS-MF-120-IN-DW-0001 | Instrument and electrical block schematic diagram | [7 empty] | IFA
7.1.2 | BK-GCS-MF-120-IN-DW-0002 | UCP system configuration diagram | [7 empty] | IFA
7.1.3 | BK-GCS-MF-120-IN-DW-0003 | BMS system configuration diagram | [7 empty] | IFA
7.1.4 | BK-GCS-MF-120-IN-DW-0004 | Instrument junction box layout and wiring termination diagram | [7 empty] | IFA
7.1.5 | BK-GCS-MF-120-IN-DW-0005 | Burner operation panel layout & wiring diagram with connections & dimensions | [7 empty] | IFA
7.1.6 | BK-GCS-MF-120-IN-DW-0006 | Hook up drawing | [7 empty] | IFA
7.1.7 | BK-GCS-MF-120-IN-DW-0007 | Instrument location layout | [7 empty] | IFA
7.1.8 | BK-GCS-MF-120-IN-DW-0008 | UCP panel layout and arrangement | [7 empty] | IFA
7.1.9 | BK-GCS-MF-120-IN-DW-0009 | BMS panel layout and arrangement | [7 empty] | IFA
7.1.10 | BK-GCS-MF-120-IN-DW-0010 | UCP system wiring diagram and connections | [7 empty] | IFA
7.1.11 | BK-GCS-MF-120-IN-DW-0011 | BMS system wiring diagram and connections | [7 empty] | IFA
7.1.12 | BK-GCS-MF-120-IN-DW-0012 | Instrument loop diagram | [7 empty] | IFA
7.1.13 | BK-GCS-MF-120-IN-DW-0013 | UCP system logic diagram | [7 empty] | IFA
7.1.14 | BK-GCS-MF-120-IN-DW-0014 | BMS system logic diagram | [7 empty] | IFA
7.1.15 | BK-GCS-MF-120-IN-DW-0015 | PRINT OUT OF HMI FOR BMS and UCP | [7 empty] | IFA
7.2 | Datasheet
7.2.1 | BK-GCS-MF-120-IN-DS-0001 | Control valve calculation sheets | [7 empty] | IFA
7.2.2 | BK-GCS-MF-120-IN-DS-0002 | Instrument D.S. for control valves | [7 empty] | IFA
7.2.3 | BK-GCS-MF-120-IN-DS-0003 | Instrument D.S. for On/Off valves | [7 empty] | IFA
7.2.4 | BK-GCS-MF-120-IN-DS-0004 | Instrument D.S. for H2O analyzer | [7 empty] | IFA
7.2.5 | BK-GCS-MF-120-IN-DS-0005 | Instrument D.S. for temperature gauge | [7 empty] | IFA
7.2.6 | BK-GCS-MF-120-IN-DS-0006 | Instrument D.S. for temperature transmitters | [7 empty] | IFA
7.2.7 | BK-GCS-MF-120-IN-DS-0007 | Instrument D.S. for pressure gauges and differential gauges | [7 empty] | IFA
7.2.8 | BK-GCS-MF-120-IN-DS-0008 | Instrument D.S. for pressure transmitters and differentia pressure transmitters | [7 empty] | IFA
7.2.9 | BK-GCS-MF-120-IN-DS-0009 | Pressure safety valves calculation | [7 empty] | IFA
7.2.10 | BK-GCS-MF-120-IN-DS-0010 | Pressure safety valves data sheet | [7 empty] | IFA
7.2.11 | BK-GCS-MF-120-IN-DS-0011 | Instrument D.S. for pressure regulator valves | [7 empty] | IFA
7.2.12 | BK-GCS-MF-120-IN-DS-0012 | Flow element calculation sheets | [7 empty] | IFA
7.2.13 | BK-GCS-MF-120-IN-DS-0013 | Instrument D.S. for flow elements | [7 empty] | IFA
7.2.14 | BK-GCS-MF-120-IN-DS-0014 | Instrument D.S. for level gauges | [7 empty] | IFA
7.2.15 | BK-GCS-MF-120-IN-DS-0015 | Instrument D.S. for level transmitters | [7 empty] | IFA
7.2.16 | BK-GCS-MF-120-IN-DS-0016 | Flame scanner data sheet | [7 empty] | IFA
7.2.17 | BK-GCS-MF-120-IN-DS-0017 | FAT procedure for UCP system | [7 empty] | IFA
7.2.18 | BK-GCS-MF-120-IN-DS-0018 | FAT procedure for BMS system | [7 empty] | IFA
7.3 | List
7.3.1 | BK-GCS-MF-120-IN-LI-0001 | Instrument list | [7 empty] | IFI
7.3.2 | BK-GCS-MF-120-IN-LI-0002 | Input/Output signal list | [7 empty] | IFI
7.3.3 | BK-GCS-MF-120-IN-LI-0003 | Instrument cable list | [7 empty] | IFI
7.3.4 | BK-GCS-MF-120-IN-LI-0004 | UCP and BMS system power consumption list | [7 empty] | IFI
7.3.5 | BK-GCS-MF-120-IN-LI-0005 | Modbus IO list (Modbus mapping list) | [7 empty] | IFI
8 | Electrical
8.1 | Drawing
8.1.1 | BK-GCS-MF-120-EL-DW-0001 | Electrical single line diagram | [7 empty] | IFA
8.1.2 | BK-GCS-MF-120-EL-DW-0002 | Earthing detail layout | [7 empty] | IFA
8.1.3 | BK-GCS-MF-120-EL-DW-0003 | Electrical/Instrument Cable Route Layout | [7 empty] | IFA
8.1.4 | BK-GCS-MF-120-EL-DW-0004 | Electrical panel layout and wiring diagram | [7 empty] | IFA
8.1.5 | BK-GCS-MF-120-EL-DW-0005 | Local control station (LCS) panel layout and wiring diagram | [7 empty] | IFA
8.2 | List
8.2.1 | BK-GCS-MF-120-EL-LI-0001 | Power and control cable list | [7 empty] | IFI
8.2.2 | BK-GCS-MF-120-EL-LI-0002 | Electrical load list | [7 empty] | IFI
8.3 | Datasheet
8.3.1 | BK-GCS-MF-120-EL-DS-0001 | Electrical motor data sheets | [7 empty] | IFA
9 | Structure
9.1 | Calculation
9.1.1 | BK-GCS-MF-120-ST-CN-0001 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA
9.1.2 | BK-GCS-MF-120-ST-CN-0002 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
9.2 | Drawing
9.2.1 | BK-GCS-MF-120-ST-DW-0001 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA