## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک ( قرارداد BK-HD-GCS-CO-0010_08)
Work Breakdown Structure for Gas Dehydration Package (WBS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 6
9184 – 073 - 053 |  |  | BK |  | GCS | MF | 120 |  | PM | WB | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
Work Breakdown Structure for Gas Dehydration Package (WBS) نگهداشت و افزایش تولید میدان نفتی بینک
V00 |  | 22.Jan. 2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک ( قرارداد BK-HD-GCS-CO-0010_08)
Work Breakdown Structure for Gas Dehydration Package (WBS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 6
9184 – 073 - 053 |  |  | BK | GCS |  | MF | 120 | PM | WB | 0001 |  | V00
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | [7 empty] | 65
2 | X | [7 empty] | 66
3 | X | [7 empty] | 67
4 | X | [7 empty] | 68
5 | X | [7 empty] | 69
6 | X | [7 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## Sheet3
WBS | Task Name | W.F.
0 | BINAK OILFIELD DEVELOPMENT | 100
1 | DOCUMENTS | 15
1.1 | Vendor's Document (According to VPIS) Document Subject According to client Approval | 14.75 | خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک ( قرارداد BK-HD-GCS-CO-0010_08)
1.1.1 | WORK BREAKDOWN STRUCTURE FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.2 | VENDOR PRINT INDEX & SCHEDULE (VPIS) FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.3 | TIME SCHEDULE FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.4 | FINAL VENDOR DATA BOOK INDEX FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.5 | SHIPPING & INSTALLATION MANUAL (INCLUDING HANDLING, TRANSPORTATION, STORAGE AND ERECTION) FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.6 | SUB-VENDOR LIST FOR GAS DEHYDRATION PACKAGE | 0.15
1.1.7 | MARKING & PACKING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, REBOILER, DRUMS, FILTERS, COLUMNS, EXCHANGERS) | 0.11
1.1.8 | MARKING & PACKING PROCEDURE FOR GLYCOL CIRCULATION PUMPS | 0.1
1.1.9 | INSPECTION AND TEST PLAN FOR GAS DEHYDRATION PACKAGE | 0.07
1.1.10 | HARDNESS TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07
1.1.11 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | 0.07
1.1.12 | PICKLING AND PASSIVATION PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07
1.1.13 | POSTWELD HEAT TREATMENT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07
1.1.14 | PMI PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07
1.1.15 | HYDROSTATIC TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | 0.07
1.1.16 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | 0.07
1.1.17 | WELD REPAIR PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07
1.1.18 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34
1.1.19 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | 0.34
1.1.20 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34
1.1.21 | UCP LOGIC DESCRIPTION FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.22 | BMS LOGIC DESCRIPTION FOR DEHYDRATION PACKAGE | 0.09
1.1.23 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.24 | PROCESS DATA SHEET FOR DEHYDRATION COLUMN | 0.09
1.1.25 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | 0.09
1.1.26 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | 0.09
1.1.27 | PROCESS DATA SHEET FOR GLYCOL STRIPPING COLUMN | 0.09
1.1.28 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | 0.09
1.1.29 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | 0.09
1.1.30 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN CONDENSER | 0.09
1.1.31 | PROCESS DATA SHEET FOR GLYCOL REBOILER | 0.09
1.1.32 | PROCESS DATA SHEET FOR GLYCOL SURGE VESSEL | 0.09
1.1.33 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | 0.09
1.1.34 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | 0.09
1.1.35 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | 0.09
1.1.36 | EQUIPMENT LIST FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.37 | ALARM & TRIP SET POINT LIST FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.38 | UTILITY CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.39 | CHEMICAL CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.40 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | 0.09
1.1.41 | PERFORMANCE TEST PROCEDURE FOR GAS DEHYDRATION PACKAGE (SAT Procedure)) | 0.09
1.1.42 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | 0.09
1.1.43 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | 0.09
1.1.44 | Mechanical Calculation Book for C-100 | 0.04
1.1.45 | Lifting Calculation Book for C-100 | 0.01
1.1.46 | General Arrangement Drawing for C-100 | 0.03
1.1.47 | Detail of Body for C-100 | 0.02
1.1.48 | NOZZLE & Manhole Detail Drawing for C-100 | 0.02
1.1.49 | External Attachment Drawing for C-100 | 0.02
1.1.50 | Internal Welded Attachments for C-100 | 0.02
1.1.51 | Name Plate Detail Drawing for C-100 | 0.01
1.1.52 | NDT Map for C-100 | 0.02
1.1.53 | Welding Map for C-100 | 0.02
1.1.54 | Mechanical Calculation Book for C-200 | 0.05
1.1.55 | General Arrangement Drawing for C-200 | 0.04
1.1.56 | Detail of Body & Nozzle drawing for C-200 | 0.03
1.1.57 | Name Plate Detail Drawing for C-200 | 0.02
1.1.58 | Internal Welded & External Attachments for C-200 | 0.02
1.1.59 | NDT Map for C-200 | 0.02
1.1.60 | Welding Map for C-200 | 0.02
1.1.61 | Mechanical Calculation Book for C-300 | 0.06
1.1.62 | General Arrangement Drawing for C-300 | 0.06
1.1.63 | Detail drawing for C-300 | 0.05
1.1.64 | Name Plate Detail Drawing for C-300 | 0.02
1.1.65 | NDT Map for C-300 | 0.02
1.1.66 | Welding Map for C-300 | 0.02
1.1.67 | Mechanical & Lifting Calculation Book for V-120 | 0.05
1.1.68 | General Arrangement Drawing for V-120 | 0.05
1.1.69 | Detail of Body for V-120 | 0.04
1.1.70 | Nozzle & Manhole Detail Drawing for V-120 | 0.03
1.1.71 | External Attachments & Saddle drawing for V-120 | 0.03
1.1.72 | Name Plate Detail Drawing for V-120 | 0.01
1.1.73 | NDT Map for V-120 | 0.02
1.1.74 | Welding Map for V-120 | 0.02
1.1.75 | Mechanical Calculation Book for F-100 | 0.08
1.1.76 | General Arrangement Drawing for F-100 | 0.07
1.1.77 | Detail Drawing for F-100 | 0.06
1.1.78 | Name Plate Detail Drawing for F-100 | 0.02
1.1.79 | Mechanical Calculation Book for F-200 | 0.09
1.1.80 | General Arrangement Drawing for F-200 | 0.08
1.1.81 | Detail Drawing for F-200 | 0.07
1.1.82 | Name Plate Detail Drawing for F-200 | 0.02
1.1.83 | Mechanical Calculation Book for E-100 | 0.09
1.1.84 | General Arrangement Drawing for E-100 | 0.08
1.1.85 | Detail Drawing for E-100 | 0.07
1.1.86 | Name Plate Detail Drawing for E-100 | 0.02
1.1.87 | Mechanical Calculation Book for E-200 | 0.09
1.1.88 | General Arrangement Drawing for E-200 | 0.08
1.1.89 | Detail Drawing for E-200 | 0.07
1.1.90 | Name Plate Detail Drawing for E-200 | 0.02
1.1.91 | Mechanical Calculation Book for E-300 | 0.09
1.1.92 | General Arrangement Drawing for E-300 | 0.08
1.1.93 | Detail Drawing for E-300 | 0.07
1.1.94 | Name Plate Detail Drawing for E-300 | 0.02
1.1.95 | Mechanical & Lifting Calculation Book for R-100 | 0.05
1.1.96 | General Arrangement Drawing for R-100 | 0.04
1.1.97 | Detail of Body for R-100 | 0.03
1.1.98 | Nozzle & Manhole Detail Drawing for R-100 | 0.03
1.1.99 | Detail of Saddle drawing for R-100 | 0.02
1.1.100 | Internal & External Welded Attachments for R-100 | 0.02
1.1.101 | Name Plate Detail Drawing for R-100 | 0.01
1.1.102 | NDT Map for R-100 | 0.02
1.1.103 | Welding Map for R-100 | 0.02
1.1.104 | Mechanical & Lifting Calculation Book for V-130 | 0.05
1.1.105 | General Arrangement Drawing for V-130 | 0.04
1.1.106 | Detail of Body for V-130 | 0.04
1.1.107 | Nozzle & Manhole Detail Drawing for V-130 | 0.03
1.1.108 | External Attachments & Saddle drawing for V-130 | 0.03
1.1.109 | Name Plate Detail Drawing for V-130 | 0.01
1.1.110 | NDT Map for V-130 | 0.02
1.1.111 | Welding Map for V-130 | 0.42
1.1.112 | BURNER DATA SHEET FOR GLYCOL REBOILER | 0.06
1.1.113 | BURNER DRAWING FOR GLYCOL REBOILER | 0.06
1.1.114 | LUBRICATION LIST FOR GAS DEHYDRATION PACKAGE | 0.06
1.1.115 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06
1.1.116 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06
1.1.117 | PUMPS INSTALLATION, OPERATION AND MAINTENANCE MANUAL FOR GLYCOL CIRCULATION PUMPS | 0.06
1.1.118 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | 0.05
1.1.119 | TWO YEARS & COMMISSIONING SPARE PART LIST FOR GLYCOL CIRCULATION PUMPS | 0.06
1.1.120 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | 0.08
1.1.121 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | 0.08
1.1.122 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | 0.08
1.1.123 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (30%) FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.124 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (60%) FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.125 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (90%) FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.126 | PACKAGE PLOT PLAN FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.127 | PIPING GENERAL ARRANGEMENT DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.128 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.129 | LINE LIST FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.130 | TIE-IN-LIST FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.131 | SUPPORT LIST FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.132 | STRESS ANALYSIS REPORT FOR GAS DEHYDRATION PACKAGE | 0.13
1.1.133 | Electrical single line diagram | 0.15
1.1.134 | Power and control cable list | 0.16
1.1.135 | Earthing detail layout | 0.1
1.1.136 | Electrical load list | 0.14
1.1.137 | Electrical/Instrument Cable Route Layout | 0.14
1.1.138 | Electrical motor data sheets | 0.14
1.1.139 | Electrical panel layout and wiring diagram | 0.1
1.1.140 | Local control station (LCS) panel layout and wiring diagram | 0.1
1.1.141 | Instrument list | 0.1
1.1.142 | Input/Output signal list | 0.1
1.1.143 | Instrument and electrical block schematic diagram | 0.1
1.1.144 | UCP system configuration diagram | 0.1
1.1.145 | BMS system configuration diagram | 0.1
1.1.146 | Instrument junction box layout and wiring termination diagram | 0.1
1.1.147 | Burner operation panel layout & wiring diagram with connections & dimensions | 0.1
1.1.148 | Control valve calculation sheets | 0.1
1.1.149 | Instrument D.S. for control valves | 0.1
1.1.150 | Instrument cable list | 0.1
1.1.151 | Instrument D.S. for On/Off valves | 0.1
1.1.152 | Instrument D.S. for H2O analyzer | 0.1
1.1.153 | Instrument D.S. for temperature gauge | 0.1
1.1.154 | Instrument D.S. for temperature transmitters | 0.1
1.1.155 | Instrument D.S. for pressure gauges and differential gauges | 0.1
1.1.156 | Instrument D.S. for pressure transmitters and differentia pressure transmitters | 0.1
1.1.157 | Pressure safety valves calculation | 0.1
1.1.158 | Pressure safety valves data sheet | 0.1
1.1.159 | Instrument D.S. for pressure regulator valves | 0.1
1.1.160 | Flow element calculation sheets | 0.1
1.1.161 | Instrument D.S. for flow elements | 0.1
1.1.162 | Instrument D.S. for level gauges | 0.1
1.1.163 | Instrument D.S. for level transmitters | 0.1
1.1.164 | Hook up drawing | 0.1
1.1.165 | Instrument location layout | 0.1
1.1.166 | Flame scanner data sheet | 0.1
1.1.167 | UCP panel layout and arrangement | 0.1
1.1.168 | BMS panel layout and arrangement | 0.1
1.1.169 | UCP system wiring diagram and connections | 0.1
1.1.170 | BMS system wiring diagram and connections | 0.1
1.1.171 | UCP and BMS system power consumption list | 0.1
1.1.172 | Instrument loop diagram | 0.1
1.1.173 | Modbus IO list (Modbus mapping list) | 0.1
1.1.174 | FAT procedure for UCP system | 0.1
1.1.175 | FAT procedure for BMS system | 0.1
1.1.176 | UCP system Logic diagram | 0.1
1.1.177 | BMS system Logic diagram | 0.1
1.1.178 | PRINT OUT OF HMI FOR BMS and UCP | 0.1
1.2 | WPS-PQR | 0.05
1.3 | WQT | 0.05
1.4 | NDT Procedures (VT-PT-MT-UT-RT) | 0.05
1.5 | NDT Personal Certificate | 0.05
1.6 | Calibration | 0.05
2 | TEST AND INSPECTION ACTIVITIES | 78
2.1 | Vessel | 30.39
2.1.1 | Raw Material Of Pressure Parts | 7
2.1.2 | Raw Material Of Non-Pressure Parts | 2.15
2.1.3 | Internals | 0.61
2.1.4 | VT & DT For Raw Material | 0.3
2.1.5 | Consumable Material (Electrode) | 0.3
2.1.6 | Cutting & Marking | 1.52
2.1.7 | Rolling & Forming | 2.43
2.1.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) | 2.13
2.1.9 | Welding | 3.95
2.1.10 | Ferrite Check For Welding Gladded Parts | 2.43
2.1.11 | NDT (VT,MT.PT,UT,RT) | 1.22
2.1.12 | Weld Repair | 1.52
2.1.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 1.22
2.1.14 | Final Visual and Dimensional | 0.91
2.1.15 | PWHT (If Any) | 0.3
2.1.16 | Hardness Check | 0.3
2.1.17 | NDT After PWHT | 0.3
2.1.18 | Pneumatic Test (Pad Test) | 0.3
2.1.19 | Hydrostatic Test Water Quality | 0.3
2.1.20 | Hydrostatic Test | 0.3
2.1.21 | Draining & Drying | 0.3
2.1.22 | Abrasive & Paint Material | 0.3
2.1.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) | 0.3
2.2 | Heat Exchangers | 4.72
2.2.1 | Raw Material for Pressure parts | 1.12
2.2.2 | Raw Material for Non-Pressure parts | 0.37
2.2.3 | VT & DT For Raw Material | 0.05
2.2.4 | Consumable Material (Electrode) | 0.05
2.2.5 | Cutting & Marking | 0.23
2.2.6 | Rolling & Forming | 0.37
2.2.7 | Tube to Tube Sheet Joint {Expansion) | 0.35
2.2.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, … ) | 0.61
2.2.9 | Welding | 0.37
2.2.10 | NDT (VT,MT.PT,UT,RT) | 0.19
2.2.11 | Weld Repair | 0.23
2.2.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 0.19
2.2.13 | Final Visual and Dimensional | 0.14
2.2.14 | PWHT (If Any) | 0.05
2.2.15 | Hardness Check | 0.05
2.2.16 | NDT After PWHT | 0.05
2.2.17 | Pneumatic Test (Pad Test) | 0.05
2.2.18 | Hydrostatic Test Water Quality | 0.05
2.2.19 | Hydrostatic Test | 0.05
2.2.20 | Draining & Drying | 0.05
2.2.21 | Abrasive & Paint Material | 0.05
2.2.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.05
2.3 | Re-boiler | 2.32
2.3.1 | Raw Material for Pressure parts | 0.59
2.3.2 | Raw Material for Non-Pressure parts | 0.21
2.3.3 | VT & DT For Raw Material | 0.02
2.3.4 | Consumable Material (Electrode) | 0.02
2.3.5 | Cutting & Marking | 0.12
2.3.6 | Rolling & Forming | 0.21
2.3.7 | Weld Preparation and Fit-Up (Shell,Nozzle, ... ) | 0.33
2.3.8 | Welding | 0.21
2.3.9 | NDT (VT,MT.PT,UT,RT) | 0.11
2.3.10 | Weld Repair | 0.14
2.3.11 | NDT After Weld Repair (VT,MT.PT,UT,R T) | 0.11
2.3.12 | Final Visual and Dimensional | 0.07
2.3.13 | PWHT (If Any) | 0.02
2.3.14 | Hardness Check | 0.02
2.3.15 | NDT After PWHT | 0.02
2.3.16 | Pneumatic Test (Pad Test) | 0.02
2.3.17 | Hydrostatic Test Water Quality | 0.02
2.3.18 | Hydrostatic Test | 0.02
2.3.19 | Draining & Drying | 0.02
2.3.20 | Abrasive & Paint Material | 0.02
2.3.21 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.02
2.4 | Field Instruments (Transmitters/ Switch/ Gauge/ Analizer etc.) | 9.36
2.4.1 | Visual Dimensional Inspection(Appearance) | 3.18
2.4.2 | Calibration Check | 2.34
2.4.3 | Tag & Model No & Specification Check | 1.59
2.4.4 | Review Material, IP,ATEX Certificate | 0.75
2.4.5 | Pressure & Performance Test | 0.75
2.4.6 | Packing Inspection& Painting | 0.75
2.5 | Cable, Wires & Tray | 1.56
2.5.1 | Cable & Wires | 0.78
2.5.1.1 | Visual Inspection | 0.39
2.5.1.2 | Type Test Sertificate or Manufacturer Catalogue | 0.39
2.5.2 | Tray | 0.78
2.5.2.1 | Material Inspection | 0.39
2.5.2.2 | Visual & Dimensional Inspection | 0.39
2.6 | Junction Box | 2.35
2.6.1 | Review IP, ATEX Certificate | 0.94
2.6.2 | Tag & Model No Check | 0.59
2.6.3 | Review IP, ATEX certificate | 0.47
2.6.4 | Packing inspection and painting | 0.35
2.7 | Local Panel (Outdoor-Hazardous Area) | 3.12
2.7.1 | Visual Inspection & Dimenslonal Check | 1.09
2.7.2 | Accessories Tag & Model No Check | 0.31
2.7.3 | Construction | 1.4
2.7.4 | Review IP, ATEX Certificate | 0.16
2.7.5 | Packing Inspection & Painting | 0.16
2.8 | Control Panel (Indoor-Safe Area) | 7.02
2.8.1 | Visual Inspection/ QTY & Dimensional Check | 2.81
2.8.2 | Tag & Model No Check | 1.76
2.8.3 | Function & Performance test (Power & Start-up Check, I/O Check) | 1.4
2.8.4 | Main equipment & Accessories Certificate IP , ATEX, SIL Certificate Check) | 1.05
2.9 | Valves | 3.09
2.9.1 | Manual Valves | 1.62
2.9.1.1 | Material Inspection | 0.81
2.9.1.2 | Visual and Dimensional Inspection | 0.65
2.9.1.3 | Other Required Tests | 0.16
2.9.2 | Inst.Valves (Shut Down, On/Off, Control & Safety Valves) | 1.47
2.9.2.1 | Material Inspection | 0.52
2.9.2.2 | Visual and Dimensional & QTY Inspection | 0.3
2.9.2.3 | Construction | 0.37
2.9.2.4 | Accessory | 0.07
2.9.2.5 | Pressure Test | 0.07
2.9.2.6 | Calibration | 0.07
2.9.2.7 | Performance test | 0.07
2.1 | Strainers | 1.56
2.10.1 | Material Inspection | 0.78
2.10.2 | Visual and Dimensional Inspection | 0.62
2.10.3 | Hydro Test | 0.16
2.11 | Piping Items (Pipe, Flange, Fitting, Gasket, Bolt & Nuts) | 2.35
2.11.1 | Material Inspection | 0.82
2.11.2 | Visual and Dimensional Inspection | 0.35
2.11.3 | Weld Preparation and Fit-Up | 0.47
2.11.4 | Welding | 0.47
2.11.5 | NDT( VT, MT, PT, UT, RT) | 0.12
2.11.6 | Hydrostatic Test | 0.12
2.12 | Pump | 1.56
2.12.1 | Final Visual and Dimensional Inspection | 1.01
2.12.2 | Performance test | 0.55
2.13 | Ladder & Platform | 1.56
2.13.1 | Visual and Dimensional Check After Welding | 1.56
2.14 | Chemical Injection Package | 3.14
2.14.1 | Raw Material for Tank | 1.09
2.14.2 | Final Inspection For Fabricated Tank | 0.16
2.14.3 | Piping & Structure Works | 1.25
2.14.4 | Performance test | 0.16
2.14.5 | Packing Inspection | 0.16
2.14.6 | IRN | 0.16
2.14.7 | Final Book | 0.16
2.15 | Reboiler Burner | 1.56
2.15.1 | Final Visual and Dimensional Inspection | 1.01
2.15.2 | Burner Test | 0.55
2.16 | Painting of Package Assembly (Piping, Structure) | 0.78
2.16.1 | Abrasive & Paint Material | 0.39
2.16.2 | Blasting & Painting (Each Layer DFT, Adhesion) | 0.39
2.17 | Pickling (For Stainless Steel Part) | 0.78
2.17.1 | Pickling and Passivation | 0.78
2.18 | Preservation | 0.78
2.18.1 | N2 Purge /Silica | 0.78
3 | PACKING | 1
3.1 | Packing Inspection | 1
4 | IRN | 1
4.1 | Release Note | 1
5 | FINAL DATA BOOK | 3
5.1 | Final Document Preparation | 3
6 | IC | 1
6.1 | Inspection Certificate | 1
7 | SITE ACCEPTANCE TEST | 1
7.1 | SAT | 1