## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PM-LI-0001 |  |  |  |  | Vendor Tr. No.: BK-HD-PEDCO-SVTR-MF-0001 |  |  | Transmital Date: 2024/01/10
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | Client Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-PM-LI-0001 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
QC comments :
1 | QA/QC: مدرك زير اضافه گردد. |  | BK-SUR-ENG-MEC-02-08963 | 2024-01-23
Packing,Marking,Shipping Procedure
N2 Purging Procedure
Ferrite Number Measurment Procedure (If Required)
SAT Procedure
2 | Welding and NDT Map براي ساير تجهيزات مانند Heat Exchanger, Structure,... اضافه گردد. |  | BK-SUR-ENG-MEC-02-08963 | 2024-01-23
3 | ابزار دقیق: - مشخص شود که Calibration certificate در کدام مدرک ارایه خواهد شد. - SAT Procedure برای سیستم UCP و BMS ارایه گردد. - SAT و FAT Report برای سیستم های UCP و BMS اضافه گردد. - SIL Study Procedure و SIL Report در لیست مدارک اضافه گردد. - مشخص شود که Instrument Earthing Layout در کدام مدرک ارایه خواهد شد. |  | BK-SUR-ENG-MEC-02-08963 | 2024-01-23
4 | بخش فرآیند: 1- مدرک مطالعات HAZOP به لیست مدارک بخش فرآیند اضافه شود. 2- با توجه به در نظر نگرفتن مدارک دیتاشیت تجهیزات در بخش مکانیک توط سازنده، پیشنهاد می گردد این مدارک از بخش فرآیند حذف شده و Mechanical Datasheet تجهیزات، به لیست مدارک بخش مکانیک اضافه شود. |  | BK-SUR-ENG-MEC-02-08963 | 2024-01-23
6 | Please find the attached comments. |  | BK-SUR-ENG-MEC-02-08963 | 2024-01-23
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 23-01-2024 |  |  |  |  | Date: