## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 10
9184 – 073 - 053 |  |  | BK |  | GCS | MF | 120 |  | PM | LI | 0001 | V02
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V02 |  | SEP.2024 |  | IFI |  |  |  | MFS |  |  | M.Fakharian |  | M.SADEGHIAN
V01 |  | MAR.2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | S.Faramarzpour
V00 |  | FEB.2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 10
9184 – 073 - 053 |  |  | BK | GCS |  | MF | 120 | PM | LI | 0001 |  | V02
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | * | * | * | [5 empty] | 65
2 | * | * | * | [5 empty] | 66
3 | * | * | * | [5 empty] | 67
4 | * | * | * | [5 empty] | 68
5 | * | * | * | [5 empty] | 69
6 | * | * | * | [5 empty] | 70
7 | * | * | * | [5 empty] | 71
8 | * | * | * | [5 empty] | 72
9 | * | * | * | [5 empty] | 73
10 | * | * | * | [5 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0010_08)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه:
9184 – 073 - 053 |  | BK | GCS | MF | 120 | PM | LI | 0001 | V02
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-MF-120-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | IFI | MOD
1.1.2 | BK-GCS-MF-120-PM-WB-0001 | WORK BEAKDOWN STRUCTURE | [7 empty] | IFA/AFC | MOD
1.1.3 | BK-GCS-MF-120-GE-SH-0001 | TIME SCHEDULE | [7 empty] | IFI
1.1.4 | BK-GCS-MF-120-GE-LI-0002 | FINAL VENDOR DATA BOOK INDEX | [7 empty] | IFI | MOD
1.1.5 | BK-GCS-MF-120-GE-VL-0001 | SUB VENDOR LIST | [7 empty] | IFI
1.1.6 | BK-GCS-MF-120-GE-LI-0002 | SPARE PART LIST | [7 empty] | IFI
1.2 | Reports
1.2.1 | BK-GCS-MF-120-GE-DO-0001 | FINAL VENDOR DATA BOOK | [7 empty] | IFA/AFC
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-MF-120-QC-PR-0001 | HARDNESS TESTING PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA/AFC
2.1.2 | BK-GCS-MF-120-QC-PR-0002 | INSPECTION AND TEST PLAN (ITP) | [7 empty] | IFA/AFC
2.1.3 | BK-GCS-MF-120-QC-PR-0003 | QUALITY CONTROL PLAN (QCP) | [7 empty] | IFA/AFC
2.1.4 | BK-GCS-MF-120-QC-PR-0004 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | [7 empty] | IFA/AFC
2.1.5 | BK-GCS-MF-120-QC-PR-0005 | PICKLING AND PASSIVATION PROCEDURE | [7 empty] | IFA/AFC
2.1.6 | BK-GCS-MF-120-QC-PR-0006 | POSTWELD HEAT TREATMENT PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA/AFC
2.1.7 | BK-GCS-MF-120-QC-PR-0007 | WPS & PQR (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA/AFC
2.1.8 | BK-GCS-MF-120-QC-PR-0008 | PMI PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA/AFC
2.1.9 | BK-GCS-MF-120-QC-PR-0009 | NDT PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | [7 empty] | IFA/AFC
2.1.10 | BK-GCS-MF-120-QC-PR-0010 | HYDROSTATIC TESTING PRCOCEDURE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | [7 empty] | IFA/AFC
2.1.11 | BK-GCS-MF-120-QC-PR-0011 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | [7 empty] | IFA/AFC
2.1.12 | BK-GCS-MF-120-QC-PR-0012 | WELD REPAIR PROCEDURE | [7 empty] | IFA/AFC
2.1.13 | BK-GCS-MF-120-QC-PR-0013 | PACKING,MARKING,SHIPPING PROCEDURE | [7 empty] | IFA/AFC
2.1.14 | BK-GCS-MF-120-QC-PR-0014 | N2 PURGING PROCEDURE | [7 empty] | IFA/AFC
2.1.15 | BK-GCS-MF-120-QC-PR-0015 | SAT PROCEDURE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
2.2 | Manual
2.2.1 | BK-GCS-MF-120-QC-ML-0001 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
3 | Process
3.1 | Basis/Criteria
3.1.1 | BK-GCS-MF-120-PR-DB-0001 | BASIS OF PROCESS DESIGN FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
3.2 | Philosophy
3.2.1 | BK-GCS-MF-120-PR-PH-0001 | CONTROL PHILOSOPHY | [7 empty] | IFA/AFC
3.3 | Calculation
3.3.1 | BK-GCS-MF-120-PR-CN-0001 | PRESSURE SAFETY VALVE CALCULATION SHEETS | [7 empty] | IFI | MOD
3.4 | Datasheet
3.4.1 | BK-GCS-MF-120-PR-DS-0001 | PROCESS DATA SHEET FOR DEHYDRATION GLYCOL CONTACTOR | [7 empty] | IFI | MOD
3.4.2 | BK-GCS-MF-120-PR-DS-0002 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | [7 empty] | IFI | MOD
3.4.3 | BK-GCS-MF-120-PR-DS-0003 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | [7 empty] | IFI | MOD
3.4.4 | BK-GCS-MF-120-PR-DS-0004 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | [7 empty] | IFI | MOD
3.4.5 | BK-GCS-MF-120-PR-DS-0014 | PROCESS DATA SHEET FOR LEAN GLYCOL FILTER | [7 empty] | IFI | ADD
3.4.6 | BK-GCS-MF-120-PR-DS-0005 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | [7 empty] | IFI | MOD
3.4.7 | BK-GCS-MF-120-PR-DS-0006 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFI | MOD
3.4.8 | BK-GCS-MF-120-PR-DS-0007 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | [7 empty] | IFI | MOD
3.4.9 | BK-GCS-MF-120-PR-DS-0008 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | [7 empty] | IFI | MOD
3.4.10 | BK-GCS-MF-120-PR-DS-0009 | PROCESS DATA SHEET FOR GLYCOL REFLUX CONDENSER | [7 empty] | IFI | MOD
3.4.11 | BK-GCS-MF-120-PR-DS-0010 | PROCESS DATA SHEET FOR GLYCOL REBOILER | [7 empty] | IFI | MOD
3.4.12 | BK-GCS-MF-120-PR-DS-0011 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | [7 empty] | IFA | MOD
3.4.13 | BK-GCS-MF-120-PR-DS-0012 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | [7 empty] | IFA | MOD
3.4.14 | BK-GCS-MF-120-PR-DS-0013 | PROCESS DATA SHEET FOR GLYCOL SURGE DRUM | [7 empty] | IFI | ADD
3.4.15 | BK-GCS-MF-120-PR-DS-0013 | PROCESS DATA SHEET FOR PRESSURE SAFETY VALVES | [7 empty] | IFA/AFC | DEL
3.5 | Drawing/Diagram
3.5.1 | BK-GCS-MF-120-PR-PF-0001 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
3.5.2 | BK-GCS-MF-120-PR-PF-0002 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
3.5.3 | BK-GCS-MF-120-PR-PI-0003 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
3.5.4 | BK-GCS-MF-120-PR-CE-0001 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFA/AFC
3.6 | List
3.6.1 | BK-GCS-MF-120-PR-LI-0001 | EQUIPMENT LIST | [7 empty] | IFI
3.6.2 | BK-GCS-MF-120-PR-LI-0002 | ALARM & TRIP SET POINT LIST | [7 empty] | IFI
3.6.3 | BK-GCS-MF-120-PR-LI-0003 | UTILITY CONSUMPTION LIST | [7 empty] | IFI
3.6.4 | BK-GCS-MF-120-PR-LI-0004 | CHEMICAL CONSUMPTION LIST | [7 empty] | IFI
3.7 | Reports
3.7.1 | BK-GCS-MF-120-PR-RE-0001 | HAZOP STUDY REPORT | [7 empty] | IFI
3.7.2 | BK-GCS-MF-120-PR-RE-0002 | SIL STUDY REPORT | [7 empty] | IFI
4 | Mechanical
4.1 | Fixed Equipment
4.1.1 | Glycol Contactor (C-100)
4.1.1.1 | BK-GCS-MF-120-ME-CN-0001 | MECHANICAL CALCULATION BOOK FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFI
4.1.1.2 | BK-GCS-MF-120-ME-DW-0001 | GENERAL ARRANGEMENT FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFA/AFC
4.1.1.3 | BK-GCS-MF-120-ME-DW-0002 | DETAILS DRAWING FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFI
4.1.1.4 | BK-GCS-MF-120-ME-DW-0003 | NAME PLATE DETAIL DRAWING FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFA/AFC
4.1.1.5 | BK-GCS-MF-120-ME-DW-0004 | TEMPLATE DRAWING FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFI
4.1.1.6 | BK-GCS-MF-120-ME-MP-0001 | WELDING & NDT MAP FOR GLYCOL CONTACTOR (C-100) | [7 empty] | IFI
4.1.2 | Still Column (C-200)
4.1.2.1 | BK-GCS-MF-120-ME-CN-0002 | MECHANICAL CALCULATION BOOK FOR STILL COLUMN (C-200) | [7 empty] | IFI
4.1.2.2 | BK-GCS-MF-120-ME-DW-0005 | GENERAL ARRANGEMENT FOR STILL COLUMN (C-200) | [7 empty] | IFA/AFC
4.1.2.3 | BK-GCS-MF-120-ME-DW-0006 | DETAILS DRAWING FOR STILL COLUMN (C-200) | [7 empty] | IFI
4.1.2.4 | BK-GCS-MF-120-ME-DW-0007 | NAME PLATE DETAIL DRAWING FOR STILL COLUMN (C-200) | [7 empty] | IFA/AFC
4.1.2.5 | BK-GCS-MF-120-ME-MP-0002 | WELDING & NDT MAP FOR STILL COLUMN (C-200) | [7 empty] | IFI
4.1.3 | Glycol Flash Drum (V-120)
4.1.3.1 | BK-GCS-MF-120-ME-CN-0003 | MECHANICAL CALCULATION BOOK FOR GLYCOL FLASH DRUM (V-120) | [7 empty] | IFI
4.1.3.2 | BK-GCS-MF-120-ME-DW-0008 | GENERAL ARRANGEMENT FOR GLYCOL FLASH DRUM (V-120) | [7 empty] | IFA/AFC
4.1.3.3 | BK-GCS-MF-120-ME-DW-0009 | DETAILS DRAWING FOR GLYCOL FLASH DRUM (V-120) | [7 empty] | IFI
4.1.3.4 | BK-GCS-MF-120-ME-DW-0010 | NAME PLATE DETAIL DRAWING FOR GLYCOL FLASH DRUM (V-120) | [7 empty] | IFA/AFC
4.1.3.5 | BK-GCS-MF-120-ME-MP-0003 | WELDING & NDT MAP FOR GLYCOL FLASH DRUM (V-120) | [7 empty] | IFI
4.1.4 | Glycol Surge Drum (V-130)
4.1.4.1 | BK-GCS-MF-120-ME-CN-0011 | MECHANICAL CALCULATION BOOK FOR GLYCOL SURGE DRUM (V-130) | [7 empty] | IFI | ADD
4.1.4.2 | BK-GCS-MF-120-ME-DW-0036 | GENERAL ARRANGEMENT FOR GLYCOL SURGE DRUM (V-130) | [7 empty] | IFA/AFC | ADD
4.1.4.3 | BK-GCS-MF-120-ME-DW-0037 | DETAILS DRAWING FOR GLYCOL SURGE DRUM (V-130) | [7 empty] | IFI | ADD
4.1.4.4 | BK-GCS-MF-120-ME-DW-0038 | NAME PLATE DETAIL DRAWING FOR GLYCOL SURGE DRUM (V-130) | [7 empty] | IFA/AFC | ADD
4.1.4.5 | BK-GCS-MF-120-ME-MP-0011 | WELDING & NDT MAP FOR GLYCOL SURGE DRUM (V-130) | [7 empty] | IFI | ADD
4.1.5 | Glycol Particle Filter (F-100 A/B)
4.1.5.1 | BK-GCS-MF-120-ME-CN-0004 | MECHANICAL CALCULATION BOOK FOR GLYCOL PARTICLE FILTER (F-100 A/B) | [7 empty] | IFI | MOD
4.1.5.2 | BK-GCS-MF-120-ME-DW-0011 | GENERAL ARRANGEMENT FOR GLYCOL PARTICLE FILTER (F-100 A/B) | [7 empty] | IFA/AFC | MOD
4.1.5.3 | BK-GCS-MF-120-ME-DW-0012 | DETAILS DRAWING FOR GLYCOL PARTICLE FILTER (F-100 A/B) | [7 empty] | IFI | MOD
4.1.5.4 | BK-GCS-MF-120-ME-DW-0013 | NAME PLATE DETAIL DRAWING FOR GLYCOL PARTICLE FILTER (F-100 A/B) | [7 empty] | IFA/AFC | MOD
4.1.5.5 | BK-GCS-MF-120-ME-MP-0004 | WELDING & NDT MAP FOR GLYCOL PARTICLE FILTER (F-100 A/B) | [7 empty] | IFI | MOD
4.1.6 | Glycol Carbon Filter (F-200)
4.1.6.1 | BK-GCS-MF-120-ME-CN-0005 | MECHANICAL CALCULATION BOOK FOR GLYCOL CARBON FILTER (F-200) | [7 empty] | IFI | MOD
4.1.6.2 | BK-GCS-MF-120-ME-DW-0014 | GENERAL ARRANGEMENT FOR GLYCOL CARBON FILTER (F-200) | [7 empty] | IFA/AFC | MOD
4.1.6.3 | BK-GCS-MF-120-ME-DW-0015 | DETAILS DRAWING FOR GLYCOL CARBON FILTER (F-200) | [7 empty] | IFI | MOD
4.1.6.4 | BK-GCS-MF-120-ME-DW-0016 | NAME PLATE DETAIL DRAWING FOR GLYCOL CARBON FILTER (F-200) | [7 empty] | IFA/AFC | MOD
4.1.6.5 | BK-GCS-MF-120-ME-MP-0005 | WELDING & NDT MAP FOR GLYCOL CARBON FILTER (F-200) | [7 empty] | IFI | MOD
Lean Glycol Filter (F-300)
4.1.7.1 | BK-GCS-MF-120-ME-CN-0010 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL FILTER (F-300) | [7 empty] | IFI | ADD
4.1.7.2 | BK-GCS-MF-120-ME-DW-0033 | GENERAL ARRANGEMENT FOR LEAN GLYCOL FILTER (F-300) | [7 empty] | IFA/AFC | ADD
4.1.7.3 | BK-GCS-MF-120-ME-DW-0034 | DETAILS DRAWING FOR LEAN GLYCOL FILTER (F-300) | [7 empty] | IFI | ADD
4.1.7.4 | BK-GCS-MF-120-ME-DW-0035 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL FILTER (F-300) | [7 empty] | IFA/AFC | ADD
4.1.7.5 | BK-GCS-MF-120-ME-MP-0010 | WELDING & NDT MAP FOR LEAN GLYCOL FILTER (F-300) | [7 empty] | IFI | ADD
4.1.8 | Glycol Reflux Condenser (E-100)
4.1.8.1 | BK-GCS-MF-120-ME-CN-0006 | THERMAL/MECHANICAL CALCULATION BOOK FOR GLYCOL REFLUX CONDENSER (E-100) | [7 empty] | IFI
4.1.8.2 | BK-GCS-MF-120-ME-DW-0017 | GENERAL ARRANGEMENT FOR GLYCOL REFLUX CONDENSER (E-100) | [7 empty] | IFA/AFC
4.1.8.3 | BK-GCS-MF-120-ME-DW-0018 | DETAILS DRAWING FOR GLYCOL REFLUX CONDENSER (E-100) | [7 empty] | IFI
4.1.8.4 | BK-GCS-MF-120-ME-DW-0019 | NAME PLATE DETAIL DRAWING FOR GLYCOL REFLUX CONDENSER (E-100) | [7 empty] | IFA/AFC
4.1.8.5 | BK-GCS-MF-120-ME-MP-0006 | WELDING & NDT MAP FOR GLYCOL REFLUX CONDENSER (E-100) | [7 empty] | IFI
4.1.9 | Rich-Lean Glycol Heat Exchanger (E-200)
4.1.9.1 | BK-GCS-MF-120-ME-CN-0007 | THERMAL/MECHANICAL CALCULATION BOOK FOR RICH-LEAN GLYCOL H.E. (E-200) | [7 empty] | IFI
4.1.9.2 | BK-GCS-MF-120-ME-DW-0020 | GENERAL ARRANGEMENT FOR RICH-LEAN GLYCOL H.E. (E-200) | [7 empty] | IFA/AFC
4.1.9.3 | BK-GCS-MF-120-ME-DW-0021 | DETAILS DRAWING FOR RICH-LEAN GLYCOL H.E. (E-200) | [7 empty] | IFI
4.1.9.4 | BK-GCS-MF-120-ME-DW-0022 | NAME PLATE DETAIL DRAWING FOR RICH-LEAN GLYCOL H.E. (E-200) | [7 empty] | IFA/AFC
4.1.9.5 | BK-GCS-MF-120-ME-MP-0007 | WELDING & NDT MAP FOR RICH-LEAN GLYCOL H.E. (E-200) | [7 empty] | IFI
4.1.10 | Lean Glycol-Dry Gas Heat Exchanger (E-300)
4.1.10.1 | BK-GCS-MF-120-ME-CN-0008 | THERMAL/MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL GAS H.E. (E-300) | [7 empty] | IFI
4.1.10.2 | BK-GCS-MF-120-ME-DW-0023 | GENERAL ARRANGEMENT FOR LEAN GLYCOL GAS H.E. (E-300) | [7 empty] | IFA/AFC
4.1.10.3 | BK-GCS-MF-120-ME-DW-0024 | DETAILS DRAWING FOR LEAN GLYCOL GAS H.E. (E-300) | [7 empty] | IFI
4.1.10.4 | BK-GCS-MF-120-ME-DW-0025 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL GAS H.E. (E-300) | [7 empty] | IFA/AFC
4.1.10.5 | BK-GCS-MF-120-ME-MP-0008 | WELDING & NDT MAP FOR LEAN GLYCOL GAS H.E. (E-300) | [7 empty] | IFI
4.1.11 | Reboiler (R-100)
4.1.11.1 | BK-GCS-MF-120-ME-CN-0009 | THERMAL/MECHANICAL CALCULATION BOOK FOR REBOILER (R-100) | [7 empty] | IFI
4.1.11.2 | BK-GCS-MF-120-ME-DW-0026 | GENERAL ARRANGEMENT FOR REBOILER (R-100) | [7 empty] | IFA/AFC
4.1.11.3 | BK-GCS-MF-120-ME-DW-0027 | DETAILS DRAWING FOR REBOILER (R-100) | [7 empty] | IFI
4.1.11.4 | BK-GCS-MF-120-ME-DW-0028 | NAME PLATE DETAIL DRAWING FOR REBOILER (R-100) | [7 empty] | IFA/AFC
4.1.11.5 | BK-GCS-MF-120-ME-MP-0009 | WELDING & NDT MAP FOR REBOILER (R-100) | [7 empty] | IFI
4.1.12 | List
4.1.12.1 | BK-GCS-MF-120-ME-LI-0001 | LUBRICATION LIST | [7 empty] | IFI | MOD
4.2 | Machinery/Package
4.2.1 | Pumps
4.2.1.1 | BK-GCS-MF-120-ME-DW-0029 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA/AFC
4.2.1.2 | BK-GCS-MF-120-ME-DW-0030 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFI
4.2.1.3 | BK-GCS-MF-120-ME-DW-0031 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | [7 empty] | IFA/AFC
4.2.2 | Burner
4.2.2.1 | BK-GCS-MF-120-ME-DS-0001 | BURNER DATA SHEET FOR GLYCOL REBOILER | [7 empty] | IFI
4.2.2.2 | BK-GCS-MF-120-ME-DW-0032 | BURNER DRAWING FOR GLYCOL REBOILER | [7 empty] | IFI
5 | Piping
5.1 | Drawing
5.1.1 | BK-GCS-MF-120-PI-DW-0001 | PACKAGE PLOT PLAN DRAWING | [7 empty] | IFA/AFC
5.1.2 | BK-GCS-MF-120-PI-DW-0002 | PIPING GENERAL ARRANGEMENT DRAWING | [7 empty] | IFA/AFC
5.1.3 | BK-GCS-MF-120-PI-DW-0003 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI
5.2 | List
5.2.1 | BK-GCS-MF-120-PI-LI-0001 | LINE LIST | [7 empty] | IFI
5.2.2 | BK-GCS-MF-120-PI-LI-0002 | TIE-IN-LIST | [7 empty] | IFA/AFC
5.3 | Reports
5.3.1 | BK-GCS-MF-120-PI-RT-0001 | PDMS MODEL REVIEW REPORT (60%) | [7 empty] | IFA/AFC
5.3.2 | BK-GCS-MF-120-PI-RT-0002 | PDMS MODEL REVIEW REPORT (90%) | [7 empty] | IFA/AFC
5.3.3 | BK-GCS-MF-120-PI-RT-0003 | STRESS ANALYSIS REPORT | [7 empty] | IFI
6 | Instrument
6.1 | Calculation
6.1.1 | BK-GCS-MF-120-IN-CN-0001 | CONTROL VALVE CALCULATION SHEETS | [7 empty] | IFA/AFC
6.1.2 | BK-GCS-MF-120-IN-CN-0002 | FLOW ELEMENT CALCULATION SHEETS | [7 empty] | IFA/AFC
6.2 | Drawing
6.2.1 | BK-GCS-MF-120-IN-DW-0001 | CONTROL SYSTEM CONFIGURATION BLOCK DIAGRAM | [7 empty] | IFA/AFC
6.2.2 | BK-GCS-MF-120-IN-DW-0002 | ESD/BMS SYSTEM CONFIGURATION BLOCK DIAGRAM | [7 empty] | IFA/AFC
6.2.3 | BK-GCS-MF-120-IN-DW-0003 | INSTRUMENT JUNCTION BOX LAYOUT AND WIRING TERMINATION DIAGRAM | [7 empty] | IFI | MOD
6.2.4 | BK-GCS-MF-120-IN-DW-0004 | BURNER OPERATION PANEL LAYOUT & WIRING DIAGRAM WITH CONNECTIONS & DIMENSIONS | [7 empty] | IFA/AFC
6.2.5 | BK-GCS-MF-120-IN-DW-0005 | HOOK UP DRAWING | [7 empty] | IFI | MOD
6.2.6 | BK-GCS-MF-120-IN-DW-0006 | INSTRUMENT LOCATION LAYOUT | [7 empty] | IFI | MOD
6.2.7 | BK-GCS-MF-120-IN-DW-0007 | CONTROL PANEL LAYOUT AND ARRANGEMENT | [7 empty] | IFA/AFC
6.2.8 | BK-GCS-MF-120-IN-DW-0008 | ESD/BMS PANEL LAYOUT AND ARRANGEMENT | [7 empty] | IFA/AFC
6.2.9 | BK-GCS-MF-120-IN-DW-0009 | CONTROL SYSTEM WIRING DIAGRAM AND CONNECTIONS | [7 empty] | IFA/AFC
6.2.10 | BK-GCS-MF-120-IN-DW-0010 | ESD/BMS SYSTEM WIRING DIAGRAM AND CONNECTIONS | [7 empty] | IFA/AFC
6.2.11 | BK-GCS-MF-120-IN-DW-0011 | CONTROL SYSTEM LOGIC DIAGRAM | [7 empty] | IFA/AFC
6.2.12 | BK-GCS-MF-120-IN-DW-0012 | ESD/BMS SYSTEM LOGIC DIAGRAM | [7 empty] | IFA/AFC
6.2.13 | BK-GCS-MF-120-IN-DW-0013 | PRINT OUT OF HMI FOR BMS AND UCP | [7 empty] | IFA/AFC
6.2.14 | BK-GCS-MF-120-IN-DW-0014 | CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING | [7 empty] | IFA/AFC
6.2.15 | BK-GCS-MF-120-IN-DW-0015 | INSTRUMENT EARTH DISTRIBUTION DIAGRAM | [7 empty] | IFI | MOD
6.2.16 | BK-GCS-MF-120-IN-DW-0016 | INSTRUMENT CABLE ROUTE/ MAIN TUBING LAYOUT DRAWING | [7 empty] | IFI | MOD
6.2.17 | BK-GCS-MF-120-IN-DW-0017 | ESD LEVEL HIERARCHY | [7 empty] | IFI | MOD
6.3 | Datasheet
6.3.1 | BK-GCS-MF-120-IN-DS-0001 | INSTRUMENT D.S. FOR CONTROL VALVES | [7 empty] | IFA/AFC
6.3.2 | BK-GCS-MF-120-IN-DS-0002 | INSTRUMENT D.S. FOR ON/OFF VALVES | [7 empty] | IFA/AFC
6.3.3 | BK-GCS-MF-120-IN-DS-0003 | INSTRUMENT D.S. FOR H2O ANALYZER | [7 empty] | IFA/AFC
6.3.4 | BK-GCS-MF-120-IN-DS-0004 | INSTRUMENT D.S. FOR TEMPERATURE GAUGE | [7 empty] | IFA/AFC
6.3.5 | BK-GCS-MF-120-IN-DS-0005 | INSTRUMENT D.S. FOR TEMPERATURE TRANSMITTERS | [7 empty] | IFA/AFC
6.3.6 | BK-GCS-MF-120-IN-DS-0006 | INSTRUMENT D.S. FOR PRESSURE GAUGES AND DIFF. PRESSURE GAUGES | [7 empty] | IFA/AFC
6.3.7 | BK-GCS-MF-120-IN-DS-0007 | INSTRUMENT D.S. FOR PRESSURE TRANSMITTERS AND DIFFE. PRESSURE TRANSMITTERS | [7 empty] | IFA/AFC
6.3.8 | BK-GCS-MF-120-IN-DS-0008 | INSTRUMENT D.S. FOR PRESSURE REGULATOR VALVES | [7 empty] | IFA/AFC
6.3.9 | BK-GCS-MF-120-IN-DS-0009 | INSTRUMENT D.S. FOR FLOW ELEMENTS | [7 empty] | IFA/AFC
6.3.10 | BK-GCS-MF-120-IN-DS-0010 | INSTRUMENT D.S. FOR LEVEL GAUGES | [7 empty] | IFA/AFC
6.3.11 | BK-GCS-MF-120-IN-DS-0011 | INSTRUMENT D.S. FOR LEVEL TRANSMITTERS | [7 empty] | IFA/AFC
6.3.12 | BK-GCS-MF-120-IN-DS-0012 | FLAME SCANNER DATA SHEET | [7 empty] | IFA/AFC
6.3.13 | BK-GCS-MF-120-IN-DS-0013 | INSTRUMENT D.S. FOR SAFETY VALVES | [7 empty] | IFA/AFC | ADD
6.4 | Procedure/Plan
6.4.1 | BK-GCS-MF-120-IN-PR-0001 | FAT PROCEDURE FOR CONTROL SYSTEM | [7 empty] | IFA/AFC
6.4.2 | BK-GCS-MF-120-IN-PR-0002 | FAT PROCEDURE FOR ESD/BMS SYSTEM | [7 empty] | IFA/AFC
6.4.3 | BK-GCS-MF-120-IN-PR-0003 | SAT PROCEDURE FOR CONTROL SYSTEM | [7 empty] | IFA/AFC
6.4.4 | BK-GCS-MF-120-IN-PR-0004 | SAT PROCEDURE FOR ESD/BMS SYSTEM | [7 empty] | IFA/AFC
6.5 | List
6.5.1 | BK-GCS-MF-120-IN-LI-0001 | INSTRUMENT LIST | [7 empty] | IFI
6.5.2 | BK-GCS-MF-120-IN-LI-0002 | INPUT/OUTPUT SIGNAL LIST | [7 empty] | IFI
6.5.3 | BK-GCS-MF-120-IN-LI-0003 | INSTRUMENT CABLE LIST | [7 empty] | IFI
6.5.4 | BK-GCS-MF-120-IN-LI-0004 | UCP AND BMS SYSTEM POWER CONSUMPTION LIST | [7 empty] | IFI
6.5.5 | BK-GCS-MF-120-IN-LI-0005 | MODBUS IO LIST (MODBUS MAPPING LIST) | [7 empty] | IFI
7 | Electrical
7.1 | Drawing
7.1.1 | BK-GCS-MF-120-EL-DW-0001 | ELECTRICAL SINGLE LINE DIAGRAM | [7 empty] | IFA/AFC
7.1.2 | BK-GCS-MF-120-EL-DW-0002 | EARTHING DETAIL LAYOUT | [7 empty] | IFA/AFC
7.1.3 | BK-GCS-MF-120-EL-DW-0003 | ELECTRICAL CABLE ROUTE | [7 empty] | IFI
7.1.4 | BK-GCS-MF-120-EL-DW-0004 | ELECTRICAL PANEL LAYOUT AND WIRING DIAGRAM | [7 empty] | IFA/AFC
7.1.5 | BK-GCS-MF-120-EL-DW-0005 | LOCAL CONTROL STATION (LCS) PANEL LAYOUT AND WIRING DIAGRAM | [7 empty] | IFA/AFC
7.1.6 | BK-GCS-MF-120-EL-DW-0006 | ELECTRICAL EQUIPMENT LAYOUT | [7 empty] | IFA/AFC
7.2 | List
7.2.1 | BK-GCS-MF-120-EL-LI-0001 | POWER AND CONTROL CABLE LIST | [7 empty] | IFI
7.2.2 | BK-GCS-MF-120-EL-LI-0002 | ELECTRICAL LOAD LIST | [7 empty] | IFI
7.2.3 | BK-GCS-MF-120-EL-LI-0003 | ELECTRICAL SIGNAL LIST | [7 empty] | IFI
7.3 | Datasheet
7.3.1 | BK-GCS-MF-120-EL-DS-0001 | ELECTRICAL MOTORS DATA SHEETS, CURVES, DRAWINGS AND CERTIFICATES | [7 empty] | IFA/AFC | MOD
7.3.2 | BK-GCS-MF-120-EL-DS-0002 | CABLE DATASHEETS | [7 empty] | IFA/AFC
7.3.3 | BK-GCS-MF-120-EL-DS-0003 | ELECTRICAL PANEL DATASHEETS | [7 empty] | IFA/AFC
7.3.4 | BK-GCS-MF-120-EL-DS-0004 | LOCAL CONTROL STATION (LCS) DATASHEETS | [7 empty] | IFA/AFC
7.3.5 | BK-GCS-MF-120-EL-DS-0005 | HAZARDOUS AREA CLASSIFICATION AND IP CERTIFICATE FOR MOTORS, LCS, LCP, LIGHTINGS, JB, HEATERS, ETC | [7 empty] | IFA/AFC | ADD
7.3.6 | BK-GCS-MF-120-EL-DS-0006 | ELECTRICAL MOTORS FAT REPORTS | [7 empty] | IFA/AFC | ADD
8 | Structure
8.1 | Calculation
8.1.1 | BK-GCS-MF-120-ST-CN-0001 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI | MOD
8.1.2 | BK-GCS-MF-120-ST-CN-0002 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI | MOD
8.2 | Drawing
8.2.1 | BK-GCS-MF-120-ST-DW-0001 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | [7 empty] | IFI | MOD
V02