## Sheet1
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PM-LI-0001_V01 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-MF- 0006 |  |  | Transmital Date: 2024/09/14
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-MF-120-PM-LI-0001_V01 |  |  | CRS Status: CM
| Comments (NISOC) |  | Email/letter No. | Comment Date | Clarification (By Vendor) |  |  | Client Conclusion
QC comments :
1 |  |  | 03/2294/60407 | 1403/02/19 | 1- اعمال شد.
2 |  |  |  |  | 2- این مورد در جلسات مورخ 1403/05/24 و 1403/06/07 مطرح، بررسی و مرتفع گردید.
3 |  |  |  |  | 3-مطابق با مذاکرات تکمیلی صورت گرفته با کارشناس محترم کارفرمای اصلی (با توجه به وجود ردیف ها و بخش های مربوطه در ITP کلی پکیج، موارد مرتفع گردید.
|  |  | صورتجلسه مورخ 1403/05/24 |  | ضمنا موارد توافق شده در صورتجلسه مورخ 1403/05/24 نیز اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (HIRGAN/PEDCO/NISOC) |  |  |  |  | VENDOR
| Commented By: BAVARSAD | Signature | H.NASERIZADEH |  |  | Clarified By: | Signature
| Date: |  |  |  |  | DATE:3/26/2024