## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PR-DB-0001 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: BASIS OF PROCESS DESIGN FOR GAS DEHYDRATION PACKAGE |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-MF-0005 |  |  | Transmital Date: 2024/10/12
[5 empty] | CRS No: PEDCO- CRS-BK-GCS-MF-120-PR-DB-0001-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دما و ترکیب درصدFuel gas مصرفی برای شرایط زمستان و تابستان تصحیح گردد. |  | PEDCO COMMENTS ON BK-HD-PEDCO-SVTR-MF-0005 | 2024-03-16 | کامنت ها مطابق با صورتجلسه به نحو مقتضی اعمال گردید.
2 | درخصوص make-up گلایکول مصرفی اطلاعاتی ارائه نشده است. ضروری است به این موضوع نیز پرداخته شود. |  | PEDCO COMMENTS ON BK-HD-PEDCO-SVTR-MF-0005 | 2024-03-16
3 | مطابق بخش 5.7.4 دما در Reboiler Stage در حدود 204 درجه سانتیگراد است. ولیکن جریان خروجی از برج 196.6 درجه است. آیا این اختلاف دما برای ورودی و خروجی Surge drum مورد تایید است؟ (با لحاظ گرم شدن stripping gas در بخش reboiler section) |  | PEDCO COMMENTS ON BK-HD-PEDCO-SVTR-MF-0005 | 2024-03-16
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.Esfandani P.bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 16/03/2024 |  |  |  |  | Date: