## Sheet1 (hidden)
WBS | Task Name | W.F.
0 | BINAK OILFIELD DEVELOPMENT | 100 | 100 | 100
1 | DOCUMENTS | 15 | 5 | 5
1.1 | Vendor's Document (According to VPIS) Document Subject According to client Approval | 14.75 | 4.9 | 4.9167 |  | 98.33%
1.1.1 | WORK BREAKDOWN STRUCTURE FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.2 | VENDOR PRINT INDEX & SCHEDULE (VPIS) FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.3 | TIME SCHEDULE FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.4 | FINAL VENDOR DATA BOOK INDEX FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.5 | SHIPPING & INSTALLATION MANUAL (INCLUDING HANDLING, TRANSPORTATION, STORAGE AND ERECTION) FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.6 | SUB-VENDOR LIST FOR GAS DEHYDRATION PACKAGE | 0.15 | 1.017% | 0.05 |  | 1.017%
1.1.7 | MARKING & PACKING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, REBOILER, DRUMS, FILTERS, COLUMNS, EXCHANGERS) | 0.11 | 0.7458% | 0.036667 |  | 0.7458%
1.1.8 | MARKING & PACKING PROCEDURE FOR GLYCOL CIRCULATION PUMPS | 0.1 | 0.678% | 0.033333 |  | 0.678%
1.1.9 | INSPECTION AND TEST PLAN FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.4746% | 0.023333 |  | 0.4746%
1.1.10 | HARDNESS TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.11 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.12 | PICKLING AND PASSIVATION PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.13 | POSTWELD HEAT TREATMENT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.14 | PMI PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.15 | HYDROSTATIC TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.16 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.17 | WELD REPAIR PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.18 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.19 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.20 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.34 | 0.023051 | 0.11333 |  | 2.305%
1.1.21 | UCP LOGIC DESCRIPTION FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.22 | BMS LOGIC DESCRIPTION FOR DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.23 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.24 | PROCESS DATA SHEET FOR DEHYDRATION COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.25 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.26 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.27 | PROCESS DATA SHEET FOR GLYCOL STRIPPING COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.28 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.29 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.30 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN CONDENSER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.31 | PROCESS DATA SHEET FOR GLYCOL REBOILER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.32 | PROCESS DATA SHEET FOR GLYCOL SURGE VESSEL | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.33 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.34 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.35 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.36 | EQUIPMENT LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.37 | ALARM & TRIP SET POINT LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.38 | UTILITY CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.39 | CHEMICAL CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.40 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.41 | PERFORMANCE TEST PROCEDURE FOR GAS DEHYDRATION PACKAGE (SAT Procedure)) | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.42 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.43 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.44 | Mechanical Calculation Book for C-100 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.45 | Lifting Calculation Book for C-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.46 | General Arrangement Drawing for C-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.47 | Detail of Body for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.48 | NOZZLE & Manhole Detail Drawing for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.49 | External Attachment Drawing for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.50 | Internal Welded Attachments for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.51 | Name Plate Detail Drawing for C-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.52 | NDT Map for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.53 | Welding Map for C-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.54 | Mechanical Calculation Book for C-200 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.55 | General Arrangement Drawing for C-200 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.56 | Detail of Body & Nozzle drawing for C-200 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.57 | Name Plate Detail Drawing for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.58 | Internal Welded & External Attachments for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.59 | NDT Map for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.60 | Welding Map for C-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.61 | Mechanical Calculation Book for C-300 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.62 | General Arrangement Drawing for C-300 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.63 | Detail drawing for C-300 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.64 | Name Plate Detail Drawing for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.65 | NDT Map for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.66 | Welding Map for C-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.67 | Mechanical & Lifting Calculation Book for V-120 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.68 | General Arrangement Drawing for V-120 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.69 | Detail of Body for V-120 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.70 | Nozzle & Manhole Detail Drawing for V-120 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.71 | External Attachments & Saddle drawing for V-120 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.72 | Name Plate Detail Drawing for V-120 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.73 | NDT Map for V-120 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.74 | Welding Map for V-120 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.75 | Mechanical Calculation Book for F-100 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.76 | General Arrangement Drawing for F-100 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.77 | Detail Drawing for F-100 | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.78 | Name Plate Detail Drawing for F-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.79 | Mechanical Calculation Book for F-200 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.80 | General Arrangement Drawing for F-200 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.81 | Detail Drawing for F-200 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.82 | Name Plate Detail Drawing for F-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.83 | Mechanical Calculation Book for E-100 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.84 | General Arrangement Drawing for E-100 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.85 | Detail Drawing for E-100 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.86 | Name Plate Detail Drawing for E-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.87 | Mechanical Calculation Book for E-200 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.88 | General Arrangement Drawing for E-200 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.89 | Detail Drawing for E-200 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.90 | Name Plate Detail Drawing for E-200 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.91 | Mechanical Calculation Book for E-300 | 0.09 | 0.0061017 | 0.03 |  | 0.6102%
1.1.92 | General Arrangement Drawing for E-300 | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.93 | Detail Drawing for E-300 | 0.07 | 0.0047458 | 0.023333 |  | 0.4746%
1.1.94 | Name Plate Detail Drawing for E-300 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.95 | Mechanical & Lifting Calculation Book for R-100 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.96 | General Arrangement Drawing for R-100 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.97 | Detail of Body for R-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.98 | Nozzle & Manhole Detail Drawing for R-100 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.99 | Detail of Saddle drawing for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.100 | Internal & External Welded Attachments for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.101 | Name Plate Detail Drawing for R-100 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.102 | NDT Map for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.103 | Welding Map for R-100 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.104 | Mechanical & Lifting Calculation Book for V-130 | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.105 | General Arrangement Drawing for V-130 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.106 | Detail of Body for V-130 | 0.04 | 0.0027119 | 0.013333 |  | 0.2712%
1.1.107 | Nozzle & Manhole Detail Drawing for V-130 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.108 | External Attachments & Saddle drawing for V-130 | 0.03 | 0.0020339 | 0.01 |  | 0.2034%
1.1.109 | Name Plate Detail Drawing for V-130 | 0.01 | 0.00067797 | 0.0033333 |  | 0.0678%
1.1.110 | NDT Map for V-130 | 0.02 | 0.0013559 | 0.0066667 |  | 0.1356%
1.1.111 | Welding Map for V-130 | 0.42 | 0.028475 | 0.14 |  | 2.847%
1.1.112 | BURNER DATA SHEET FOR GLYCOL REBOILER | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.113 | BURNER DRAWING FOR GLYCOL REBOILER | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.114 | LUBRICATION LIST FOR GAS DEHYDRATION PACKAGE | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.115 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.116 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.117 | PUMPS INSTALLATION, OPERATION AND MAINTENANCE MANUAL FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.118 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | 0.05 | 0.0033898 | 0.016667 |  | 0.339%
1.1.119 | TWO YEARS & COMMISSIONING SPARE PART LIST FOR GLYCOL CIRCULATION PUMPS | 0.06 | 0.0040678 | 0.02 |  | 0.4068%
1.1.120 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.121 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.122 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | 0.08 | 0.0054237 | 0.026667 |  | 0.5424%
1.1.123 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (30%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.124 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (60%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.125 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (90%) FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.126 | PACKAGE PLOT PLAN FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.127 | PIPING GENERAL ARRANGEMENT DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.128 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.129 | LINE LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.130 | TIE-IN-LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.131 | SUPPORT LIST FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.132 | STRESS ANALYSIS REPORT FOR GAS DEHYDRATION PACKAGE | 0.13 | 0.0088136 | 0.043333 |  | 0.8814%
1.1.133 | Electrical single line diagram | 0.15 | 0.010169 | 0.05 |  | 1.017%
1.1.134 | Power and control cable list | 0.16 | 0.010847 | 0.053333 |  | 1.085%
1.1.135 | Earthing detail layout | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.136 | Electrical load list | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.137 | Electrical/Instrument Cable Route Layout | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.138 | Electrical motor data sheets | 0.14 | 0.0094915 | 0.046667 |  | 0.9492%
1.1.139 | Electrical panel layout and wiring diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.140 | Local control station (LCS) panel layout and wiring diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.141 | Instrument list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.142 | Input/Output signal list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.143 | Instrument and electrical block schematic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.144 | UCP system configuration diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.145 | BMS system configuration diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.146 | Instrument junction box layout and wiring termination diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.147 | Burner operation panel layout & wiring diagram with connections & dimensions | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.148 | Control valve calculation sheets | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.149 | Instrument D.S. for control valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.150 | Instrument cable list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.151 | Instrument D.S. for On/Off valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.152 | Instrument D.S. for H2O analyzer | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.153 | Instrument D.S. for temperature gauge | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.154 | Instrument D.S. for temperature transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.155 | Instrument D.S. for pressure gauges and differential gauges | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.156 | Instrument D.S. for pressure transmitters and differentia pressure transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.157 | Pressure safety valves calculation | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.158 | Pressure safety valves data sheet | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.159 | Instrument D.S. for pressure regulator valves | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.160 | Flow element calculation sheets | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.161 | Instrument D.S. for flow elements | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.162 | Instrument D.S. for level gauges | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.163 | Instrument D.S. for level transmitters | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.164 | Hook up drawing | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.165 | Instrument location layout | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.166 | Flame scanner data sheet | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.167 | UCP panel layout and arrangement | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.168 | BMS panel layout and arrangement | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.169 | UCP system wiring diagram and connections | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.170 | BMS system wiring diagram and connections | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.171 | UCP and BMS system power consumption list | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.172 | Instrument loop diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.173 | Modbus IO list (Modbus mapping list) | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.174 | FAT procedure for UCP system | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.175 | FAT procedure for BMS system | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.176 | UCP system Logic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.177 | BMS system Logic diagram | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.1.178 | PRINT OUT OF HMI FOR BMS and UCP | 0.1 | 0.0067797 | 0.033333 |  | 0.678%
1.2 | WPS-PQR | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.3 | WQT | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.4 | NDT Procedures (VT-PT-MT-UT-RT) | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.5 | NDT Personal Certificate | 0.05 | 0.01 | 0.016667 |  | 0.3333%
1.6 | Calibration | 0.05 | 0.01 | 0.016667 |  | 0.3333%
2 | TEST AND INSPECTION ACTIVITIES | 78 | 88 | 88
2.1 | Vessel | 30.39 | 30.39 | 30.39 |  | 38.96%
2.1.1 | Raw Material Of Pressure Parts | 7 | 0.23034 | 7 |  | 23.03%
| PLATE |  | 0 | 4.2 | √ | 60%
| FLANG |  | 0 | 2.1 | √ | 30%
| PIPE |  | 0 | 0.7 | √ | 10%
2.1.2 | Raw Material Of Non-Pressure Parts | 2.15 | 0.070747 | 2.15 |  | 7.075%
| PLATE |  | 0 | 1.935 | √ | 90%
| PROFILE |  | 0 | 0.215 | √ | 10%
2.1.3 | Internals | 0.61 | 0.020072 | 0.61 |  | 2.007%
2.1.4 | VT & DT For Raw Material | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.5 | Consumable Material (Electrode) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.6 | Cutting & Marking | 1.52 | 0.050016 | 1.52 | √ | 5.002%
2.1.7 | Rolling & Forming | 2.43 | 0.079961 | 2.43 | √ | 7.996%
2.1.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) | 2.13 | 0.070089 | 2.13 | √ | 7.009%
2.1.9 | Welding | 3.95 | 0.12998 | 3.95 | √ | 13%
2.1.10 | Ferrite Check For Welding Gladded Parts | 2.43 | 0.079961 | 2.43 | √ | 7.996%
2.1.11 | NDT (VT,MT.PT,UT,RT) | 1.22 | 0.040145 | 1.22 |  | 4.014%
2.1.12 | Weld Repair | 1.52 | 0.050016 | 1.52 |  | 5.002%
2.1.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 1.22 | 0.040145 | 1.22 |  | 4.014%
2.1.14 | Final Visual and Dimensional | 0.91 | 0.029944 | 0.91 |  | 2.994%
2.1.15 | PWHT (If Any) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.16 | Hardness Check | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.17 | NDT After PWHT | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.18 | Pneumatic Test (Pad Test) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.19 | Hydrostatic Test Water Quality | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.20 | Hydrostatic Test | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.21 | Draining & Drying | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.22 | Abrasive & Paint Material | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.1.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) | 0.3 | 0.0098717 | 0.3 |  | 0.9872%
2.2 | Heat Exchangers | 4.72 | 4.66 | 4.66 |  | 6.051%
2.2.1 | Raw Material for Pressure parts | 1.12 | 0.24034 | 1.1058 |  | 23.73%
| PLATE |  | 0 | 0.66346 | √ | 60%
| FLANG |  | 0 | 0.33173 | √ | 30%
| PIPE |  | 0 | 0.11058 | √ | 10%
2.2.2 | Raw Material for Non-Pressure parts | 0.37 | 0.079399 | 0.3653 |  | 7.839%
| PLATE |  | 0 | 0.32877 | √ | 90%
| PROFILE |  | 0 | 0.03653 | √ | 10%
2.2.3 | VT & DT For Raw Material | 0.05 | 0.01073 | 0.049364 | √ | 1.059%
2.2.4 | Consumable Material (Electrode) | 0.05 | 0.01073 | 0.049364 | √ | 1.059%
2.2.5 | Cutting & Marking | 0.23 | 0.049356 | 0.22708 | √ | 4.873%
2.2.6 | Rolling & Forming | 0.37 | 0.079399 | 0.3653 | √ | 7.839%
2.2.7 | Tube to Tube Sheet Joint {Expansion) | 0.35 | 0.075107 | 0.34555 | √ | 7.415%
2.2.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, … ) | 0.61 | 0.1309 | 0.60225 |  | 12.92%
2.2.9 | Welding | 0.37 | 0.079399 | 0.3653 |  | 7.839%
2.2.10 | NDT (VT,MT.PT,UT,RT) | 0.19 | 0.040773 | 0.18758 |  | 4.025%
2.2.11 | Weld Repair | 0.23 | 0.049356 | 0.22708 |  | 4.873%
2.2.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 0.19 | 0.040773 | 0.18758 |  | 4.025%
2.2.13 | Final Visual and Dimensional | 0.14 | 0.030043 | 0.13822 |  | 2.966%
2.2.14 | PWHT (If Any) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.15 | Hardness Check | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.16 | NDT After PWHT | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.17 | Pneumatic Test (Pad Test) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.18 | Hydrostatic Test Water Quality | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.19 | Hydrostatic Test | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.20 | Draining & Drying | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.21 | Abrasive & Paint Material | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.2.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.05 | 0.01073 | 0.049364 |  | 1.059%
2.3 | Re-boiler | 2.32 | 2.45 | 2.45 |  | 2.974%
2.3.1 | Raw Material for Pressure parts | 0.59 | 0.24082 | 0.62306 |  | 25.43%
| PLATE |  | 0 | 0.37384 | √ | 60%
| FLANG |  | 0 | 0.18692 | √ | 30%
| PIPE |  | 0 | 0.062306 | √ | 10%
2.3.2 | Raw Material for Non-Pressure parts | 0.21 | 0.085714 | 0.22177 |  | 9.052%
| PLATE |  | 0 | 0.19959 | √ | 90%
| PROFILE |  | 0 | 0.022177 | √ | 10%
2.3.4 | Consumable Material (Electrode) | 0.02 | 0.0081633 | 0.021121 | √ | 0.8621%
2.3.5 | Cutting & Marking | 0.12 | 0.04898 | 0.12672 | √ | 5.172%
2.3.6 | Rolling & Forming | 0.21 | 0.085714 | 0.22177 | √ | 9.052%
2.3.7 | Weld Preparation and Fit-Up (Shell,Nozzle, ... ) | 0.33 | 0.13469 | 0.34849 | √ | 14.22%
2.3.8 | Welding | 0.21 | 0.085714 | 0.22177 | √ | 9.052%
2.3.9 | NDT (VT,MT.PT,UT,RT) | 0.11 | 0.044898 | 0.11616 |  | 4.741%
2.3.10 | Weld Repair | 0.14 | 0.057143 | 0.14784 |  | 6.034%
2.3.11 | NDT After Weld Repair (VT,MT.PT,UT,R T) | 0.11 | 0.044898 | 0.11616 |  | 4.741%
2.3.12 | Final Visual and Dimensional | 0.07 | 0.028571 | 0.073922 |  | 3.017%
2.3.13 | PWHT (If Any) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.14 | Hardness Check | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.15 | NDT After PWHT | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.16 | Pneumatic Test (Pad Test) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.17 | Hydrostatic Test Water Quality | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.18 | Hydrostatic Test | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.19 | Draining & Drying | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.20 | Abrasive & Paint Material | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.3.21 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.02 | 0.0081633 | 0.021121 |  | 0.8621%
2.4 | Field Instruments (Transmitters/ Switch/ Gauge/ Analizer etc.) | 9.36 | 14.71 | 14.71 |  | 12%
2.4.1 | Visual Dimensional Inspection(Appearance) | 3.18 | 0.21618 | 4.9976 |  | 33.97%
2.4.2 | Calibration Check | 2.34 | 0.15908 | 3.6775 |  | 25%
2.4.3 | Tag & Model No & Specification Check | 1.59 | 0.10809 | 2.4988 |  | 16.99%
2.4.4 | Review Material, IP,ATEX Certificate | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.4.5 | Pressure & Performance Test | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.4.6 | Packing Inspection& Painting | 0.75 | 0.050986 | 1.1787 |  | 8.013%
2.5 | Cable, Wires & Tray | 1.56 | 1.96 | 1.96 |  | 2%
2.5.1 | Cable & Wires | 0.78 | 0.39796 | 0.98 |  | 50%
2.5.1.1 | Visual Inspection | 0.39 | 0.98 | 0.49
2.5.1.2 | Type Test Sertificate or Manufacturer Catalogue | 0.39 | 0.98 | 0.49
2.5.2 | Tray | 0.78 | 0.39796 | 0.98 |  | 50%
2.5.2.1 | Material Inspection | 0.39 | 0.98 | 0.49
2.5.2.2 | Visual & Dimensional Inspection | 0.39 | 0.98 | 0.49
2.6 | Junction Box | 2.35 | 2.94 | 2.94 |  | 3.013%
2.6.1 | Review IP, ATEX Certificate | 0.94 | 0.31973 | 1.176 |  | 40%
2.6.2 | Tag & Model No Check | 0.59 | 0.20068 | 0.73813 |  | 25.11%
2.6.3 | Review IP, ATEX certificate | 0.47 | 0.15986 | 0.588 |  | 20%
2.6.4 | Packing inspection and painting | 0.35 | 0.11905 | 0.43787 |  | 14.89%
2.7 | Local Panel (Outdoor-Hazardous Area) | 3.12 | 2.94 | 2.94 |  | 4%
2.7.1 | Visual Inspection & Dimenslonal Check | 1.09 | 0.37075 | 1.0271 |  | 34.94%
2.7.2 | Accessories Tag & Model No Check | 0.31 | 0.10544 | 0.29212 |  | 9.936%
2.7.3 | Construction | 1.4 | 0.47619 | 1.3192 |  | 44.87%
2.7.4 | Review IP, ATEX Certificate | 0.16 | 0.054422 | 0.15077 |  | 5.128%
2.7.5 | Packing Inspection & Painting | 0.16 | 0.054422 | 0.15077 |  | 5.128%
2.8 | Control Panel (Indoor-Safe Area) | 7.02 | 12.25 | 12.25 |  | 9%
2.8.1 | Visual Inspection/ QTY & Dimensional Check | 2.81 | 0.22939 | 4.9035 |  | 40.03%
2.8.2 | Tag & Model No Check | 1.76 | 0.14367 | 3.0712 |  | 25.07%
2.8.3 | Function & Performance test (Power & Start-up Check, I/O Check) | 1.4 | 0.11429 | 2.443 |  | 19.94%
2.8.4 | Main equipment & Accessories Certificate IP , ATEX, SIL Certificate Check) | 1.05 | 0.085714 | 1.8323 |  | 14.96%
2.9 | Valves | 3.09 | 7.84 | 7.84 |  | 3.962%
2.9.1 | Manual Valves | 1.62 | 0.20663 | 4.1103 |  | 52.43%
2.9.1.1 | Material Inspection | 0.81 | 3.92 | 2.0551 |  | 50%
2.9.1.2 | Visual and Dimensional Inspection | 0.65 | 3.1457 | 0.8246 |  | 40.12%
2.9.1.3 | Other Required Tests | 0.16 | 0.77432 | 0.081442 |  | 9.877%
2.9.2 | Inst.Valves (Shut Down, On/Off, Control & Safety Valves) | 1.47 | 0.1875 | 3.7297 |  | 47.57%
2.9.2.1 | Material Inspection | 0.52 | 2.7733 | 1.3194 |  | 35.37%
2.9.2.2 | Visual and Dimensional & QTY Inspection | 0.3 | 1.6 | 0.76117 |  | 20.41%
2.9.2.3 | Construction | 0.37 | 1.9733 | 0.93877 |  | 25.17%
2.9.2.4 | Accessory | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.5 | Pressure Test | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.6 | Calibration | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.9.2.7 | Performance test | 0.07 | 0.37333 | 0.17761 |  | 4.762%
2.1 | Strainers | 1.56 | 2.94 | 2.94 |  | 2%
2.10.1 | Material Inspection | 0.78 | 0.26531 | 1.47 |  | 50%
2.10.2 | Visual and Dimensional Inspection | 0.62 | 0.21088 | 1.1685 |  | 39.74%
2.10.3 | Hydro Test | 0.16 | 0.054422 | 0.30154 |  | 10.26%
2.11 | Piping Items (Pipe, Flange, Fitting, Gasket, Bolt & Nuts) | 2.35 | 3.92 | 3.92 |  | 3.013%
2.11.1 | Material Inspection | 0.82 | 0.20918 | 1.3678 | √ | 34.89%
2.11.2 | Visual and Dimensional Inspection | 0.35 | 0.089286 | 0.20372 | √ | 14.89%
2.11.3 | Weld Preparation and Fit-Up | 0.47 | 0.1199 | 0.040744 |  | 20%
2.11.4 | Welding | 0.47 | 0.1199 | 0.0081488 |  | 20%
2.11.5 | NDT( VT, MT, PT, UT, RT) | 0.12 | 0.030612 | 0.00041611 |  | 5.106%
2.11.6 | Hydrostatic Test | 0.12 | 0.030612 | 2.1248e-05 |  | 5.106%
2.12 | Pump | 1.56 | 2.94 | 2.94 |  | 2%
2.12.1 | Final Visual and Dimensional Inspection | 1.01 | 0.34354 | 1.9035 |  | 64.74%
2.12.2 | Performance test | 0.55 | 0.18707 | 1.0365 |  | 35.26%
2.13 | Ladder & Platform | 1.56 | 1.96 | 1.96 |  | 2%
2.13.1 | Visual and Dimensional Check After Welding | 1.56 | 0.79592 | 1.96
2.14 | Chemical Injection Package | 3.14 | 4.17 | 4.17 |  | 4.026%
2.14.1 | Raw Material for Tank | 1.09 | 0.26139 | 1.4475 | √ | 34.71%
2.14.2 | Final Inspection For Fabricated Tank | 0.16 | 0.038369 | 0.21248 | √ | 5.096%
2.14.3 | Piping & Structure Works | 1.25 | 0.29976 | 1.66 |  | 39.81%
2.14.4 | Performance test | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.5 | Packing Inspection | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.6 | IRN | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.14.7 | Final Book | 0.16 | 0.038369 | 0.21248 |  | 5.096%
2.15 | Reboiler Burner | 1.56 | 1.96 | 1.96 |  | 2%
2.15.1 | Final Visual and Dimensional Inspection | 1.01 | 0.51531 | 1.269 |  | 0.64744
2.15.2 | Burner Test | 0.55 | 0.28061 | 0.69103 |  | 0.35256
2.16 | Painting of Package Assembly (Piping, Structure) | 0.78 | 0.98 | 0.98 |  | 1%
2.16.1 | Abrasive & Paint Material | 0.39 | 0.39796 | 0.49 |  | 50%
2.16.2 | Blasting & Painting (Each Layer DFT, Adhesion) | 0.39 | 0.39796 | 0.49
2.17 | Pickling (For Stainless Steel Part) | 0.78 | 0.98 | 0.98 |  | 1%
2.17.1 | Pickling and Passivation | 0.78 | 0.79592 | 0.98
2.18 | Preservation | 0.78 | 0 | 0 |  | 1%
2.18.1 | N2 Purge /Silica | 0.78 | 0 | 0
3 | PACKING | 1 | 1 | 1
3.1 | Packing Inspection | 1 | 1 | 1
4 | IRN | 1 | 1 | 1
4.1 | Release Note | 1 | 1 | 1
5 | FINAL DATA BOOK | 3 | 3 | 3
5.1 | Final Document Preparation | 3 | 1 | 1
6 | IC | 1 | 1 | 1
6.1 | Inspection Certificate | 1 | 1 | 1
7 | SITE ACCEPTANCE TEST | 1 | 1 | 1
7.1 | SAT | 1 | 1 | 1

## WBS
WBS | Task Name | W.F. | WF
0 | BINAK OILFIELD DEVELOPMENT | 100 | 100
1 | DOCUMENTS | 5.9283 | 10
1.1 | Vendor's Document (According to VPIS) Document Subject According to client Approval | 5.9283 | 10 |  | 100%
1.1.1 | WORK BREAKDOWN STRUCTURE FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.2 | VENDOR PRINT INDEX & SCHEDULE (VPIS) FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.3 | TIME SCHEDULE FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.4 | FINAL VENDOR DATA BOOK INDEX FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.5 | SPARE PART LIST FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.6 | SUB-VENDOR LIST FOR GAS DEHYDRATION PACKAGE | 0.0669 | 0.1338 |  | 1.338% | 1.338%
1.1.7 | INSPECTION AND TEST PLAN FOR GAS DEHYDRATION PACKAGE | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.8 | QUALITY CONTROL PLAN (QCP) FOR GAS DEHYDRATION PACKAGE | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.9 | N2 PURGING PROCEDURE | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.10 | MARKING & PACKING PROCEDURE FOR GLYCOL CIRCULATION PUMPS | 0.033 | 0.1054 |  | 1.054% | 1.054%
1.1.11 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.12 | PICKLING AND PASSIVATION PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.13 | POSTWELD HEAT TREATMENT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.14 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | 0.033 | 0.1338 |  | 1.338% | 1.338%
1.1.15 | WPS & PQR FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.1164 | 0.2328 |  | 2.328% | 2.328%
1.1.16 | PMI PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.17 | NDT PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.18 | HYDROSTATIC TESTING PROCEDURE FOR GAS DEHYDRATION PACKAGE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.19 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.20 | WELD REPAIR PROCEDURE FOR GAS DEHYDRATION PACKAGE | 0.033 | 0.066 |  | 0.66% | 0.66%
1.1.21 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.098 | 0.196 |  | 1.96% | 1.96%
1.1.22 | BASIS OF PROCESS DESIGN FOR GAS DEHYDRATION PACKAGEFOR GAS DEHYDRATION PACKAGE | 0.098 | 0.196 |  | 1.96% | 1.96%
1.1.23 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | 0.098 | 0.196 |  | 1.96% | 1.96%
1.1.24 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.098 | 0.196 |  | 1.96% | 1.96%
1.1.25 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.26 | CONTROL PHILOSOPHY FOR GAS DEHYDRATION PACKAGE | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.27 | UCP LOGIC DESCRIPTION FOR GAS DEHYDRATION PACKAGE | 0.0382 | 0.0764 |  | 0.764% | 0.764%
1.1.28 | BMS LOGIC DESCRIPTION FOR DEHYDRATION PACKAGE | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.29 | PROCESS DATA SHEET FOR DEHYDRATION COLUMN | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.30 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.31 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.32 | PROCESS DATA SHEET FOR GLYCOL STRIPPING COLUMN | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.33 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.34 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.35 | PROCESS DATA SHEET FOR GLYCOL REFLUX CONDENSER | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.36 | PROCESS DATA SHEET FOR GLYCOL REBOILER | 0.0264 | 0.053 |  | 0.53% | 0.53%
1.1.37 | PROCESS DATA SHEET FOR GLYCOL SURGE DRUM | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.38 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.39 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.40 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.41 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.42 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | 0.0265 | 0.053 |  | 0.53% | 0.53%
1.1.43 | EQUIPMENT LIST FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.44 | PRESSURE SAFETY VALVE CALCULATION SHEETS FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.45 | ALARM & TRIP SET POINT LIST FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.46 | UTILITY CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.47 | CHEMICAL CONSUMPTION LIST FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.48 | HAZOP STUDY REPORT FOR GAS DEHYDRATION PACKAGE | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.49 | SIL STUDY REPORT (SAT Procedure)) | 0.108 | 0.053 |  | 0.53% | 0.53%
1.1.50 | Mechanical Calculation Book for C-100 | 0.014 | 0.028 |  | 0.28% | 0.28%
1.1.51 | General Arrangement for C-100 | 0.0108 | 0.0216 |  | 0.216% | 0.216%
1.1.52 | TEMPLATE DRAWING FOR GLYCOL CONTACTOR (C-100) | 0.0071 | 0.0142 |  | 0.142% | 0.142%
1.1.53 | DETAILS DRAWING FOR GLYCOL CONTACTOR (C-100) | 0.0066 | 0.0132 |  | 0.132% | 0.132%
1.1.54 | Name Plate Detail Drawing for C-100 | 0.0034 | 0.0068 |  | 0.068% | 0.068%
1.1.55 | Welding & NDT Map for C-100 | 0.0046 | 0.0092 |  | 0.092% | 0.092%
1.1.56 | Mechanical Calculation Book for C-200 | 0.0174 | 0.0348 |  | 0.348% | 0.348%
1.1.57 | General Arrangement for C-200 | 0.014 | 0.028 |  | 0.28% | 0.28%
1.1.58 | Details Drawing for C-200 | 0.0094 | 0.0188 |  | 0.188% | 0.188%
1.1.59 | Name Plate Detail Drawing for C-200 | 0.0043 | 0.0086 |  | 0.086% | 0.086%
1.1.60 | Welding & NDT Map for C-200 | 0.0046 | 0.0092 |  | 0.092% | 0.092%
1.1.61 | Mechanical Calculation Book for F-300 | 0.0185 | 0.037 |  | 0.37% | 0.37%
1.1.62 | General Arrangement Drawing for F-300 | 0.0168 | 0.0336 |  | 0.336% | 0.336%
1.1.63 | Detail drawing for F-300 | 0.014 | 0.028 |  | 0.28% | 0.28%
1.1.64 | Name Plate Detail Drawing for F-300 | 0.0046 | 0.0092 |  | 0.092% | 0.092%
1.1.65 | Welding & NDT for F-300 | 0.0046 | 0.0092 |  | 0.092% | 0.092%
1.1.66 | Mechanical Calculation Book for V-120 | 0.014 | 0.028 |  | 0.28% | 0.28%
1.1.67 | General Arrangement for V-120 | 0.0131 | 0.0262 |  | 0.262% | 0.262%
1.1.68 | Details Drawing for V-120 | 0.0108 | 0.0216 |  | 0.216% | 0.216%
1.1.69 | Name Plate Detail Drawing for V-120 | 0.0034 | 0.0068 |  | 0.068% | 0.068%
1.1.70 | Welding & NDT Map for V-120 | 0.0046 | 0.0092 |  | 0.092% | 0.092%
1.1.71 | Mechanical Calculation Book for (F-100 A/B) | 0.0234 | 0.0468 |  | 0.468% | 0.468%
1.1.72 | General Arrangement for (F-100 A/B) | 0.0211 | 0.0422 |  | 0.422% | 0.422%
1.1.73 | Details Drawing for (F-100 A/B) | 0.0174 | 0.027 |  | 0.27% | 0.27%
1.1.74 | Name Plate Detail Drawing for (F-100 A/B) | 0.0057 | 0.0028 |  | 0.028% | 0.028%
1.1.75 | Welding & NDT Map for (F-100 A/B) | 0.05 | 0.0162 |  | 0.162% | 0.162%
1.1.76 | Mechanical Calculation Book for F-200 | 0.0262 | 0.058 |  | 0.58% | 0.58%
1.1.77 | General Arrangement for F-200 | 0.0234 | 0.0516 |  | 0.516% | 0.516%
1.1.78 | Details Drawing for F-200 | 0.0185 | 0.0298 |  | 0.298% | 0.298%
1.1.79 | Name Plate Detail Drawing for F-200 | 0.0066 | 0.003 |  | 0.03% | 0.03%
1.1.80 | Welding & NDT Map for F-200 | 0.108 | 0.018 |  | 0.18% | 0.18%
1.1.81 | Thermal/Mechanical Calculation Book for E-100 | 0.0259 | 0.0568 |  | 0.568% | 0.568%
1.1.82 | General Arrangement for E-100 | 0.0231 | 0.0506 |  | 0.506% | 0.506%
1.1.83 | Details Drawing for E-100 | 0.0185 | 0.0296 |  | 0.296% | 0.296%
1.1.84 | Name Plate Detail Drawing for E-100 | 0.0066 | 0.003 |  | 0.03% | 0.03%
1.1.85 | Welding & NDT Map for E-100 | 0.05 | 0.0178 |  | 0.178% | 0.178%
1.1.86 | Thermal/Mechanical Calculation Book for E-200 | 0.0262 | 0.058 |  | 0.58% | 0.58%
1.1.87 | General Arrangement for E-200 | 0.0234 | 0.0516 |  | 0.516% | 0.516%
1.1.88 | Details Drawing for E-200 | 0.0185 | 0.0298 |  | 0.298% | 0.298%
1.1.89 | Name Plate Detail Drawing for E-200 | 0.0066 | 0.003 |  | 0.03% | 0.03%
1.1.90 | Welding & NDT Map for F-200 | 0.108 | 0.018 |  | 0.18% | 0.18%
1.1.91 | Thermal/Mechanical Calculation Book for E-300 | 0.0262 | 0.058 |  | 0.58% | 0.58%
1.1.92 | General Arrangement Drawing for E-300 | 0.0234 | 0.0516 |  | 0.516% | 0.516%
1.1.93 | Details Drawing for E-300 | 0.0185 | 0.0298 |  | 0.298% | 0.298%
1.1.94 | Name Plate Detail Drawing for E-300 | 0.0066 | 0.003 |  | 0.03% | 0.03%
1.1.95 | Welding & NDT Map for E-300 | 0.05 | 0.018 |  | 0.18% | 0.18%
1.1.96 | Thermal/Mechanical Calculation Book for R-100 | 0.0137 | 0.0174 |  | 0.174% | 0.174%
1.1.97 | General Arrangement for R-100 | 0.0117 | 0.0148 |  | 0.148% | 0.148%
1.1.98 | Details Drawing for R-100 | 0.0094 | 0.017 |  | 0.17% | 0.17%
1.1.99 | Name Plate Detail Drawing for R-100 | 0.0034 | 0.0018 |  | 0.018% | 0.018%
1.1.100 | Welding & NDT Map for R-100 | 0.0046 | 0.0102 |  | 0.102% | 0.102%
1.1.101 | Mechanical Calculation Book for V-130 | 0.014 | 0.019 |  | 0.19% | 0.19%
1.1.102 | General Arrangement Drawing for V-130 | 0.0131 | 0.0178 |  | 0.178% | 0.178%
1.1.103 | Details Drawing for V-130 | 0.0108 | 0.0184 |  | 0.184% | 0.184%
1.1.104 | Name Plate Detail Drawing for V-130 | 0.0034 | 0.0018 |  | 0.018% | 0.018%
1.1.105 | Welding & NDT Map for V-130 | 0.05 | 0.011 |  | 0.11% | 0.11%
1.1.106 | BURNER DATA SHEET FOR GLYCOL REBOILER | 0.0171 | 0.0342 |  | 0.342% | 0.342%
1.1.107 | BURNER DRAWING FOR GLYCOL REBOILER | 0.0171 | 0.0342 |  | 0.342% | 0.342%
1.1.108 | LUBRICATION LIST FOR GAS DEHYDRATION PACKAGE | 0.0171 | 0.0342 |  | 0.342% | 0.342%
1.1.109 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.0171 | 0.0342 |  | 0.342% | 0.342%
1.1.110 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | 0.0171 | 0.0342 |  | 0.342% | 0.342%
1.1.111 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | 0.0168 | 0.0336 |  | 0.336% | 0.336%
1.1.112 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | 0.0311 | 0.0622 |  | 0.622% | 0.622%
1.1.113 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | 0.0311 | 0.0622 |  | 0.622% | 0.622%
1.1.114 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | 0.0311 | 0.0622 |  | 0.622% | 0.622%
1.1.115 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (30%) FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.116 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (60%) FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.117 | 3D MODEL NAVIS FILE AND PDMS DATA BASE (90%) FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.118 | PACKAGE PLOT PLAN FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.119 | PIPING GENERAL ARRANGEMENT DRAWING FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.120 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.121 | LINE LIST FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.122 | TIE-IN-LIST FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.123 | SUPPORT LIST FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.124 | STRESS ANALYSIS REPORT FOR GAS DEHYDRATION PACKAGE | 0.0373 | 0.0746 |  | 0.746% | 0.746%
1.1.125 | Electrical single line diagram | 0.0445 | 0.089 |  | 0.89% | 0.89%
1.1.126 | ELECTRICAL PANEL LAYOUT AND WIRING DIAGRAM | 0.0445 | 0.089 |  | 0.89% | 0.89%
1.1.127 | Power and control cable list | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.128 | Earthing detail layout | 0.0308 | 0.0616 |  | 0.616% | 0.616%
1.1.129 | ELECTRICAL EQUIPMENT LAYOUT | 0.0308 | 0.0616 |  | 0.616% | 0.616%
1.1.130 | Electrical load list | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.131 | ELECTRICAL SIGNAL LIST | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.132 | Electrical Cable Route | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.133 | Electrical motor data sheets , CURVES, DRAWINGS AND CERTIFICATES | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.134 | CABLE DATASHEETS | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.135 | ELECTRICAL PANEL DATASHEETS | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.136 | LOCAL CONTROL STATION (LCS) DATASHEETS | 0.0442 | 0.0884 |  | 0.884% | 0.884%
1.1.137 | Local control station (LCS) panel layout and wiring diagram | 0.0399 | 0.0798 |  | 0.798% | 0.798%
1.1.138 | Instrument list | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.139 | Input/Output signal list | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.140 | CONTROL SYSTEM CONFIGURATION BLOCK DIAGRAM | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.141 | ESD/BMS SYSTEM CONFIGURATION BLOCK DIAGRAM | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.142 | Instrument junction box layout and wiring termination diagram | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.143 | Burner operation panel layout & wiring diagram with connections & dimensions | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.144 | Instrument D.S. for control valves | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.145 | Instrument cable list | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.146 | Instrument D.S. for On/Off valves | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.147 | Instrument D.S. for H2O analyzer | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.148 | Instrument D.S. for temperature gauge | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.149 | Instrument D.S. for temperature transmitters | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.150 | Instrument D.S. for pressure gauges and differential gauges | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.151 | Instrument D.S. for pressure transmitters and differentia pressure transmitters | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.152 | INSTRUMENT D.S. FOR SAFETY VALVES | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.153 | Instrument D.S. for pressure regulator valves | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.154 | Instrument D.S. for flow elements | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.155 | Instrument D.S. for level gauges | 0.0285 | 0.0572 |  | 0.572% | 0.572%
1.1.156 | Instrument D.S. for level transmitters | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.157 | Hook up drawing | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.158 | ESD LEVEL HIERARCHY | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.159 | Instrument location layout | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.160 | INSTRUMENT EARTH DISTRIBUTION DIAGRAM | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.161 | INSTRUMENT CABLE ROUTE/ MAIN TUBING LAYOUT DRAWING | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.162 | Flame scanner data sheet | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.163 | CONTROL PANEL LAYOUT AND ARRANGEMENT | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.164 | ESD/BMS PANEL LAYOUT AND ARRANGEMENT | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.165 | CONTROL SYSTEM WIRING DIAGRAM AND CONNECTIONS | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.166 | ESD/BMS SYSTEM WIRING DIAGRAM AND CONNECTIONS | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.167 | UCP and BMS system power consumption list | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.168 | CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.169 | Modbus IO list (Modbus mapping list) | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.170 | FAT PROCEDURE FOR CONTROL SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.171 | FAT PROCEDURE FOR ESD/BMS SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.172 | SAT PROCEDURE FOR CONTROL SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.173 | SAT PROCEDURE FOR ESD/BMS SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.174 | ITP FOR CONTROL SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.175 | ITP FOR ESD/BMS SYSTEM | 0.0282 | 0.0564 |  | 0.564% | 0.564%
1.1.176 | CONTROL SYSTEM LOGIC DIAGRAM | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.177 | ESD/BMS SYSTEM LOGIC DIAGRAM | 0.0285 | 0.057 |  | 0.57% | 0.57%
1.1.178 | PRINT OUT OF HMI FOR BMS and UCP | 0.0285 | 0.057 |  | 0.57% | 0.57%
2 | Manufacturing | 78 | 83 | [8 empty] | 45.2075
2.1 | Vessel | 30.39 | 37 |  | 38.96% | 42.5 | 42.5% |  |  | 44.58% | 42.95% | 37.8
2.1.1 | Raw Material Of Pressure Parts | 7 | 10.915 |  | 29.5% | 8.965 | 8.965% |  |  |  |  | 11.151
2.1.1.1 | PLATE |  | 6.549 | √ | 60% | 5.379 | 5.379% |  |  |  |  | 6.6906
2.1.1.1.1 | Inquiry-plate |  | 0.6549 |  |  |  |  | 10% |  |  |  | 0.66906
2.1.1.1.2 | PO-plate |  | 1.3098 |  |  |  |  | 20% |  |  |  | 1.3381
2.1.1.1.3 | IRN-plate |  | 2.6196 |  |  |  |  | 40% |  |  |  | 2.6762
2.1.1.1.4 | Delivery-plate |  | 1.9647 |  |  |  |  | 30% |  |  |  | 2.0072
2.1.1.2 | FLANG |  | 3.2745 | √ | 30% | 2.6895 | 2.69% |  |  |  |  | 3.3453
2.1.1.2.1 | Inquiry-Flange |  | 0.32745 |  |  |  |  | 10% |  |  |  | 0.33453
2.1.1.2.2 | PO-Flange |  | 0.6549 |  |  |  |  | 20% |  |  |  | 0.66906
2.1.1.2.3 | IRN-Flange |  | 1.3098 |  |  |  |  | 40% |  |  |  | 1.3381
2.1.1.2.4 | Delivery-Flange |  | 0.98235 |  |  |  |  | 30% |  |  |  | 1.0036
2.1.1.3 | PIPE |  | 1.0915 | √ | 10% | 0.8965 | 0.8965% |  |  |  |  | 1.1151
2.1.1.3.1 | Inquiry-Pipe |  | 0.10915 |  |  |  |  | 10% |  |  |  | 0.11151
2.1.1.3.2 | PO-Pipe |  | 0.2183 |  |  |  |  | 20% |  |  |  | 0.22302
2.1.1.3.3 | IRN-Pipe |  | 0.4366 |  |  |  |  | 40% |  |  |  | 0.44604
2.1.1.3.4 | Delivery-Pipe |  | 0.32745 |  |  |  |  | 30% |  |  |  | 0.33453
2.1.2 | Raw Material Of Non-Pressure Parts | 2.15 | 3.3559 |  | 9.07% | 2.15 | 2.15% |  |  |  |  | 3.4285
2.1.2.1 | PLATE |  | 3.0203 | √ | 90% | 1.935 | 1.935% |  |  |  |  | 3.0856
2.1.2.1.1 | Inquiry-plate |  | 0.30203 |  |  |  |  | 10% |  |  |  | 0.30856
2.1.2.1.2 | PO-plate |  | 0.60406 |  |  |  |  | 20% |  |  |  | 0.61712
2.1.2.1.3 | IRN-plate |  | 1.2081 |  |  |  |  | 40% |  |  |  | 1.2342
2.1.2.1.4 | Delivery-plate |  | 0.90609 |  |  |  |  | 30% |  |  |  | 0.92568
2.1.2.2 | PROFILE |  | 0.33559 | √ | 10% | 0.215 | 0.215% |  |  |  |  | 0.34285
2.1.2.2.1 | Inquiry-Profile |  | 0.033559 |  |  |  |  | 10% |  |  |  | 0.034285
2.1.2.2.2 | PO-Profile |  | 0.067118 |  |  |  |  | 20% |  |  |  | 0.068569
2.1.2.2.3 | IRN-Profile |  | 0.13424 |  |  |  |  | 40% |  |  |  | 0.13714
2.1.2.2.4 | Delivery-Profile |  | 0.10068 |  |  |  |  | 30% |  |  |  | 0.10285
2.1.3 | Internals | 0.61 | 0.74268 |  | 2.007% | 0.61 | 0.61% |  |  |  |  | 0.75874
2.1.3.1 | Inquiry-Internal |  | 0.074268 |  |  |  |  | 10% |  |  |  | 0.075874
2.1.3.2 | PO-Internal |  | 0.14854 |  |  |  |  | 20% |  |  |  | 0.15175
2.1.3.3 | IRN-Internal |  | 0.29707 |  |  |  |  | 40% |  |  |  | 0.30349
2.1.3.4 | Delivery-Internal |  | 0.2228 |  |  |  |  | 30% |  |  |  | 0.22762
2.1.4 | VT & DT For Raw Material | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.5 | Consumable Material (Electrode) | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.6 | Cutting & Marking | 1.52 | 1.8506 | √ | 5.002% | 1.52 | 1.52% |  |  |  |  | 1.8906
2.1.7 | Rolling & Forming | 2.43 | 2.9585 | √ | 7.996% | 2.43 | 2.43% |  |  |  |  | 3.0225
2.1.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) | 2.13 | 2.5933 | √ | 7.009% | 2.13 | 2.13% |  |  |  |  | 2.6494
2.1.9 | Welding | 3.95 | 4.8091 | √ | 13% | 3.95 | 3.95% |  |  |  |  | 4.9131
2.1.10 | Ferrite Check For Welding Gladded Parts | 2.43 | 2.9585 | √ | 7.996% | 2.43 | 2.43% |  |  |  |  | 3.0225
2.1.11 | NDT (VT,MT.PT,UT,RT) | 1.22 | 0.74 |  | 2% | 0.6078 | 0.6078% |  |  |  |  | 0.756
2.1.12 | Weld Repair | 1.52 | 0.37 |  | 0.01 | 0.3039 | 0.003039 |  |  |  |  | 0.378
2.1.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 1.22 | 0.7437 |  | 2.01% | 1.22 | 1.22% |  |  |  |  | 0.75978
2.1.14 | Final Visual and Dimensional | 0.91 | 1.1079 |  | 2.994% | 0.91 | 0.91% |  |  |  |  | 1.1319
2.1.15 | PWHT (If Any) | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.16 | Hardness Check | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.17 | NDT After PWHT | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.18 | Pneumatic Test (Pad Test) | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.19 | Hydrostatic Test Water Quality | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.20 | Hydrostatic Test | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.21 | Draining & Drying | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.22 | Abrasive & Paint Material | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.1.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) | 0.3 | 0.36525 |  | 0.9872% | 0.3 | 0.3% |  |  |  |  | 0.37315
2.2 | Heat Exchangers | 4.72 | 7.5 |  | 6.051% | 10 | 10% |  |  | 9.036% | 9.091% | 8
2.2.1 | Raw Material for Pressure parts | 1.12 | 2.4547 |  | 32.73% | 1.385 | 1.385% |  |  |  |  | 2.6184
2.2.1.1 | PLATE |  | 1.4728 | √ | 60% | 0.83097 | 0.831% |  |  |  |  | 1.571
2.2.1.1.1 | Inquiry-plate |  | 0.14728 |  |  |  |  | 10% |  |  |  | 0.1571
2.2.1.1.2 | PO-plate |  | 0.29457 |  |  |  |  | 20% |  |  |  | 0.31421
2.2.1.1.3 | IRN-plate |  | 0.58914 |  |  |  |  | 40% |  |  |  | 0.62842
2.2.1.1.4 | Delivery-plate |  | 0.44185 |  |  |  |  | 30% |  |  |  | 0.47131
2.2.1.2 | FLANG |  | 0.73642 | √ | 30% | 0.41549 | 0.4155% |  |  |  |  | 0.78552
2.2.1.2.1 | Inquiry-Flange |  | 0.073642 |  |  |  |  | 10% |  |  |  | 0.078552
2.2.1.2.2 | PO-Flange |  | 0.14728 |  |  |  |  | 20% |  |  |  | 0.1571
2.2.1.2.3 | IRN-Flange |  | 0.29457 |  |  |  |  | 40% |  |  |  | 0.31421
2.2.1.2.4 | Delivery-Flange |  | 0.22093 |  |  |  |  | 30% |  |  |  | 0.23566
2.2.1.3 | PIPE |  | 0.24547 | √ | 10% | 0.1385 | 0.1385% |  |  |  |  | 0.26184
2.2.1.3.1 | Inquiry-Pipe |  | 0.024547 |  |  |  |  | 10% |  |  |  | 0.026184
2.2.1.3.2 | PO-Pipe |  | 0.049095 |  |  |  |  | 20% |  |  |  | 0.052368
2.2.1.3.3 | IRN-Pipe |  | 0.09819 |  |  |  |  | 40% |  |  |  | 0.10474
2.2.1.3.4 | Delivery-Pipe |  | 0.073642 |  |  |  |  | 30% |  |  |  | 0.078552
2.2.2 | Raw Material for Non-Pressure parts | 0.37 | 0.58792 |  | 7.839% | 0.3653 | 0.3653% |  |  |  |  | 0.62712
2.2.2.1 | PLATE |  | 0.52913 | √ | 90% | 0.32877 | 0.3288% |  |  |  |  | 0.56441
2.2.2.1.1 | Inquiry-plate |  | 0.052913 |  |  |  |  | 10% |  |  |  | 0.056441
2.2.2.1.2 | PO-plate |  | 0.10583 |  |  |  |  | 20% |  |  |  | 0.11288
2.2.2.1.3 | IRN-plate |  | 0.21165 |  |  |  |  | 40% |  |  |  | 0.22576
2.2.2.1.4 | Delivery-plate |  | 0.15874 |  |  |  |  | 30% |  |  |  | 0.16932
2.2.2.2 | PROFILE |  | 0.058792 | √ | 10% | 0.03653 | 0.03653% |  |  |  |  | 0.062712
2.2.2.2.1 | Inquiry-Profile |  | 0.0058792 |  |  |  |  | 10% |  |  |  | 0.0062712
2.2.2.2.2 | PO-Profile |  | 0.011758 |  |  |  |  | 20% |  |  |  | 0.012542
2.2.2.2.3 | IRN-Profile |  | 0.023517 |  |  |  |  | 40% |  |  |  | 0.025085
2.2.2.2.4 | Delivery-Profile |  | 0.017638 |  |  |  |  | 30% |  |  |  | 0.018814
2.2.3 | VT & DT For Raw Material | 0.05 | 0.079449 | √ | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.4 | Consumable Material (Electrode) | 0.05 | 0.079449 | √ | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.5 | Cutting & Marking | 0.23 | 0.36547 | √ | 4.873% | 0.22708 | 0.2271% |  |  |  |  | 0.38983
2.2.6 | Rolling & Forming | 0.37 | 0.58792 | √ | 7.839% | 0.3653 | 0.3653% |  |  |  |  | 0.62712
2.2.7 | Tube to Tube Sheet Joint {Expansion) | 0.35 | 0.55614 |  | 7.415% | 0.34555 | 0.3456% |  |  |  |  | 0.59322
2.2.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, … ) | 0.61 | 0.819 |  | 10.92% | 0.60225 | 0.6022% |  |  |  |  | 0.8736
2.2.9 | Welding | 0.37 | 0.58792 |  | 7.839% | 0.3653 | 0.3653% |  |  |  |  | 0.62712
2.2.10 | NDT (VT,MT.PT,UT,RT) | 0.19 | 0.15225 |  | 2.03% | 0.094598 | 0.0946% |  |  |  |  | 0.1624
2.2.11 | Weld Repair | 0.23 | 0.21525 |  | 2.87% | 0.13374 | 0.1337% |  |  |  |  | 0.2296
2.2.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) | 0.19 | 0.07725 |  | 1.03% | 0.094598 | 0.0946% |  |  |  |  | 0.0824
2.2.13 | Final Visual and Dimensional | 0.14 | 0.22246 |  | 2.966% | 0.13822 | 0.1382% |  |  |  |  | 0.23729
2.2.14 | PWHT (If Any) | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.15 | Hardness Check | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.16 | NDT After PWHT | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.17 | Pneumatic Test (Pad Test) | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.18 | Hydrostatic Test Water Quality | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.19 | Hydrostatic Test | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.20 | Draining & Drying | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.21 | Abrasive & Paint Material | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.2.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.05 | 0.079449 |  | 1.059% | 0.049364 | 0.04936% |  |  |  |  | 0.084746
2.3 | Re-boiler | 2.32 | 4 |  | 2.974% | 5 | 5% |  |  | 4.819% | 5% | 4.4
2.3.1 | Raw Material for Pressure parts | 0.59 | 1.452 |  | 36.3% | 0.74235 | 0.7424% |  |  |  |  | 1.5972
2.3.1.1 | PLATE |  | 0.8712 | √ | 60% | 0.44541 | 0.4454% |  |  |  |  | 0.95832
2.3.1.1.1 | Inquiry-plate |  | 0.08712 |  |  |  |  | 10% |  |  |  | 0.095832
2.3.1.1.2 | PO-plate |  | 0.017424 |  |  |  |  | 20% |  |  |  | 0.019166
2.3.1.1.3 | IRN-plate |  | 0.0069696 |  |  |  |  | 40% |  |  |  | 0.0076666
2.3.1.1.4 | Delivery-plate |  | 0.0020909 |  |  |  |  | 30% |  |  |  | 0.0023
2.3.1.2 | FLANG |  | 0.4356 | √ | 30% | 0.22271 | 0.2227% |  |  |  |  | 0.47916
2.3.1.2.1 | Inquiry-Flange |  | 0.04356 |  |  |  |  | 10% |  |  |  | 0.047916
2.3.1.2.2 | PO-Flange |  | 0.08712 |  |  |  |  | 20% |  |  |  | 0.095832
2.3.1.2.3 | IRN-Flange |  | 0.17424 |  |  |  |  | 40% |  |  |  | 0.19166
2.3.1.2.4 | Delivery-Flange |  | 0.13068 |  |  |  |  | 30% |  |  |  | 0.14375
2.3.1.3 | PIPE |  | 0.1452 | √ | 10% | 0.074235 | 0.07424% |  |  |  |  | 0.15972
2.3.1.3.1 | Inquiry-Pipe |  | 0.01452 |  |  |  |  | 10% |  |  |  | 0.015972
2.3.1.3.2 | PO-Pipe |  | 0.02904 |  |  |  |  | 20% |  |  |  | 0.031944
2.3.1.3.3 | IRN-Pipe |  | 0.05808 |  |  |  |  | 40% |  |  |  | 0.063888
2.3.1.3.4 | Delivery-Pipe |  | 0.04356 |  |  |  |  | 30% |  |  |  | 0.047916
2.3.2 | Raw Material for Non-Pressure parts | 0.21 | 0.36207 |  | 9.052% | 0.22177 | 0.2218% |  |  |  |  | 0.39828
2.3.2.1 | PLATE |  | 0.32586 | √ | 90% | 0.19959 | 0.1996% |  |  |  |  | 0.35845
2.3.2.1.1 | Inquiry-plate |  | 0.032586 |  |  |  |  | 10% |  |  |  | 0.035845
2.3.2.1.2 | PO-plate |  | 0.065172 |  |  |  |  | 20% |  |  |  | 0.07169
2.3.2.1.3 | IRN-plate |  | 0.13034 |  |  |  |  | 40% |  |  |  | 0.14338
2.3.2.1.4 | Delivery-plate |  | 0.097759 |  |  |  |  | 30% |  |  |  | 0.10753
2.3.2.2 | PROFILE |  | 0.036207 | √ | 10% | 0.022177 | 0.02218% |  |  |  |  | 0.039828
2.3.2.2.1 | Inquiry-Profile |  | 0.0036207 |  |  |  |  | 10% |  |  |  | 0.0039828
2.3.2.2.2 | PO-Profile |  | 0.0072414 |  |  |  |  | 20% |  |  |  | 0.0079655
2.3.2.2.3 | IRN-Profile |  | 0.014483 |  |  |  |  | 40% |  |  |  | 0.015931
2.3.2.2.4 | Delivery-Profile |  | 0.010862 |  |  |  |  | 30% |  |  |  | 0.011948
2.3.4 | Consumable Material (Electrode) | 0.02 | 0.034483 | √ | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.5 | Cutting & Marking | 0.12 | 0.2069 | √ | 5.172% | 0.12672 | 0.1267% |  |  |  |  | 0.22759
2.3.6 | Rolling & Forming | 0.21 | 0.36207 | √ | 9.052% | 0.22177 | 0.2218% |  |  |  |  | 0.39828
2.3.7 | Weld Preparation and Fit-Up (Shell,Nozzle, ... ) | 0.33 | 0.56897 | √ | 14.22% | 0.34849 | 0.3485% |  |  |  |  | 0.62586
2.3.8 | Welding | 0.21 | 0.36207 | √ | 9.052% | 0.22177 | 0.2218% |  |  |  |  | 0.39828
2.3.9 | NDT (VT,MT.PT,UT,RT) | 0.11 | 0.0696 |  | 1.74% | 0.11616 | 0.1162% |  |  |  |  | 0.07656
2.3.10 | Weld Repair | 0.14 | 0.0812 |  | 2.03% | 0.049735 | 0.04974% |  |  |  |  | 0.08932
2.3.11 | NDT After Weld Repair (VT,MT.PT,UT,R T) | 0.11 | 0.0696 |  | 1.74% | 0.11616 | 0.1162% |  |  |  |  | 0.07656
2.3.12 | Final Visual and Dimensional | 0.07 | 0.12069 |  | 3.017% | 0.073922 | 0.07392% |  |  |  |  | 0.13276
2.3.13 | PWHT (If Any) | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.14 | Hardness Check | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.15 | NDT After PWHT | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.16 | Pneumatic Test (Pad Test) | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.17 | Hydrostatic Test Water Quality | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.18 | Hydrostatic Test | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.19 | Draining & Drying | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.20 | Abrasive & Paint Material | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.3.21 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) | 0.02 | 0.034483 |  | 0.8621% | 0.021121 | 0.02112% |  |  |  |  | 0.037931
2.4 | Field Instruments (Transmitters/ Switch/ Gauge/ Analizer etc.) | 9.36 | 10 |  | 12% | 7 | 7% | 4 | 6 | 12.05% | 9.091% | 8
2.4.1 | Inquiry-Transmitters/ Switch/ Gauge/ Analizer etc. |  | 0.4 |  |  |  |  | 10% |  |  |  | 0.32
2.4.2 | PO-Transmitters/ Switch/ Gauge/ Analizer etc. |  | 0.8 |  |  |  |  | 20% |  |  |  | 0.64
2.4.3 | IRN-Transmitters/ Switch/ Gauge/ Analizer etc. |  | 1.6 |  |  |  |  | 40% |  |  |  | 1.28
2.4.4 | Delivery-Transmitters/ Switch/ Gauge/ Analizer etc. |  | 1.2 |  |  |  |  | 30% |  |  |  | 0.96
2.4.5 | Visual Dimensional Inspection(Appearance) | 3.18 | 2.0385 |  | 33.97% | 4.9976 | 4.998% |  |  |  |  | 1.6308
2.4.6 | Calibration Check | 2.34 | 1.5 |  | 25% | 3.6775 | 3.678% |  |  |  |  | 1.2
2.4.7 | Tag & Model No & Specification Check | 1.59 | 1.0192 |  | 16.99% | 2.4988 | 2.499% |  |  |  |  | 0.81538
2.4.8 | Review Material, IP,ATEX Certificate | 0.75 | 0.48077 |  | 8.013% | 1.1787 | 1.179% |  |  |  |  | 0.38462
2.4.9 | Pressure & Performance Test | 0.75 | 0.48077 |  | 8.013% | 1.1787 | 1.179% |  |  |  |  | 0.38462
2.4.10 | Packing Inspection& Painting | 0.75 | 0.48077 |  | 8.013% | 1.1787 | 1.179% |  |  |  |  | 0.38462
2.5 | Cable, Wires & Tray | 1.56 | 1.95 |  | 2% | 1.96 | 1.96% |  |  | 2.349% | 1.96% | 1.7248
2.5.1 | Cable & Wires | 0.78 | 0.975 |  | 50% | 0.98 | 0.98% | 0.39 | 0.585 |  |  | 0.8624
2.5.1.1 | Inquiry-Cable & Wires |  | 0.039 |  |  |  |  | 10% |  |  |  | 0.034496
2.5.1.2 | PO-Cable & Wires |  | 0.078 |  |  |  |  | 20% |  |  |  | 0.068992
2.5.1.3 | IRN-Cable & Wires |  | 0.156 |  |  |  |  | 40% |  |  |  | 0.13798
2.5.1.4 | Delivery-Cable & Wires |  | 0.117 |  |  |  |  | 30% |  |  |  | 0.10349
2.5.1.5 | Visual Inspection | 0.39 | 0.2925 |  |  | 0.49 | 0.49% |  |  |  |  | 0.25872
2.5.1.6 | Type Test Sertificate or Manufacturer Catalogue | 0.39 | 0.2925 |  |  | 0.49 | 0.49% |  |  |  |  | 0.25872
2.5.2 | Tray | 0.78 | 0.975 |  | 50% | 0.98 | 0.98% | 0.39 | 0.585 |  |  | 0.8624
2.5.2.1 | Inquiry-Tray |  | 0.039 |  |  |  |  | 10% |  |  |  | 0.034496
2.5.2.2 | PO-Tray |  | 0.078 |  |  |  |  | 20% |  |  |  | 0.068992
2.5.2.3 | IRN-Tray |  | 0.156 |  |  |  |  | 40% |  |  |  | 0.13798
2.5.2.4 | Delivery-Tray |  | 0.117 |  |  |  |  | 30% |  |  |  | 0.10349
2.5.2.5 | Material Inspection | 0.39 | 0.2925 |  |  | 0.49 | 0.49% |  |  |  |  | 0.25872
2.5.2.6 | Visual & Dimensional Inspection | 0.39 | 0.2925 |  |  | 0.49 | 0.49% |  |  |  |  | 0.25872
2.6 | Junction Box | 2.35 | 2 |  | 3.013% | 2.94 | 2.94% | 0.8 | 1.2 | 2.41% | 2.273% | 2
2.6.1 | Inquiry-Junction Box |  | 0.08 |  |  |  |  | 10% |  |  |  | 0.08
2.6.2 | PO- Junction Box |  | 0.16 |  |  |  |  | 20% |  |  |  | 0.16
2.6.3 | IRN-Junction Box |  | 0.32 |  |  |  |  | 40% |  |  |  | 0.32
2.6.4 | Delivery- Junction Box |  | 0.24 |  |  |  |  | 30% |  |  |  | 0.24
2.6.5 | Review IP, ATEX Certificate | 0.94 | 0.48 |  | 40% | 1.176 | 1.176% |  |  |  |  | 0.48
2.6.6 | Tag & Model No Check | 0.59 | 0.30128 |  | 25.11% | 0.73813 | 0.7381% |  |  |  |  | 0.30128
2.6.7 | Review IP, ATEX certificate | 0.47 | 0.24 |  | 20% | 0.588 | 0.588% |  |  |  |  | 0.24
2.6.8 | Packing inspection and painting | 0.35 | 0.17872 |  | 14.89% | 0.43787 | 0.4379% |  |  |  |  | 0.17872
2.7 | Local Panel (Outdoor-Hazardous Area) | 3.12 | 2 |  | 4% | 2.94 | 2.94% | 0.8 | 1.2 | 2.41% | 2.273% | 2
2.7.1 | Inquiry-Local Panel |  | 0.08 |  |  |  |  | 10% |  |  |  | 0.08
2.7.2 | PO- Local Panel |  | 0.16 |  |  |  |  | 20% |  |  |  | 0.16
2.7.3 | IRN-Local Panel |  | 0.32 |  |  |  |  | 40% |  |  |  | 0.32
2.7.4 | Delivery- Local Panel |  | 0.24 |  |  |  |  | 30% |  |  |  | 0.24
2.7.5 | Visual Inspection & Dimenslonal Check | 1.09 | 0.41923 |  | 34.94% | 1.0271 | 1.027% |  |  |  |  | 0.41923
2.7.6 | Accessories Tag & Model No Check | 0.31 | 0.11923 |  | 9.936% | 0.29212 | 0.2921% |  |  |  |  | 0.11923
2.7.7 | Construction | 1.4 | 0.53846 |  | 44.87% | 1.3192 | 1.319% |  |  |  |  | 0.53846
2.7.8 | Review IP, ATEX Certificate | 0.16 | 0.061538 |  | 5.128% | 0.15077 | 0.1508% |  |  |  |  | 0.061538
2.7.9 | Packing Inspection & Painting | 0.16 | 0.061538 |  | 5.128% | 0.15077 | 0.1508% |  |  |  |  | 0.061538
2.8 | Control Panel (Indoor-Safe Area) | 7.02 | 6 |  | 9% | 8 | 8% |  |  | 7.229% | 8% | 7.04
2.8.1 | ESD/BMS |  | 3 |  |  |  |  | 1.2 | 1.8 |  |  | 3.52
2.8.1.1 | Inquiry-ESD/BMS |  | 0.12 |  |  |  |  | 10% |  |  |  | 0.1408
2.8.1.2 | PO-ESD/BMS |  | 0.24 |  |  |  |  | 20% |  |  |  | 0.2816
2.8.1.3 | IRN-ESD/BMS |  | 0.48 |  |  |  |  | 40% |  |  |  | 0.5632
2.8.1.4 | Delivery-ESD/BMS |  | 0.36 |  |  |  |  | 30% |  |  |  | 0.4224
2.8.1.5 | Visual Inspection/ QTY & Dimensional Check | 2.81 | 0.72051 |  | 40.03% | 4.9035 | 4.903% |  |  |  |  | 0.8454
2.8.1.6 | Tag & Model No Check | 1.76 | 0.45128 |  | 25.07% | 3.0712 | 3.071% |  |  |  |  | 0.5295
2.8.1.7 | Function & Performance test (Power & Start-up Check, I/O Check) | 1.4 | 0.35897 |  | 19.94% | 2.443 | 2.443% |  |  |  |  | 0.4212
2.8.1.8 | Main equipment & Accessories Certificate IP , ATEX, SIL Certificate Check) | 1.05 | 0.26923 |  | 14.96% | 1.8323 | 1.832% |  |  |  |  | 0.3159
2.8.2 | Control |  | 3 |  |  |  |  | 1.2 | 1.8 |  |  | 3.52
2.8.2.1 | Inquiry-Control |  | 0.12 |  |  |  |  | 10% |  |  |  | 0.1408
2.8.2.2 | PO-Control |  | 0.24 |  |  |  |  | 20% |  |  |  | 0.2816
2.8.2.3 | IRN-Control |  | 0.48 |  |  |  |  | 40% |  |  |  | 0.5632
2.8.2.4 | Delivery-Control |  | 0.36 |  |  |  |  | 30% |  |  |  | 0.4224
2.8.2.5 | Visual Inspection/ QTY & Dimensional Check | 2.81 | 0.72051 |  | 40.03% | [6 empty] | 0.8454
2.8.2.6 | Tag & Model No Check | 1.76 | 0.45128 |  | 25.07% | [6 empty] | 0.5295
2.8.2.7 | Function & Performance test (Power & Start-up Check, I/O Check) | 1.4 | 0.35897 |  | 19.94% | [6 empty] | 0.4212
2.8.2.8 | Main equipment & Accessories Certificate IP , ATEX, SIL Certificate Check) | 1.05 | 0.26923 |  | 14.96% | [6 empty] | 0.3159
2.9 | Valves | 3.09 | 3 |  | 3.962% | 4 | 4% |  |  | 3.614% | 4% | 3.52
2.9.1 | Manual Valves | #REF! | 1.5 | [8 empty] | 1.76
2.9.1.1 | Manual Valves | 0.81 | 1.5 |  | 50% |  |  | 0.6 | 0.9 |  |  | 0.88
2.9.1.1.1 | Inquiry-Psv |  | 0.06 |  |  |  |  | 10% |  |  |  | 0.0352
2.9.1.1.2 | PO- Psv |  | 0.12 |  |  |  |  | 20% |  |  |  | 0.0704
2.9.1.1.3 | IRN- Psv |  | 0.24 |  |  |  |  | 40% |  |  |  | 0.1408
2.9.1.1.4 | Delivery- Psv |  | 0.18 |  |  |  |  | 30% |  |  |  | 0.1056
2.9.1.1.5 | Material Inspection | 0.405 | 0.45 |  | 50% | [6 empty] | 0.264
2.9.1.1.6 | Visual and Dimensional Inspection | 0.325 | 0.36111 |  | 40.12% | [6 empty] | 0.21185
2.9.1.1.7 | Other Required Tests | 0.08 | 0.088889 |  | 9.877% | [6 empty] | 0.052148
2.9.2 | Inst.Valves (Shut Down, On/Off, Control & Safety Valves) | 1.545 | 1.5 | [8 empty] | 1.76
2.9.2.1 | PSV | 0.81 | 0.49995 |  | 33.33% | 4.1103 | 4.11% | 0.19998 | 0.29997 |  |  | 0.58661
2.9.2.1.1 | Inquiry-Psv |  | 0.019998 |  |  |  |  | 10% |  |  |  | 0.023464
2.9.2.1.2 | PO- Psv |  | 0.039996 |  |  |  |  | 20% |  |  |  | 0.046929
2.9.2.1.3 | IRN- Psv |  | 0.079992 |  |  |  |  | 40% |  |  |  | 0.093857
2.9.2.1.4 | Delivery- Psv |  | 0.059994 |  |  |  |  | 30% |  |  |  | 0.070393
2.9.2.1.5 | Material Inspection | 0.405 | 0.14999 |  | 50% | 2.0551 | 2.055% |  |  |  |  | 0.17598
2.9.2.1.6 | Visual and Dimensional Inspection | 0.325 | 0.12036 |  | 40.12% | 0.8246 | 0.8246% |  |  |  |  | 0.14122
2.9.2.1.7 | Other Required Tests | 0.08 | 0.029627 |  | 9.877% | 0.081442 | 0.08144% |  |  |  |  | 0.034762
2.9.2.2 | On/Off Valve | 0.735 | 0.49995 |  | 33.33% | 3.7297 | 3.73% | 0.19998 | 0.29997 |  |  | 0.58661
2.9.2.2.1 | Inquiry-On/Off Valve |  | 0.019998 |  |  |  |  | 10% |  |  |  | 0.023464
2.9.2.2.2 | PO-On/Off Valve |  | 0.039996 |  |  |  |  | 20% |  |  |  | 0.046929
2.9.2.2.3 | IRN-On/Off Valve |  | 0.079992 |  |  |  |  | 40% |  |  |  | 0.093857
2.9.2.2.4 | Delivery-On/Off Valve |  | 0.059994 |  |  |  |  | 30% |  |  |  | 0.070393
2.9.2.2.5 | Material Inspection | 0.26 | 0.10611 |  | 35.37% | 1.3194 | 1.319% |  |  |  |  | 0.1245
2.9.2.2.6 | Visual and Dimensional & QTY Inspection | 0.15 | 0.10203 |  | 20.41% | 0.76117 | 0.7612% |  |  |  |  | 0.11972
2.9.2.2.7 | Construction | 0.185 | 0.12584 |  | 25.17% | 0.93877 | 0.9388% |  |  |  |  | 0.14765
2.9.2.2.8 | Accessory | 0.035 | 0.023807 |  | 4.762% | 0.17761 | 0.1776% |  |  |  |  | 0.027934
2.9.2.2.9 | Pressure Test | 0.035 | 0.023807 |  | 4.762% | 0.17761 | 0.1776% |  |  |  |  | 0.027934
2.9.2.2.10 | Calibration | 0.035 | 0.023807 |  | 4.762% | 0.17761 | 0.1776% |  |  |  |  | 0.027934
2.9.2.2.11 | Performance test | 0.035 | 0.023807 |  | 4.762% | 0.17761 | 0.1776% |  |  |  |  | 0.027934
2.9.2.3 | Control Valve | 0.735 | 0.49995 |  | 33.33% |  |  | 0.19998 | 0.29997 |  |  | 0.58661
2.9.2.3.1 | Inquiry-Control Valve |  | 0.019998 |  |  |  |  | 10% |  |  |  | 0.023464
2.9.2.3.2 | PO-Control Valve |  | 0.039996 |  |  |  |  | 20% |  |  |  | 0.046929
2.9.2.3.3 | IRN-Control Valve |  | 0.079992 |  |  |  |  | 40% |  |  |  | 0.093857
2.9.2.3.4 | Delivery-Control Valve |  | 0.059994 |  |  |  |  | 30% |  |  |  | 0.070393
2.9.2.3.5 | Material Inspection |  | 0.10611 |  | 35.37%
2.9.2.3.6 | Visual and Dimensional & QTY Inspection |  | 0.061218 |  | 20.41%
2.9.2.3.7 | Construction |  | 0.075503 |  | 25.17%
2.9.2.3.8 | Accessory |  | 0.014284 |  | 4.762%
2.9.2.3.9 | Pressure Test |  | 0.014284 |  | 4.762%
2.9.2.3.10 | Calibration |  | 0.014284 |  | 4.762%
2.9.2.3.11 | Performance test |  | 0.014284 |  | 4.762%
2.1 | Strainers | 1.56 | 1 |  | 2% | 1 | 1% | 0.4 | 0.6 | 1.205% | 1.705% | 1.5
2.10.1 | Inquiry-Strainers |  | 0.04 |  |  |  |  | 10% |  |  |  | 0.06
2.10.2 | PO-Strainers |  | 0.08 |  |  |  |  | 20% |  |  |  | 0.12
2.10.3 | IRN-Strainers |  | 0.16 |  |  |  |  | 40% |  |  |  | 0.24
2.10.4 | Delivery-Strainers |  | 0.12 |  |  |  |  | 30% |  |  |  | 0.18
2.10.5 | Material Inspection | 0.78 | 0.3 |  | 50% | 1.47 | 1.47% |  |  |  |  | 0.45
2.10.6 | Visual and Dimensional Inspection | 0.62 | 0.23846 |  | 39.74% | 1.1685 | 1.168% |  |  |  |  | 0.35769
2.10.7 | Hydro Test | 0.16 | 0.061538 |  | 10.26% | 0.30154 | 0.3015% |  |  |  |  | 0.092308
2.11 | Piping Items (Pipe, Flange, Fitting, Gasket, Bolt & Nuts) | 2.35 | 3 |  | 3.013% | 3.92 | 3.92% | 1.2 | 1.8 | 3.614% | 3.92% | 3.4496
2.11.1 | Inquiry-Pipe, Flange, Fitting, Gasket, Bolt & Nuts |  | 0.12 |  |  |  |  | 10% |  |  |  | 0.13798
2.11.2 | PO-Pipe, Flange, Fitting, Gasket, Bolt & Nuts |  | 0.24 |  |  |  |  | 20% |  |  |  | 0.27597
2.11.3 | IRN-Pipe, Flange, Fitting, Gasket, Bolt & Nuts |  | 0.48 |  |  |  |  | 40% |  |  |  | 0.55194
2.11.4 | Delivery-Pipe, Flange, Fitting, Gasket, Bolt & Nuts |  | 0.36 |  |  |  |  | 30% |  |  |  | 0.41395
2.11.5 | Material Inspection | 0.82 | 0.62809 | √ | 34.89% | 1.3678 | 1.368% |  |  |  |  | 0.72221
2.11.6 | Visual and Dimensional Inspection | 0.35 | 0.26809 | √ | 14.89% | 0.20372 | 0.2037% |  |  |  |  | 0.30826
2.11.7 | Weld Preparation and Fit-Up | 0.47 | 0.36 |  | 20% | 0.040744 | 0.04074% |  |  |  |  | 0.41395
2.11.8 | Welding | 0.47 | 0.36 |  | 20% | 0.0081488 | 0.008149% |  |  |  |  | 0.41395
2.11.9 | NDT( VT, MT, PT, UT, RT) | 0.12 | 0.091915 |  | 5.106% | 0.00041611 | 0.0004161% |  |  |  |  | 0.10569
2.11.10 | Hydrostatic Test | 0.12 | 0.091915 |  | 5.106% | 2.1248e-05 | 2.125e-05% |  |  |  |  | 0.10569
2.12 | Pump | 1.56 | 1 |  | 2% | 2.94 | 2.94% |  |  | 1.205% | 2.273% | 2
2.12.1 | Final Visual and Dimensional Inspection | 1.01 | 0.64744 |  | 64.74% | 1.9035 | 1.903% |  |  |  |  | 1.2949
2.12.2 | Performance test | 0.55 | 0.35256 |  | 35.26% | 1.0365 | 1.037% |  |  |  |  | 0.70513
2.13 | Ladder & Platform | 1.56 | 1 |  | 2% | 1.96 | 1.96% |  |  | 1.205% | 1.96% | 1.7248
2.13.1 | Visual and Dimensional Check After Welding | 1.56 | 1.96 |  |  | 1.96 | 1.96% |  |  |  |  | 1.96
2.14 | Chemical Injection Package | 3.14 | 1 |  | 4.026% | 2 | 2% |  |  | 1.205% | 1.705% | 1.5
2.14.1 | Raw Material for Tank | 1.09 | 0.34713 | √ | 34.71% | 1.4475 | 1.448% |  |  |  |  | 0.5207
2.14.2 | Final Inspection For Fabricated Tank | 0.16 | 0.050955 | √ | 5.096% | 0.21248 | 0.2125% |  |  |  |  | 0.076433
2.14.3 | Piping & Structure Works | 1.25 | 0.39809 |  | 39.81% | 1.66 | 1.66% |  |  |  |  | 0.59713
2.14.4 | Performance test | 0.16 | 0.050955 |  | 5.096% | 0.21248 | 0.2125% |  |  |  |  | 0.076433
2.14.5 | Packing Inspection | 0.16 | 0.050955 |  | 5.096% | 0.21248 | 0.2125% |  |  |  |  | 0.076433
2.14.6 | IRN | 0.16 | 0.050955 |  | 5.096% | 0.21248 | 0.2125% |  |  |  |  | 0.076433
2.14.7 | Final Book | 0.16 | 0.050955 |  | 5.096% | 0.21248 | 0.2125% |  |  |  |  | 0.076433
2.15 | Reboiler Burner | 1.56 | 1 |  | 2% | 1.97 | 1.97% |  |  | 1.205% | 1.97% | 1.7336
2.15.1 | Final Visual and Dimensional Inspection | 1.01 | 0.64744 |  | 0.64744 | 1.269 | 1.269% |  |  |  |  | 1.1224
2.15.2 | Burner Test | 0.55 | 0.35256 |  | 0.35256 | 0.69103 | 0.691% |  |  |  |  | 0.61121
2.16 | Painting of Package Assembly (Piping, Structure) | 0.78 | 0.7553 |  | 1% | 0.91 | 0.91% |  |  | 0.91% | 0.91% | 0.8008
2.16.1 | Abrasive & Paint Material | 0.39 | 0.37765 |  | 50% | 0.49 | 0.49% |  |  |  |  | 0.4004
2.16.2 | Blasting & Painting (Each Layer DFT, Adhesion) | 0.39 | 0.49 |  |  | 0.49 | 0.49% |  |  |  |  | 0.49
2.17 | Pickling (For Stainless Steel Part) | 0.78 | 0.7968 |  | 1% | 0.96 | 0.96% |  |  | 0.96% | 0.96% | 0.8448
2.17.1 | Pickling and Passivation | 0.78 | 0.98 |  |  | 0.98 | 0.98% |  |  |  |  | 0.98
2.18 | Preservation | 0.78 | 0 |  | 1% | 0 | 0% |  |  |  |  | 0
2.18.1 | N2 Purge /Silica | 0.78 | 0
3 | PACKING | 1 | 1
3.1 | Packing Inspection | 1 | 1
4 | IRN | 1 | 1
4.1 | Release Note | 1 | 1
5 | FINAL DATA BOOK | 3 | 3
5.1 | Final Document Preparation | 3 | 1
6 | IC | 1 | 1
6.1 | Inspection Certificate | 1 | 1
7 | SITE ACCEPTANCE TEST | 1 | 1
7.1 | SAT | 1 | 1