## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک ( قرارداد BK-HD-GCS-CO-0010_08)
Work Breakdown Structure (WBS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 25
9184 – 073 - 053 |  |  | BK |  | GCS | MF | 120 |  | PM | WB | 0001 | V02
طرح نگهداشت و افزایش تولید 27 مخزن
Work Breakdown Structure for Gas Dehydration Package (WBS) نگهداشت و افزایش تولید میدان نفتی بینک
V02 |  | NOV-2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | M.Sadghian
V01 |  | OCT-2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | M.Sadghian
V00 |  | JAN-2024 |  | IFA |  |  |  | MFS |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید بسته نم زدای گاز ایستگاه تقویت فشار گاز بینک ( قرارداد BK-HD-GCS-CO-0010_08)
Work Breakdown Structure (WBS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از25
9184 – 073 - 053 |  |  | BK | GCS |  | MF | 120 | PM | WB | 0001 |  | V02
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | X | [5 empty] | 65
2 | X | X | X | [5 empty] | 66
3 | X | X | X | [5 empty] | 67
4 | X | X | X | [5 empty] | 68
5 | X | X | X | [5 empty] | 69
6 | X | X | X | [5 empty] | 70
7 |  | X | X | [5 empty] | 71
8 |  | X | X | [5 empty] | 72
9 |  | X | X | [5 empty] | 73
10 |  |  | X | [5 empty] | 74
11 |  |  | X | [5 empty] | 75
12 |  |  | X | [5 empty] | 76
13 |  |  | X | [5 empty] | 77
14 |  |  | X | [5 empty] | 78
15 |  |  | X | [5 empty] | 79
16 |  |  | X | [5 empty] | 80
17 |  |  | X | [5 empty] | 81
18 |  |  | X | [5 empty] | 82
19 |  |  | X | [5 empty] | 83
20 |  |  | X | [5 empty] | 84
21 |  |  | X | [5 empty] | 85
22 |  |  | X | [5 empty] | 86
23 |  |  | X | [5 empty] | 87
24 |  |  | X | [5 empty] | 88
25 |  |  | X | [5 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## WBS_V02
WBS | Task Name | Doc. No. | WF (Total) | WF (Disc.)
0 | BINAK OILFIELD DEVELOPMENT |  | 100 | %
1 | DOCUMENTS |  | 7
1.1 | According to VPIS:
1.1.1 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | BK-GCS-MF-120-PM-LI-0001 | 0.0938 | 1.34%
1.1.2 | WORK BEAKDOWN STRUCTURE | BK-GCS-MF-120-PM-WB-0001 | 0.0938 | 1.34%
1.1.3 | TIME SCHEDULE | BK-GCS-MF-120-GE-SH-0001 | 0.0938 | 1.34%
1.1.4 | FINAL VENDOR DATA BOOK INDEX | BK-GCS-MF-120-GE-LI-0002 | 0.09366 | 1.338%
1.1.5 | SUB VENDOR LIST | BK-GCS-MF-120-GE-VL-0001 | 0.09366 | 1.338%
1.1.6 | SPARE PART LIST | BK-GCS-MF-120-GE-LI-0002 | 0.09366 | 1.338%
1.1.7 | HARDNESS TESTING PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | BK-GCS-MF-120-QC-PR-0001 | 0.0462 | 0.66%
1.1.8 | INSPECTION AND TEST PLAN (ITP) | BK-GCS-MF-120-QC-PR-0002 | 0.0938 | 1.34%
1.1.9 | QUALITY CONTROL PLAN (QCP) | BK-GCS-MF-120-QC-PR-0003 | 0.0462 | 0.66%
1.1.10 | SURFACE PREPARATION AND INTERNAL/EXTERNAL PAINTING PROCEDURE FOR TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS | BK-GCS-MF-120-QC-PR-0004 | 0.0462 | 0.66%
1.1.11 | PICKLING AND PASSIVATION PROCEDURE | BK-GCS-MF-120-QC-PR-0005 | 0.0462 | 0.66%
1.1.12 | POSTWELD HEAT TREATMENT PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | BK-GCS-MF-120-QC-PR-0006 | 0.0462 | 0.66%
1.1.13 | WPS & PQR (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | BK-GCS-MF-120-QC-PR-0007 | 0.1344 | 1.92%
1.1.14 | PMI PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | BK-GCS-MF-120-QC-PR-0008 | 0.0462 | 0.66%
1.1.15 | NDT PROCEDURE (TOWER, COLUMNS, REBOILER, DRUMS, FILTERS & EXCHANGERS) | BK-GCS-MF-120-QC-PR-0009 | 0.0462 | 0.66%
1.1.16 | HYDROSTATIC TESTING PRCOCEDURE (TOWER, COLUMNS, REBOILER, DRUMS & FILTERS) | BK-GCS-MF-120-QC-PR-0010 | 0.0462 | 0.66%
1.1.17 | HYDROSTATIC TEST PROCEDURE FOR HEAT EXCHANGERS | BK-GCS-MF-120-QC-PR-0011 | 0.0462 | 0.66%
1.1.18 | WELD REPAIR PROCEDURE | BK-GCS-MF-120-QC-PR-0012 | 0.0462 | 0.66%
1.1.19 | PACKING,MARKING,SHIPPING PROCEDURE | BK-GCS-MF-120-QC-PR-0013 | 0.0462 | 0.66%
1.1.20 | N2 PURGING PROCEDURE | BK-GCS-MF-120-QC-PR-0014 | 0.0462 | 0.66%
1.1.21 | SAT PROCEDURE FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-QC-PR-0015 | 0.0462 | 0.66%
1.1.22 | OPERATION, COMMISSIONING & MAINTENANCE MANUAL FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-QC-ML-0001 | 0.0938 | 1.34%
1.1.23 | BASIS OF PROCESS DESIGN FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PR-DB-0001 | 0.1218 | 1.74%
1.1.24 | CONTROL PHILOSOPHY | BK-GCS-MF-120-PR-PH-0001 | 0.0371 | 0.53%
1.1.25 | PRESSURE SAFETY VALVE CALCULATION SHEETS | BK-GCS-MF-120-PR-CN-0001 | 0.0371 | 0.53%
1.1.26 | PROCESS DATA SHEET FOR DEHYDRATION GLYCOL CONTACTOR | BK-GCS-MF-120-PR-DS-0001 | 0.0371 | 0.53%
1.1.27 | PROCESS DATA SHEET FOR GLYCOL FLASH DRUM | BK-GCS-MF-120-PR-DS-0002 | 0.0371 | 0.53%
1.1.28 | PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER | BK-GCS-MF-120-PR-DS-0003 | 0.0371 | 0.53%
1.1.29 | PROCESS DATA SHEET FOR GLYCOL CARBON FILTER | BK-GCS-MF-120-PR-DS-0004 | 0.0371 | 0.53%
1.1.30 | PROCESS DATA SHEET FOR LEAN GLYCOL FILTER | BK-GCS-MF-120-PR-DS-0014 | 0.0371 | 0.53%
1.1.31 | PROCESS DATA SHEET FOR GLYCOL STILL COLUMN | BK-GCS-MF-120-PR-DS-0005 | 0.0371 | 0.53%
1.1.32 | PROCESS DATA SHEET FOR GLYCOL CIRCULATION PUMPS | BK-GCS-MF-120-PR-DS-0006 | 0.0371 | 0.53%
1.1.33 | PROCESS DATA SHEET FOR LEAN GLYCOL DRY GAS HEAT EXCHSNGER | BK-GCS-MF-120-PR-DS-0007 | 0.0371 | 0.53%
1.1.34 | PROCESS DATA SHEET FOR RICH / LEAN GLYCOL HEAT EXCHANGER | BK-GCS-MF-120-PR-DS-0008 | 0.0371 | 0.53%
1.1.35 | PROCESS DATA SHEET FOR GLYCOL REFLUX CONDENSER | BK-GCS-MF-120-PR-DS-0009 | 0.0371 | 0.53%
1.1.36 | PROCESS DATA SHEET FOR GLYCOL REBOILER | BK-GCS-MF-120-PR-DS-0010 | 0.0371 | 0.53%
1.1.37 | PROCESS DATA SHEET FOR ANTI-FOAM PACKAGE | BK-GCS-MF-120-PR-DS-0011 | 0.0371 | 0.53%
1.1.38 | PROCESS DATA SHEET FOR PH-CONTROLLER PACKAGE | BK-GCS-MF-120-PR-DS-0012 | 0.0371 | 0.53%
1.1.39 | PROCESS DATA SHEET FOR GLYCOL SURGE DRUM | BK-GCS-MF-120-PR-DS-0013 | 0.0371 | 0.53%
1.1.40 | PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PR-PF-0001 | 0.1372 | 1.96%
1.1.41 | HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PR-PF-0002 | 0.1372 | 1.96%
1.1.42 | PIPING & INSTRUMENTATION DIAGRAM FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PR-PI-0003 | 0.1372 | 1.96%
1.1.43 | CAUSE AND EFFECT DIAGRAM FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PR-CE-0001 | 0.0371 | 0.53%
1.1.44 | EQUIPMENT LIST | BK-GCS-MF-120-PR-LI-0001 | 0.0371 | 0.53%
1.1.45 | ALARM & TRIP SET POINT LIST | BK-GCS-MF-120-PR-LI-0002 | 0.0371 | 0.53%
1.1.46 | UTILITY CONSUMPTION LIST | BK-GCS-MF-120-PR-LI-0003 | 0.0371 | 0.53%
1.1.47 | CHEMICAL CONSUMPTION LIST | BK-GCS-MF-120-PR-LI-0004 | 0.0371 | 0.53%
1.1.48 | HAZOP STUDY REPORT | BK-GCS-MF-120-PR-RE-0001 | 0.0371 | 0.53%
1.1.49 | SIL STUDY REPORT | BK-GCS-MF-120-PR-RE-0002 | 0.0371 | 0.53%
1.1.50 | MECHANICAL CALCULATION BOOK FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-CN-0001 | 0.0196 | 0.28%
1.1.51 | GENERAL ARRANGEMENT FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-DW-0001 | 0.01512 | 0.216%
1.1.52 | DETAILS DRAWING FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-DW-0002 | 0.0091 | 0.13%
1.1.53 | NAME PLATE DETAIL DRAWING FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-DW-0003 | 0.0049 | 0.07%
1.1.54 | TEMPLATE DRAWING FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-DW-0004 | 0.0098 | 0.14%
1.1.55 | WELDING & NDT MAP FOR GLYCOL CONTACTOR (C-100) | BK-GCS-MF-120-ME-MP-0001 | 0.0063 | 0.09%
1.1.56 | MECHANICAL CALCULATION BOOK FOR STILL COLUMN (C-200) | BK-GCS-MF-120-ME-CN-0002 | 0.0245 | 0.35%
1.1.57 | GENERAL ARRANGEMENT FOR STILL COLUMN (C-200) | BK-GCS-MF-120-ME-DW-0005 | 0.0196 | 0.28%
1.1.58 | DETAILS DRAWING FOR STILL COLUMN (C-200) | BK-GCS-MF-120-ME-DW-0006 | 0.0133 | 0.19%
1.1.59 | NAME PLATE DETAIL DRAWING FOR STILL COLUMN (C-200) | BK-GCS-MF-120-ME-DW-0007 | 0.0063 | 0.09%
1.1.60 | WELDING & NDT MAP FOR STILL COLUMN (C-200) | BK-GCS-MF-120-ME-MP-0002 | 0.0063 | 0.09%
1.1.61 | MECHANICAL CALCULATION BOOK FOR GLYCOL FLASH DRUM (V-120) | BK-GCS-MF-120-ME-CN-0003 | 0.0196 | 0.28%
1.1.62 | GENERAL ARRANGEMENT FOR GLYCOL FLASH DRUM (V-120) | BK-GCS-MF-120-ME-DW-0008 | 0.0182 | 0.26%
1.1.63 | DETAILS DRAWING FOR GLYCOL FLASH DRUM (V-120) | BK-GCS-MF-120-ME-DW-0009 | 0.0154 | 0.22%
1.1.64 | NAME PLATE DETAIL DRAWING FOR GLYCOL FLASH DRUM (V-120) | BK-GCS-MF-120-ME-DW-0010 | 0.0049 | 0.07%
1.1.65 | WELDING & NDT MAP FOR GLYCOL FLASH DRUM (V-120) | BK-GCS-MF-120-ME-MP-0003 | 0.0063 | 0.09%
1.1.66 | MECHANICAL CALCULATION BOOK FOR GLYCOL SURGE DRUM (V-130) | BK-GCS-MF-120-ME-CN-0011 | 0.0133 | 0.19%
1.1.67 | GENERAL ARRANGEMENT FOR GLYCOL SURGE DRUM (V-130) | BK-GCS-MF-120-ME-DW-0036 | 0.01246 | 0.178%
1.1.68 | DETAILS DRAWING FOR GLYCOL SURGE DRUM (V-130) | BK-GCS-MF-120-ME-DW-0037 | 0.01288 | 0.184%
1.1.69 | NAME PLATE DETAIL DRAWING FOR GLYCOL SURGE DRUM (V-130) | BK-GCS-MF-120-ME-DW-0038 | 0.00126 | 0.018%
1.1.70 | WELDING & NDT MAP FOR GLYCOL SURGE DRUM (V-130) | BK-GCS-MF-120-ME-MP-0011 | 0.0077 | 0.11%
1.1.71 | MECHANICAL CALCULATION BOOK FOR GLYCOL PARTICLE FILTER (F-100 A/B) | BK-GCS-MF-120-ME-CN-0004 | 0.03276 | 0.468%
1.1.72 | GENERAL ARRANGEMENT FOR GLYCOL PARTICLE FILTER (F-100 A/B) | BK-GCS-MF-120-ME-DW-0011 | 0.02954 | 0.422%
1.1.73 | DETAILS DRAWING FOR GLYCOL PARTICLE FILTER (F-100 A/B) | BK-GCS-MF-120-ME-DW-0012 | 0.0189 | 0.27%
1.1.74 | NAME PLATE DETAIL DRAWING FOR GLYCOL PARTICLE FILTER (F-100 A/B) | BK-GCS-MF-120-ME-DW-0013 | 0.00196 | 0.028%
1.1.75 | WELDING & NDT MAP FOR GLYCOL PARTICLE FILTER (F-100 A/B) | BK-GCS-MF-120-ME-MP-0004 | 0.01134 | 0.162%
1.1.76 | MECHANICAL CALCULATION BOOK FOR GLYCOL CARBON FILTER (F-200) | BK-GCS-MF-120-ME-CN-0005 | 0.0406 | 0.58%
1.1.77 | GENERAL ARRANGEMENT FOR GLYCOL CARBON FILTER (F-200) | BK-GCS-MF-120-ME-DW-0014 | 0.03612 | 0.516%
1.1.78 | DETAILS DRAWING FOR GLYCOL CARBON FILTER (F-200) | BK-GCS-MF-120-ME-DW-0015 | 0.02086 | 0.298%
1.1.79 | NAME PLATE DETAIL DRAWING FOR GLYCOL CARBON FILTER (F-200) | BK-GCS-MF-120-ME-DW-0016 | 0.0021 | 0.03%
1.1.80 | WELDING & NDT MAP FOR GLYCOL CARBON FILTER (F-200) | BK-GCS-MF-120-ME-MP-0005 | 0.0126 | 0.18%
1.1.81 | MECHANICAL CALCULATION BOOK FOR LEAN GLYCOL FILTER (F-300) | BK-GCS-MF-120-ME-CN-0010 | 0.0259 | 0.37%
1.1.82 | GENERAL ARRANGEMENT FOR LEAN GLYCOL FILTER (F-300) | BK-GCS-MF-120-ME-DW-0033 | 0.02352 | 0.336%
1.1.83 | DETAILS DRAWING FOR LEAN GLYCOL FILTER (F-300) | BK-GCS-MF-120-ME-DW-0034 | 0.0196 | 0.28%
1.1.84 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL FILTER (F-300) | BK-GCS-MF-120-ME-DW-0035 | 0.00644 | 0.092%
1.1.85 | WELDING & NDT MAP FOR LEAN GLYCOL FILTER (F-300) | BK-GCS-MF-120-ME-MP-0010 | 0.00644 | 0.092%
1.1.86 | THERMAL/MECH. CALCULATION BOOK FOR GLYCOL REFLUX CONDENSER (E-100) | BK-GCS-MF-120-ME-CN-0006 | 0.03976 | 0.568%
1.1.87 | GENERAL ARRANGEMENT FOR GLYCOL REFLUX CONDENSER (E-100) | BK-GCS-MF-120-ME-DW-0017 | 0.03542 | 0.506%
1.1.88 | DETAILS DRAWING FOR GLYCOL REFLUX CONDENSER (E-100) | BK-GCS-MF-120-ME-DW-0018 | 0.02072 | 0.296%
1.1.89 | NAME PLATE DETAIL DRAWING FOR GLYCOL REFLUX CONDENSER (E-100) | BK-GCS-MF-120-ME-DW-0019 | 0.0021 | 0.03%
1.1.90 | WELDING & NDT MAP FOR GLYCOL REFLUX CONDENSER (E-100) | BK-GCS-MF-120-ME-MP-0006 | 0.01246 | 0.178%
1.1.91 | THERMAL/MECH. CALCULATION BOOK FOR RICH-LEAN GLYCOL H.E. (E-200) | BK-GCS-MF-120-ME-CN-0007 | 0.0406 | 0.58%
1.1.92 | GENERAL ARRANGEMENT FOR RICH-LEAN GLYCOL H.E. (E-200) | BK-GCS-MF-120-ME-DW-0020 | 0.03612 | 0.516%
1.1.93 | DETAILS DRAWING FOR RICH-LEAN GLYCOL H.E. (E-200) | BK-GCS-MF-120-ME-DW-0021 | 0.02086 | 0.298%
1.1.94 | NAME PLATE DETAIL DRAWING FOR RICH-LEAN GLYCOL H.E. (E-200) | BK-GCS-MF-120-ME-DW-0022 | 0.0021 | 0.03%
1.1.95 | WELDING & NDT MAP FOR RICH-LEAN GLYCOL H.E. (E-200) | BK-GCS-MF-120-ME-MP-0007 | 0.0126 | 0.18%
1.1.96 | THERMAL/MECH. CALCULATION BOOK FOR LEAN GLYCOL GAS H.E. (E-300) | BK-GCS-MF-120-ME-CN-0008 | 0.0406 | 0.58%
1.1.97 | GENERAL ARRANGEMENT FOR LEAN GLYCOL GAS H.E. (E-300) | BK-GCS-MF-120-ME-DW-0023 | 0.03612 | 0.516%
1.1.98 | DETAILS DRAWING FOR LEAN GLYCOL GAS H.E. (E-300) | BK-GCS-MF-120-ME-DW-0024 | 0.02086 | 0.298%
1.1.99 | NAME PLATE DETAIL DRAWING FOR LEAN GLYCOL GAS H.E. (E-300) | BK-GCS-MF-120-ME-DW-0025 | 0.0021 | 0.03%
1.1.100 | WELDING & NDT MAP FOR LEAN GLYCOL GAS H.E. (E-300) | BK-GCS-MF-120-ME-MP-0008 | 0.0126 | 0.18%
1.1.101 | THERMAL/MECHANICAL CALCULATION BOOK FOR REBOILER (R-100) | BK-GCS-MF-120-ME-CN-0009 | 0.01218 | 0.174%
1.1.102 | GENERAL ARRANGEMENT FOR REBOILER (R-100) | BK-GCS-MF-120-ME-DW-0026 | 0.01036 | 0.148%
1.1.103 | DETAILS DRAWING FOR REBOILER (R-100) | BK-GCS-MF-120-ME-DW-0027 | 0.0119 | 0.17%
1.1.104 | NAME PLATE DETAIL DRAWING FOR REBOILER (R-100) | BK-GCS-MF-120-ME-DW-0028 | 0.00126 | 0.018%
1.1.105 | WELDING & NDT MAP FOR REBOILER (R-100) | BK-GCS-MF-120-ME-MP-0009 | 0.00714 | 0.102%
1.1.106 | LUBRICATION LIST | BK-GCS-MF-120-ME-LI-0001 | 0.02394 | 0.342%
1.1.107 | GENERAL ASSEMBLY DRAWING FOR GLYCOL CIRCULATION PUMPS | BK-GCS-MF-120-ME-DW-0029 | 0.02394 | 0.342%
1.1.108 | PUMPS CROSS SECTIONAL DRAWING FOR GLYCOL CIRCULATION PUMPS | BK-GCS-MF-120-ME-DW-0030 | 0.02394 | 0.342%
1.1.109 | NAME PLATE FOR GLYCOL CIRCULATION PUMPS | BK-GCS-MF-120-ME-DW-0031 | 0.02352 | 0.336%
1.1.110 | BURNER DATA SHEET FOR GLYCOL REBOILER | BK-GCS-MF-120-ME-DS-0001 | 0.02394 | 0.342%
1.1.111 | BURNER DRAWING FOR GLYCOL REBOILER | BK-GCS-MF-120-ME-DW-0032 | 0.02394 | 0.342%
1.1.112 | PACKAGE PLOT PLAN DRAWING | BK-GCS-MF-120-PI-DW-0001 | 0.05222 | 0.746%
1.1.113 | PIPING GENERAL ARRANGEMENT DRAWING | BK-GCS-MF-120-PI-DW-0002 | 0.05222 | 0.746%
1.1.114 | PIPING ISOMETRIC DRAWING FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-PI-DW-0003 | 0.05222 | 0.746%
1.1.115 | LINE LIST | BK-GCS-MF-120-PI-LI-0001 | 0.05222 | 0.746%
1.1.116 | TIE-IN-LIST | BK-GCS-MF-120-PI-LI-0002 | 0.05222 | 0.746%
1.1.117 | PDMS MODEL REVIEW REPORT (60%) | BK-GCS-MF-120-PI-RT-0001 | 0.05222 | 0.746%
1.1.118 | PDMS MODEL REVIEW REPORT (90%) | BK-GCS-MF-120-PI-RT-0002 | 0.05222 | 0.746%
1.1.119 | STRESS ANALYSIS REPORT | BK-GCS-MF-120-PI-RT-0003 | 0.05222 | 0.746%
1.1.120 | CONTROL VALVE CALCULATION SHEETS | BK-GCS-MF-120-IN-CN-0001 | 0.04004 | 0.572%
1.1.121 | FLOW ELEMENT CALCULATION SHEETS | BK-GCS-MF-120-IN-CN-0002 | 0.04004 | 0.572%
1.1.122 | CONTROL SYSTEM CONFIGURATION BLOCK DIAGRAM | BK-GCS-MF-120-IN-DW-0001 | 0.04004 | 0.572%
1.1.123 | ESD/BMS SYSTEM CONFIGURATION BLOCK DIAGRAM | BK-GCS-MF-120-IN-DW-0002 | 0.04004 | 0.572%
1.1.124 | INSTRUMENT JUNCTION BOX LAYOUT AND WIRING TERMINATION DIAGRAM | BK-GCS-MF-120-IN-DW-0003 | 0.04004 | 0.572%
1.1.125 | BURNER OPERATION PANEL LAYOUT & WIRING DIAGRAM WITH CONNECTIONS & DIMENSIONS | BK-GCS-MF-120-IN-DW-0004 | 0.04004 | 0.572%
1.1.126 | HOOK UP DRAWING | BK-GCS-MF-120-IN-DW-0005 | 0.0399 | 0.57%
1.1.127 | INSTRUMENT LOCATION LAYOUT | BK-GCS-MF-120-IN-DW-0006 | 0.0399 | 0.57%
1.1.128 | CONTROL PANEL LAYOUT AND ARRANGEMENT | BK-GCS-MF-120-IN-DW-0007 | 0.0399 | 0.57%
1.1.129 | ESD/BMS PANEL LAYOUT AND ARRANGEMENT | BK-GCS-MF-120-IN-DW-0008 | 0.0399 | 0.57%
1.1.130 | CONTROL SYSTEM WIRING DIAGRAM AND CONNECTIONS | BK-GCS-MF-120-IN-DW-0009 | 0.0399 | 0.57%
1.1.131 | ESD/BMS SYSTEM WIRING DIAGRAM AND CONNECTIONS | BK-GCS-MF-120-IN-DW-0010 | 0.0399 | 0.57%
1.1.132 | CONTROL SYSTEM LOGIC DIAGRAM | BK-GCS-MF-120-IN-DW-0011 | 0.0399 | 0.57%
1.1.133 | ESD/BMS SYSTEM LOGIC DIAGRAM | BK-GCS-MF-120-IN-DW-0012 | 0.0399 | 0.57%
1.1.134 | PRINT OUT OF HMI FOR BMS AND UCP | BK-GCS-MF-120-IN-DW-0013 | 0.0399 | 0.57%
1.1.135 | CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING | BK-GCS-MF-120-IN-DW-0014 | 0.0399 | 0.57%
1.1.136 | INSTRUMENT EARTH DISTRIBUTION DIAGRAM | BK-GCS-MF-120-IN-DW-0015 | 0.0399 | 0.57%
1.1.137 | INSTRUMENT CABLE ROUTE/ MAIN TUBING LAYOUT DRAWING | BK-GCS-MF-120-IN-DW-0016 | 0.0399 | 0.57%
1.1.138 | ESD LEVEL HIERARCHY | BK-GCS-MF-120-IN-DW-0017 | 0.0399 | 0.57%
1.1.139 | INSTRUMENT D.S. FOR CONTROL VALVES | BK-GCS-MF-120-IN-DS-0001 | 0.04004 | 0.572%
1.1.140 | INSTRUMENT D.S. FOR ON/OFF VALVES | BK-GCS-MF-120-IN-DS-0002 | 0.04004 | 0.572%
1.1.141 | INSTRUMENT D.S. FOR H2O ANALYZER | BK-GCS-MF-120-IN-DS-0003 | 0.04004 | 0.572%
1.1.142 | INSTRUMENT D.S. FOR TEMPERATURE GAUGE | BK-GCS-MF-120-IN-DS-0004 | 0.04004 | 0.572%
1.1.143 | INSTRUMENT D.S. FOR TEMPERATURE TRANSMITTERS | BK-GCS-MF-120-IN-DS-0005 | 0.04004 | 0.572%
1.1.144 | INSTRUMENT D.S. FOR PRESSURE GAUGES AND DIFF. PRESSURE GAUGES | BK-GCS-MF-120-IN-DS-0006 | 0.04004 | 0.572%
1.1.145 | INSTRUMENT D.S. FOR PRESSURE TRANSMITTERS AND DIFFE. PRESSURE TRANSMITTERS | BK-GCS-MF-120-IN-DS-0007 | 0.04004 | 0.572%
1.1.146 | INSTRUMENT D.S. FOR PRESSURE REGULATOR VALVES | BK-GCS-MF-120-IN-DS-0008 | 0.04004 | 0.572%
1.1.147 | INSTRUMENT D.S. FOR FLOW ELEMENTS | BK-GCS-MF-120-IN-DS-0009 | 0.04004 | 0.572%
1.1.148 | INSTRUMENT D.S. FOR LEVEL GAUGES | BK-GCS-MF-120-IN-DS-0010 | 0.04004 | 0.572%
1.1.149 | INSTRUMENT D.S. FOR LEVEL TRANSMITTERS | BK-GCS-MF-120-IN-DS-0011 | 0.04004 | 0.572%
1.1.150 | FLAME SCANNER DATA SHEET | BK-GCS-MF-120-IN-DS-0012 | 0.0399 | 0.57%
1.1.151 | INSTRUMENT D.S. FOR SAFETY VALVES | BK-GCS-MF-120-IN-DS-0013 | 0.04004 | 0.572%
1.1.152 | FAT PROCEDURE FOR CONTROL SYSTEM | BK-GCS-MF-120-IN-PR-0001 | 0.03948 | 0.564%
1.1.153 | FAT PROCEDURE FOR ESD/BMS SYSTEM | BK-GCS-MF-120-IN-PR-0002 | 0.03948 | 0.564%
1.1.154 | SAT PROCEDURE FOR CONTROL SYSTEM | BK-GCS-MF-120-IN-PR-0003 | 0.03948 | 0.564%
1.1.155 | SAT PROCEDURE FOR ESD/BMS SYSTEM | BK-GCS-MF-120-IN-PR-0004 | 0.03948 | 0.564%
1.1.156 | INSTRUMENT LIST | BK-GCS-MF-120-IN-LI-0001 | 0.04004 | 0.572%
1.1.157 | INPUT/OUTPUT SIGNAL LIST | BK-GCS-MF-120-IN-LI-0002 | 0.04004 | 0.572%
1.1.158 | INSTRUMENT CABLE LIST | BK-GCS-MF-120-IN-LI-0003 | 0.04004 | 0.572%
1.1.159 | UCP AND BMS SYSTEM POWER CONSUMPTION LIST | BK-GCS-MF-120-IN-LI-0004 | 0.0399 | 0.57%
1.1.160 | MODBUS IO LIST (MODBUS MAPPING LIST) | BK-GCS-MF-120-IN-LI-0005 | 0.0399 | 0.57%
1.1.161 | ELECTRICAL SINGLE LINE DIAGRAM | BK-GCS-MF-120-EL-DW-0001 | 0.0623 | 0.89%
1.1.162 | EARTHING DETAIL LAYOUT | BK-GCS-MF-120-EL-DW-0002 | 0.04312 | 0.616%
1.1.163 | ELECTRICAL CABLE ROUTE | BK-GCS-MF-120-EL-DW-0003 | 0.06188 | 0.884%
1.1.164 | ELECTRICAL PANEL LAYOUT AND WIRING DIAGRAM | BK-GCS-MF-120-EL-DW-0004 | 0.0623 | 0.89%
1.1.165 | LOCAL CONTROL STATION (LCS) PANEL LAYOUT AND WIRING DIAGRAM | BK-GCS-MF-120-EL-DW-0005 | 0.05586 | 0.798%
1.1.166 | ELECTRICAL EQUIPMENT LAYOUT | BK-GCS-MF-120-EL-DW-0006 | 0.04312 | 0.616%
1.1.167 | POWER AND CONTROL CABLE LIST | BK-GCS-MF-120-EL-LI-0001 | 0.06188 | 0.884%
1.1.168 | ELECTRICAL LOAD LIST | BK-GCS-MF-120-EL-LI-0002 | 0.06188 | 0.884%
1.1.169 | ELECTRICAL SIGNAL LIST | BK-GCS-MF-120-EL-LI-0003 | 0.0623 | 0.89%
1.1.170 | ELECTRICAL MOTORS DATA SHEETS, CURVES, DRAWINGS AND CERTIFICATES | BK-GCS-MF-120-EL-DS-0001 | 0.06188 | 0.884%
1.1.171 | CABLE DATASHEETS | BK-GCS-MF-120-EL-DS-0002 | 0.06188 | 0.884%
1.1.172 | ELECTRICAL PANEL DATASHEETS | BK-GCS-MF-120-EL-DS-0003 | 0.06188 | 0.884%
1.1.173 | LOCAL CONTROL STATION (LCS) DATASHEETS | BK-GCS-MF-120-EL-DS-0004 | 0.06188 | 0.884%
1.1.174 | HAZARDOUS AREA CLASSIFICATION AND IP CERTIFICATE FOR MOTORS, LCS, LCP, LIGHTINGS, JB, HEATERS, ETC | BK-GCS-MF-120-EL-DS-0005 | 0.06188 | 0.884%
1.1.175 | ELECTRICAL MOTORS FAT REPORTS | BK-GCS-MF-120-EL-DS-0006 | 0.06188 | 0.884%
1.1.176 | STRUCTURAL DESIGN CALCULATION FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-ST-CN-0001 | 0.04354 | 0.622%
1.1.177 | FOUNDATION LOADING DATA FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-ST-CN-0002 | 0.04354 | 0.622%
1.1.178 | STEEL STRUCTURAL DETAIL DRAWING FOR GAS DEHYDRATION PACKAGE | BK-GCS-MF-120-ST-DW-0001 | 0.04354 | 0.622%
2 | MANUFACTURING |  | 84
2.1 | Vessel |  | 31.4
2.1.1 | Glycol Contactor (C-100) |  | 3.925 | 12.5%
2.1.1.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.1.1.1 | PLATE |  | 0.54245 | 60%
2.1.1.1.1.1 | PO |  | 0.10849 | 20%
2.1.1.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.1.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.1.1.2 | FLANGE |  | 0.27122 | 30%
2.1.1.1.2.1 | PO |  | 0.054245 | 20%
2.1.1.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.1.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.1.1.3 | PIPE |  | 0.090408 | 10%
2.1.1.1.3.1 | PO |  | 0.018082 | 20%
2.1.1.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.1.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.1.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.1.2.1 | PLATE |  | 0.24991 | 90%
2.1.1.2.1.1 | PO |  | 0.049983 | 20%
2.1.1.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.1.2.1.3 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.1.2.2 | PROFILE |  | 0.027768 | 10%
2.1.1.2.2.1 | PO |  | 0.0055536 | 20%
2.1.1.2.2.1 | Delivery To Factory |  | 0.0083305 | 30%
2.1.1.2.2.1 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.1.3 | Internals |  | 0.078784 | 2.007%
2.1.1.3.1 | PO |  | 0.015757 | 20%
2.1.1.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.1.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.1.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.1.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.1.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.1.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.1.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.1.9 | Welding |  | 0.51016 | 13%
2.1.1.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.1.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.1.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.1.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.1.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.1.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.1.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.1.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.1.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.1.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.1.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.1.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.1.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.1.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.2 | Still Column (C-200) |  | 3.925 | 12.5%
2.1.2.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.2.1.1 | PLATE |  | 0.54245 | 60%
2.1.2.1.1.1 | PO |  | 0.10849 | 20%
2.1.2.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.2.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.2.1.2 | FLANGE |  | 0.27122 | 30%
2.1.2.1.2.1 | PO |  | 0.054245 | 20%
2.1.2.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.2.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.2.1.3 | PIPE |  | 0.090408 | 10%
2.1.2.1.3.1 | PO |  | 0.018082 | 20%
2.1.2.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.2.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.2.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.2.2.1 | PLATE |  | 0.24991 | 90%
2.1.2.2.1.1 | PO |  | 0.049983 | 20%
2.1.2.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.2.2.1.3 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.2.2.2 | PROFILE |  | 0.027768 | 10%
2.1.2.2.2.1 | PO |  | 0.0055536 | 20%
2.1.2.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.2.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.2.3 | Internals |  | 0.078784 | 2.007%
2.1.2.3.1 | PO |  | 0.015757 | 20%
2.1.2.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.2.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.2.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.2.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.2.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.2.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.2.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.2.9 | Welding |  | 0.51016 | 13%
2.1.2.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.2.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.2.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.2.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.2.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.2.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.2.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.2.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.2.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.2.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.2.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.2.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.2.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.2.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.3 | Glycol Flash Drum (V-120) |  | 3.925 | 12.5%
2.1.3.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.3.1.1 | PLATE |  | 0.54245 | 60%
2.1.3.1.1.1 | PO |  | 0.10849 | 20%
2.1.3.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.3.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.3.1.2 | FLANGE |  | 0.27122 | 30%
2.1.3.1.2.1 | PO |  | 0.054245 | 20%
2.1.3.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.3.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.3.1.3 | PIPE |  | 0.090408 | 10%
2.1.3.1.3.1 | PO |  | 0.018082 | 20%
2.1.3.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.3.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.3.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.3.2.1 | PLATE |  | 0.24991 | 90%
2.1.3.2.1.1 | PO |  | 0.049983 | 20%
2.1.3.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.3.2.1.3 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.3.2.2 | PROFILE |  | 0.027768 | 10%
2.1.3.2.2.1 | PO |  | 0.0055536 | 20%
2.1.3.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.3.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.3.3 | Internals |  | 0.078784 | 2.007%
2.1.3.3.1 | PO |  | 0.015757 | 20%
2.1.3.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.3.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.3.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.3.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.3.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.3.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.3.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.3.9 | Welding |  | 0.51016 | 13%
2.1.3.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.3.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.3.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.3.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.3.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.3.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.3.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.3.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.3.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.3.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.3.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.3.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.3.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.3.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.4 | Glycol Surge Drum (V-130) |  | 3.925 | 12.5%
2.1.4.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.4.1.1 | PLATE |  | 0.54245 | 60%
2.1.4.1.1.1 | PO |  | 0.10849 | 20%
2.1.4.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.4.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.4.1.2 | FLANGE |  | 0.27122 | 30%
2.1.4.1.2.1 | PO |  | 0.054245 | 20%
2.1.4.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.4.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.4.1.3 | PIPE |  | 0.090408 | 10%
2.1.4.1.3.1 | PO |  | 0.018082 | 20%
2.1.4.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.4.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.4.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.4.2.1 | PLATE |  | 0.24991 | 90%
2.1.4.2.1.1 | PO |  | 0.049983 | 20%
2.1.4.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.4.2.1.4 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.4.2.2 | PROFILE |  | 0.027768 | 10%
2.1.4.2.2.1 | PO |  | 0.0055536 | 20%
2.1.4.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.4.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.4.3 | Internals |  | 0.078784 | 2.007%
2.1.4.3.1 | PO |  | 0.015757 | 20%
2.1.4.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.4.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.4.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.4.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.4.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.4.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.4.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.4.9 | Welding |  | 0.51016 | 13%
2.1.4.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.4.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.4.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.4.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.4.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.4.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.4.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.4.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.4.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.4.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.4.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.4.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.4.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.4.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.5 | Glycol Particle Filter (F-100 A/B) |  | 3.925 | 12.5%
2.1.5.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.5.1.1 | PLATE |  | 0.54245 | 60%
2.1.5.1.1.1 | PO |  | 0.10849 | 20%
2.1.5.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.5.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.5.1.2 | FLANGE |  | 0.27122 | 30%
2.1.5.1.2.1 | PO |  | 0.054245 | 20%
2.1.5.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.5.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.5.1.3 | PIPE |  | 0.090408 | 10%
2.1.5.1.3.1 | PO |  | 0.018082 | 20%
2.1.5.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.5.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.5.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.5.2.1 | PLATE |  | 0.24991 | 90%
2.1.5.2.1.1 | PO |  | 0.049983 | 20%
2.1.5.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.5.2.1.5 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.5.2.2 | PROFILE |  | 0.027768 | 10%
2.1.5.2.2.1 | PO |  | 0.0055536 | 20%
2.1.5.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.5.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.5.3 | Internals |  | 0.078784 | 2.007%
2.1.5.3.1 | PO |  | 0.015757 | 20%
2.1.5.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.5.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.5.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.5.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.5.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.5.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.5.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.5.9 | Welding |  | 0.51016 | 13%
2.1.5.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.5.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.5.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.5.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.5.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.5.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.5.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.5.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.5.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.5.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.5.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.5.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.5.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.5.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.6 | Glycol Carbon Filter (F-200) |  | 3.925 | 12.5%
2.1.6.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.6.1.1 | PLATE |  | 0.54245 | 60%
2.1.6.1.1.1 | PO |  | 0.10849 | 20%
2.1.6.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.6.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.6.1.2 | FLANGE |  | 0.27122 | 30%
2.1.6.1.2.1 | PO |  | 0.054245 | 20%
2.1.6.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.6.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.6.1.3 | PIPE |  | 0.090408 | 10%
2.1.6.1.3.1 | PO |  | 0.018082 | 20%
2.1.6.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.6.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.6.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.6.2.1 | PLATE |  | 0.24991 | 90%
2.1.6.2.1.1 | PO |  | 0.049983 | 20%
2.1.6.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.6.2.1.6 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.6.2.2 | PROFILE |  | 0.027768 | 10%
2.1.6.2.2.1 | PO |  | 0.0055536 | 20%
2.1.6.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.6.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.6.3 | Internals |  | 0.078784 | 2.007%
2.1.6.3.1 | PO |  | 0.015757 | 20%
2.1.6.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.6.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.6.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.6.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.6.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.6.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.6.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.6.9 | Welding |  | 0.51016 | 13%
2.1.6.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.6.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.6.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.6.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.6.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.6.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.6.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.6.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.6.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.6.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.6.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.6.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.6.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.6.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.7 | Lean Glycol Filter (F-300) |  | 3.925 | 12.5%
2.1.7.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.7.1.1 | PLATE |  | 0.54245 | 60%
2.1.7.1.1.1 | PO |  | 0.10849 | 20%
2.1.7.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.7.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.7.1.2 | FLANGE |  | 0.27122 | 30%
2.1.7.1.2.1 | PO |  | 0.054245 | 20%
2.1.7.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.7.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.7.1.3 | PIPE |  | 0.090408 | 10%
2.1.7.1.3.1 | PO |  | 0.018082 | 20%
2.1.7.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.7.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.7.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.7.2.1 | PLATE |  | 0.24991 | 90%
2.1.7.2.1.1 | PO |  | 0.049983 | 20%
2.1.7.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.7.2.1.7 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.7.2.2 | PROFILE |  | 0.027768 | 10%
2.1.7.2.2.1 | PO |  | 0.0055536 | 20%
2.1.7.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.7.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.7.3 | Internals |  | 0.078784 | 2.007%
2.1.7.3.1 | PO |  | 0.015757 | 20%
2.1.7.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.7.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.1.7.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.7.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.1.7.6 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.7.7 | Rolling & Forming |  | 0.31385 | 7.996%
2.1.7.8 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.7.9 | Welding |  | 0.51016 | 13%
2.1.7.10 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.7.11 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.7.12 | Weld Repair |  | 0.19631 | 5.002%
2.1.7.13 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.1.7.14 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.7.15 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.1.7.16 | Hardness Check |  | 0.038746 | 0.9872%
2.1.7.17 | NDT After PWHT |  | 0.038746 | 0.9872%
2.1.7.18 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.7.19 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.1.7.20 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.7.21 | Draining & Drying |  | 0.038746 | 0.9872%
2.1.7.22 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.7.23 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.1.8 | Glycol Reflux Condenser (E-100) |  | 3.925 | 12.5%
2.1.8.1 | Raw Material Of Pressure Parts |  | 0.90408 | 23.03%
2.1.8.1.1 | PLATE |  | 0.54245 | 60%
2.1.8.1.1.1 | PO |  | 0.10849 | 20%
2.1.8.1.1.2 | Delivery To Factory |  | 0.16273 | 30%
2.1.8.1.1.3 | Inspection Of Material By TPI |  | 0.27122 | 50%
2.1.8.1.2 | FLANGE |  | 0.27122 | 30%
2.1.8.1.2.1 | PO |  | 0.054245 | 20%
2.1.8.1.2.2 | Delivery To Factory |  | 0.081367 | 30%
2.1.8.1.2.3 | Inspection Of Material By TPI |  | 0.13561 | 50%
2.1.8.1.3 | PIPE |  | 0.090408 | 10%
2.1.8.1.3.1 | PO |  | 0.018082 | 20%
2.1.8.1.3.2 | Delivery To Factory |  | 0.027122 | 30%
2.1.8.1.3.3 | Inspection Of Material By TPI |  | 0.045204 | 50%
2.1.8.2 | Raw Material Of Non-Pressure Parts |  | 0.27768 | 7.075%
2.1.8.2.1 | PLATE |  | 0.24991 | 90%
2.1.8.2.1.1 | PO |  | 0.049983 | 20%
2.1.8.2.1.2 | Delivery To Factory |  | 0.074974 | 30%
2.1.8.2.1.8 | Inspection Of Material By TPI |  | 0.12496 | 50%
2.1.8.2.2 | PROFILE |  | 0.027768 | 10%
2.1.8.2.2.1 | PO |  | 0.0055536 | 20%
2.1.8.2.2.2 | Delivery To Factory |  | 0.0083305 | 30%
2.1.8.2.2.3 | Inspection Of Material By TPI |  | 0.013884 | 50%
2.1.8.3 | Internals |  | 0.078784 | 2.007%
2.1.8.3.1 | PO |  | 0.015757 | 20%
2.1.8.3.2 | Delivery To Factory |  | 0.023635 | 30%
2.1.8.3.3 | Inspection Of Material By TPI |  | 0.039392 | 50%
2.8.1.4 | VT & DT For Raw Material |  | 0.038746 | 0.9872%
2.1.8.5 | Consumable Material (Electrode) |  | 0.038746 | 0.9872%
2.8.1.5 | Cutting & Marking |  | 0.19631 | 5.002%
2.1.8.6 | Rolling & Forming |  | 0.31385 | 7.996%
2.8.1.6 | Weld Preparation and Fit-Up (Shell, Nozzle, …) |  | 0.2751 | 7.009%
2.1.8.7 | Welding |  | 0.51016 | 13%
2.8.1.7 | Ferrite Check For Welding Gladded Parts |  | 0.31385 | 7.996%
2.1.8.8 | NDT (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.8.1.8 | Weld Repair |  | 0.19631 | 5.002%
2.1.8.9 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.15757 | 4.014%
2.8.1.9 | Final Visual and Dimensional |  | 0.11753 | 2.994%
2.1.8.10 | PWHT (If Any) |  | 0.038746 | 0.9872%
2.8.1.10 | Hardness Check |  | 0.038746 | 0.9872%
2.1.8.11 | NDT After PWHT |  | 0.038746 | 0.9872%
2.8.1.11 | Pneumatic Test (Pad Test) |  | 0.038746 | 0.9872%
2.1.8.12 | Hydrostatic Test Water Quality |  | 0.038746 | 0.9872%
2.8.1.12 | Hydrostatic Test |  | 0.038746 | 0.9872%
2.1.8.13 | Draining & Drying |  | 0.038746 | 0.9872%
2.8.1.13 | Abrasive & Paint Material |  | 0.038746 | 0.9872%
2.1.8.14 | Blasting & Painting (EachLayer OFT,Adhesion,Holiday) |  | 0.038746 | 0.9872%
2.2 | Heat Exchangers |  | 7
2.2.1 | E -200 Rich-Lean HE |  | 3.5 | 50%
2.2.1.1 | Raw Material for Pressure parts |  | 1.1455 | 32.73%
2.2.1.1.1 | PLATE |  | 0.68733 | 60%
2.2.1.1.1.1 | PO |  | 0.13747 | 20%
2.2.1.1.1.2 | Delivery To Factory |  | 0.2062 | 30%
2.2.1.1.1.3 | Inspection Of Material By TPI |  | 0.34366 | 50%
2.2.1.1.2 | FLANGE |  | 0.34366 | 30%
2.2.1.1.2.1 | PO |  | 0.068733 | 20%
2.2.1.1.2.2 | Delivery To Factory |  | 0.1031 | 30%
2.2.1.1.2.3 | Inspection Of Material By TPI |  | 0.17183 | 50%
2.2.1.1.3 | PIPE |  | 0.11455 | 10%
2.2.1.1.3.1 | PO |  | 0.022911 | 20%
2.2.1.1.3.2 | Delivery To Factory |  | 0.034366 | 30%
2.2.1.1.3.3 | Inspection Of Material By TPI |  | 0.057277 | 50%
2.2.1.2 | Raw Material for Non-Pressure parts |  | 0.27436 | 7.839%
2.2.1.2.1 | PLATE |  | 0.24693 | 90%
2.2.1.2.1.1 | PO |  | 0.049386 | 20%
2.2.1.2.1.2 | Delivery To Factory |  | 0.074078 | 30%
2.2.1.2.1.3 | Inspection Of Material By TPI |  | 0.12346 | 50%
2.2.1.2.1.2 | PROFILE |  | 0.027436 | 10%
2.2.1.2.1.2.1 | PO |  | 0.0054873 | 20%
2.2.1.2.1.2.2 | Delivery To Factory |  | 0.0082309 | 30%
2.2.1.2.1.2.3 | Inspection Of Material By TPI |  | 0.013718 | 50%
2.2.1.3 | VT & DT For Raw Material |  | 0.037076 | 1.059%
2.2.1.4 | Consumable Material (Electrode) |  | 0.037076 | 1.059%
2.2.1.5 | Cutting & Marking |  | 0.17055 | 4.873%
2.2.1.6 | Rolling & Forming |  | 0.27436 | 7.839%
2.2.1.7 | Tube to Tube Sheet Joint {Expansion) |  | 0.25953 | 7.415%
2.2.1.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, …) |  | 0.3822 | 10.92%
2.2.1.9 | Welding |  | 0.27436 | 7.839%
2.2.1.10 | NDT (VT,MT.PT,UT,RT) |  | 0.07105 | 2.03%
2.2.1.11 | Weld Repair |  | 0.10045 | 2.87%
2.2.1.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.03605 | 1.03%
2.2.1.13 | Final Visual and Dimensional |  | 0.10381 | 2.966%
2.2.1.14 | PWHT (If Any) |  | 0.037076 | 1.059%
2.2.1.15 | Hardness Check |  | 0.037076 | 1.059%
2.2.1.16 | NDT After PWHT |  | 0.037076 | 1.059%
2.2.1.17 | Pneumatic Test (Pad Test) |  | 0.037076 | 1.059%
2.2.1.18 | Hydrostatic Test Water Quality |  | 0.037076 | 1.059%
2.2.1.19 | Hydrostatic Test |  | 0.037076 | 1.059%
2.2.1.20 | Draining & Drying |  | 0.037076 | 1.059%
2.2.1.21 | Abrasive & Paint Material |  | 0.037076 | 1.059%
2.2.1.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) |  | 0.037076 | 1.059%
2.2.2 | E -300 LEAN TEG - DRY GAS EXCH |  | 3.5 | 50%
2.2.2.1 | Raw Material for Pressure parts |  | 1.1455 | 32.73%
2.2.2.1.1 | PLATE |  | 0.68733 | 60%
2.2.2.1.1.1 | PO |  | 0.13747 | 20%
2.2.2.1.1.2 | Delivery To Factory |  | 0.2062 | 30%
2.2.2.1.1.3 | Inspection Of Material By TPI |  | 0.34366 | 50%
2.2.2.1.2 | FLANGE |  | 0.34366 | 30%
2.2.2.1.2.1 | PO |  | 0.068733 | 20%
2.2.2.1.2.2 | Delivery To Factory |  | 0.1031 | 30%
2.2.2.1.2.3 | Inspection Of Material By TPI |  | 0.17183 | 50%
2.2.2.1.3 | PIPE |  | 0.11455 | 10%
2.2.2.1.3.1 | PO |  | 0.022911 | 20%
2.2.2.1.3.2 | Delivery To Factory |  | 0.034366 | 30%
2.2.2.1.3.3 | Inspection Of Material By TPI |  | 0.057277 | 50%
2.2.2.2 | Raw Material for Non-Pressure parts |  | 0.27436 | 7.839%
2.2.2.2.1 | PLATE |  | 0.24693 | 90%
2.2.2.2.1.1 | PO |  | 0.049386 | 20%
2.2.2.2.1.2 | Delivery To Factory |  | 0.074078 | 30%
2.2.2.2.1.3 | Inspection Of Material By TPI |  | 0.12346 | 50%
2.2.2.2.2 | PROFILE |  | 0.027436 | 10%
2.2.2.2.2.1 | PO |  | 0.0054873 | 20%
2.2.2.2.2.2 | Delivery To Factory |  | 0.0082309 | 30%
2.2.2.2.2.3 | Inspection Of Material By TPI |  | 0.013718 | 50%
2.2.2.3 | VT & DT For Raw Material |  | 0.037076 | 1.059%
2.2.2.4 | Consumable Material (Electrode) |  | 0.037076 | 1.059%
2.2.2.5 | Cutting & Marking |  | 0.17055 | 4.873%
2.2.2.6 | Rolling & Forming |  | 0.27436 | 7.839%
2.2.2.7 | Tube to Tube Sheet Joint {Expansion) |  | 0.25953 | 7.415%
2.2.2.8 | Weld Preparation and Fit-Up (Shell,Nozzle,Tubes, Tube Sheet, …) |  | 0.3822 | 10.92%
2.2.2.9 | Welding |  | 0.27436 | 7.839%
2.2.2.10 | NDT (VT,MT.PT,UT,RT) |  | 0.07105 | 2.03%
2.2.2.11 | Weld Repair |  | 0.10045 | 2.87%
2.2.2.12 | NDT After Weld Repair (VT,MT.PT,UT,RT) |  | 0.03605 | 1.03%
2.2.2.13 | Final Visual and Dimensional |  | 0.10381 | 2.966%
2.2.2.14 | PWHT (If Any) |  | 0.037076 | 1.059%
2.2.2.15 | Hardness Check |  | 0.037076 | 1.059%
2.2.2.16 | NDT After PWHT |  | 0.037076 | 1.059%
2.2.2.17 | Pneumatic Test (Pad Test) |  | 0.037076 | 1.059%
2.2.2.18 | Hydrostatic Test Water Quality |  | 0.037076 | 1.059%
2.2.2.19 | Hydrostatic Test |  | 0.037076 | 1.059%
2.2.2.20 | Draining & Drying |  | 0.037076 | 1.059%
2.2.2.21 | Abrasive & Paint Material |  | 0.037076 | 1.059%
2.2.2.22 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) |  | 0.037076 | 1.059%
2.3 | Re-boiler |  | 6
2.3.1 | Raw Material for Pressure parts |  | 2.0706 | 34.51%
2.3.1.1 | PLATE |  | 1.2424 | 60%
2.3.1.1.1 | PO |  | 0.24847 | 20%
2.3.1.1.2 | Delivery To Factory |  | 0.37271 | 30%
2.3.1.1.3 | Inspection Of Material By TPI |  | 0.62118 | 50%
2.3.1.2 | FLANGE |  | 0.62118 | 30%
2.3.1.2.1 | PO |  | 0.12424 | 20%
2.3.1.2.2 | Delivery To Factory |  | 0.18635 | 30%
2.3.1.2.3 | Inspection Of Material By TPI |  | 0.31059 | 50%
2.3.1.3 | PIPE |  | 0.20706 | 10%
2.3.1.3.1 | PO |  | 0.041412 | 20%
2.3.1.3.2 | Delivery To Factory |  | 0.062118 | 30%
2.3.1.3.3 | Inspection Of Material By TPI |  | 0.10353 | 50%
2.3.2 | Raw Material for Non-Pressure parts |  | 0.5166 | 8.61%
2.3.2.1 | PLATE |  | 0.46494 | 90%
2.3.2.1.1 | PO |  | 0.092988 | 20%
2.3.2.1.2 | Delivery To Factory |  | 0.13948 | 30%
2.3.2.1.3 | Inspection Of Material By TPI |  | 0.23247 | 50%
2.3.2.2 | PROFILE |  | 0.05166 | 10%
2.3.2.2.1 | PO |  | 0.010332 | 20%
2.3.2.2.2 | Delivery To Factory |  | 0.015498 | 30%
2.3.2.2.3 | Inspection Of Material By TPI |  | 0.02583 | 50%
2.3.4 | Consumable Material (Electrode) |  | 0.0492 | 0.82%
2.3.5 | Cutting & Marking |  | 0.2952 | 4.92%
2.3.6 | Rolling & Forming |  | 0.5166 | 8.61%
2.3.7 | Weld Preparation and Fit-Up (Shell,Nozzle, ... ) |  | 1.1064 | 18.44%
2.3.8 | Welding |  | 0.5166 | 8.61%
2.3.9 | NDT (VT,MT.PT,UT,RT) |  | 0.099 | 1.65%
2.3.10 | Weld Repair |  | 0.1158 | 1.93%
2.3.11 | NDT After Weld Repair (VT,MT.PT,UT,R T) |  | 0.099 | 1.65%
2.3.12 | Final Visual and Dimensional |  | 0.1722 | 2.87%
2.3.13 | PWHT (If Any) |  | 0.0492 | 0.82%
2.3.14 | Hardness Check |  | 0.0492 | 0.82%
2.3.15 | NDT After PWHT |  | 0.0492 | 0.82%
2.3.16 | Pneumatic Test (Pad Test) |  | 0.0492 | 0.82%
2.3.17 | Hydrostatic Test Water Quality |  | 0.0492 | 0.82%
2.3.18 | Hydrostatic Test |  | 0.0492 | 0.82%
2.3.19 | Draining & Drying |  | 0.0492 | 0.82%
2.3.20 | Abrasive & Paint Material |  | 0.0492 | 0.82%
2.3.21 | Blasting & Painting (Each Layer DFT, Adhesion, Holiday) |  | 0.0492 | 0.82%
2.4 | Field Instruments (Transmitters/ Switch/ Gauge/ Analizer etc.) |  | 5
2.4.1 | PO |  | 1 | 20%
2.4.2 | Visual Dimensional Inspection(Appearance) |  | 0.75 | 15%
2.4.3 | Calibration Check |  | 0.5 | 10%
2.4.4 | Tag & Model No & Specification Check |  | 0.625 | 12.5%
2.4.5 | Review Material, IP,ATEX Certificate |  | 0.625 | 12.5%
2.4.6 | Pressure & Performance Test |  | 1 | 20%
2.4.7 | Packing Inspection& Painting |  | 0.5 | 10%
2.5 | Cable, Wires & Tray |  | 1.45
2.5.1 | Cable & Wires |  | 0.725 | 50%
2.5.1.1 | PO |  | 0.145 | 20%
2.5.1.2 | Visual Inspection |  | 0.29 | 40%
2.5.1.3 | Type Test Sertificate or Manufacturer Catalogue |  | 0.29 | 40%
2.5.2 | Tray |  | 0.725 | 50%
2.5.2.1 | PO |  | 0.145 | 20%
2.5.2.2 | Material Inspection |  | 0.29 | 40%
2.5.2.3 | Visual & Dimensional Inspection |  | 0.29 | 40%
2.6 | Junction Box |  | 2
2.6.1 | PO |  | 0.4 | 20%
2.6.2 | Review IP, ATEX Certificate |  | 0.4 | 20%
2.6.3 | Tag & Model No Check |  | 0.4 | 20%
2.6.4 | Review IP, ATEX certificate |  | 0.4 | 20%
2.6.5 | Packing inspection and painting |  | 0.4 | 20%
2.7 | Local Panel (Outdoor-Hazardous Area) |  | 2
2.7.1 | PO |  | 0.4 | 20%
2.7.2 | Visual Inspection & Dimenslonal Check |  | 0.16667 | 8.333%
2.7.3 | Accessories Tag & Model No Check |  | 0.16667 | 8.333%
2.7.4 | Construction |  | 0.16667 | 8.333%
2.7.5 | Review IP, ATEX Certificate |  | 0.16667 | 8.333%
2.7.6 | Packing Inspection & Painting |  | 0.16667 | 8.333%
2.8 | Control & ESD/BMS Panels (Indoor-Safe Area) |  | 10
2.8.1 | ESD/BMS |  | 5 | 50%
2.8.1.1 | PO |  | 1 | 20%
2.8.1.2 | Visual Inspection & Dimenslonal Check |  | 0.5 | 10%
2.8.1.3 | Tag & Model No Check |  | 0.5 | 10%
2.8.1.4 | Functional & Performance Test |  | 2.5 | 50%
2.8.1.5 | Review IP, ATEX Certificate |  | 0.5 | 10%
2.8.2 | Control System |  | 5 | 50%
2.8.2.1 | PO |  | 1 | 20%
2.8.2.2 | Visual Inspection & Dimenslonal Check |  | 0.5 | 10%
2.8.2.3 | Tag & Model No Check |  | 0.5 | 10%
2.8.2.4 | Functional & Performance Test |  | 2.5 | 50%
2.8.2.5 | Review IP, ATEX Certificate |  | 0.5 | 10%
2.9 | Valves |  | 5.5
2.9.1 | Manual Valves |  | 2.475 | 45%
2.9.1.1 | Manual Valves |  | 2.475 | 100%
2.9.1.1.1 | PO |  | 0.495 | 20%
2.9.1.1.2 | Material Inspection |  | 0.495 | 20%
2.9.1.1.3 | Visual & Dimensional Check |  | 0.495 | 20%
2.9.1.1.4 | Other Required Tests |  | 0.99 | 40%
2.9.2 | Inst.Valves (On/Off, Control & Safety Valves) |  | 3.025 | 55%
2.9.2.1 | PSV |  | 1.0083 | 33.33%
2.9.2.1.1 | PO |  | 0.20167 | 20%
2.9.2.1.2 | Material Inspection |  | 0.10083 | 10%
2.9.2.1.3 | Visual and Dimensional Inspection |  | 0.10083 | 10%
2.9.2.1.4 | Construction |  | 0.10083 | 10%
2.9.2.1.5 | Accessory |  | 0.10083 | 10%
2.9.2.1.6 | Pressure Test |  | 0.10083 | 10%
2.9.2.1.7 | Calibration |  | 0.10083 | 10%
2.9.2.1.8 | Performance Test |  | 0.15125 | 15%
2.9.2.2 | On/Off Valve |  | 1.0082 | 33.33%
2.9.2.2.1 | PO |  | 0.20167 | 20%
2.9.2.2.2 | Material Inspection |  | 0.10083 | 10%
2.9.2.2.3 | Visual and Dimensional Inspection |  | 0.10083 | 10%
2.9.2.2.4 | Construction |  | 0.10083 | 10%
2.9.2.2.5 | Accessory |  | 0.10083 | 10%
2.9.2.2.6 | Pressure Test |  | 0.10083 | 10%
2.9.2.2.7 | Calibration |  | 0.10083 | 10%
2.9.2.2.8 | Performance Test |  | 0.15125 | 15%
2.9.2.3 | Control Valve |  | 1.0082 | 33.33%
2.9.2.3.1 | PO |  | 0.20167 | 20%
2.9.2.3.2 | Material Inspection |  | 0.10083 | 10%
2.9.2.3.3 | Visual and Dimensional Inspection |  | 0.10083 | 10%
2.9.2.3.4 | Construction |  | 0.10083 | 10%
2.9.2.3.5 | Accessory |  | 0.10083 | 10%
2.9.2.3.6 | Pressure Test |  | 0.10083 | 10%
2.9.2.3.7 | Calibration |  | 0.10083 | 10%
2.9.2.3.8 | Performance Test |  | 0.15125 | 15%
2.1 | Strainers |  | 1
2.10.1 | PO |  | 0.2 | 20%
2.10.2 | Material Inspection |  | 0.2 | 20%
2.10.3 | Visual and Dimensional Inspection |  | 0.3 | 30%
2.10.4 | Hydro Test |  | 0.3 | 30%
2.11 | Piping Items (Pipe, Flange, Fitting, Gasket, Bolt & Nuts) |  | 1.5
2.11.1 | Pipe |  | 0.375 | 25%
2.11.1 | PO |  | 0.075 | 20%
2.11.2 | Delivery To Factory |  | 0.1125 | 30%
2.11.3 | Inspection Of Material By TPI |  | 0.03125 | 8.333%
2.11.6 | Visual and Dimensional Inspection |  | 0.03125 | 8.333%
2.11.7 | Weld Preparation and Fit-Up |  | 0.03125 | 8.333%
2.11.8 | Welding |  | 0.03125 | 8.333%
2.11.9 | NDT( VT, MT, PT, UT, RT) |  | 0.03125 | 8.333%
2.11.10 | Hydrostatic Test |  | 0.03125 | 8.333%
2.11.2 | Flange |  | 0.375 | 25%
2.11.2.1 | PO |  | 0.075 | 20%
2.11.2.2 | Delivery To Factory |  | 0.1125 | 30%
2.11.2.3 | Inspection Of Material By TPI |  | 0.03125 | 8.333%
2.11.2.4 | Visual and Dimensional Inspection |  | 0.03125 | 8.333%
2.11.2.5 | Weld Preparation and Fit-Up |  | 0.03125 | 8.333%
2.11.2.6 | Welding |  | 0.03125 | 8.333%
2.11.2.7 | NDT( VT, MT, PT, UT, RT) |  | 0.03125 | 8.333%
2.11.2.8 | Hydrostatic Test |  | 0.03125 | 8.333%
2.11.3 | Fitting |  | 0.3 | 20%
2.11.3.1 | PO |  | 0.06 | 20%
2.11.3.2 | Delivery To Factory |  | 0.09 | 30%
2.11.3.3 | Inspection Of Material By TPI |  | 0.025 | 8.333%
2.11.3.4 | Visual and Dimensional Inspection |  | 0.025 | 8.333%
2.11.3.5 | Weld Preparation and Fit-Up |  | 0.025 | 8.333%
2.11.3.6 | Welding |  | 0.025 | 8.333%
2.11.3.7 | NDT( VT, MT, PT, UT, RT) |  | 0.025 | 8.333%
2.11.3.8 | Hydrostatic Test |  | 0.025 | 8.333%
2.11.4 | Gasket |  | 0.225 | 15%
2.11.4.1 | PO |  | 0.045 | 20%
2.11.4.2 | Delivery To Factory |  | 0.0675 | 30%
2.11.4.3 | Inspection Of Material By TPI |  | 0.01875 | 8.333%
2.11.4.4 | Visual and Dimensional Inspection |  | 0.01875 | 8.333%
2.11.4.5 | Weld Preparation and Fit-Up |  | 0.01875 | 8.333%
2.11.4.6 | Welding |  | 0.01875 | 8.333%
2.11.4.7 | NDT( VT, MT, PT, UT, RT) |  | 0.01875 | 8.333%
2.11.4.8 | Hydrostatic Test |  | 0.01875 | 8.333%
2.11.5 | Bolt & Nuts |  | 0.225 | 15%
2.11.5.1 | PO |  | 0.045 | 20%
2.11.5.2 | Delivery To Factory |  | 0.0675 | 30%
2.11.5.3 | Inspection Of Material By TPI |  | 0.01875 | 8.333%
2.11.5.4 | Visual and Dimensional Inspection |  | 0.01875 | 8.333%
2.11.5.5 | Weld Preparation and Fit-Up |  | 0.01875 | 8.333%
2.11.5.6 | Welding |  | 0.01875 | 8.333%
2.11.5.7 | NDT( VT, MT, PT, UT, RT) |  | 0.01875 | 8.333%
2.11.5.8 | Hydrostatic Test |  | 0.01875 | 8.333%
2.12 | Pump |  | 2
2.12.1 | PO |  | 0.4 | 20%
2.12.2 | Inspection Of Material By TPI |  | 0.4 | 20%
2.12.3 | Final Visual and Dimensional Inspection |  | 0.4 | 20%
2.12.4 | Performance test |  | 0.8 | 40%
2.13 | Ladder & Platform (Package Structure) |  | 5
2.13.1 | Visual and Dimensional Check After Welding |  | 5 | 100%
2.14 | Chemical Injection Package |  | 2
2.14.1 | Raw Material for Tank |  | 0.69427 | 34.71%
2.14.2 | Final Inspection For Fabricated Tank |  | 0.10191 | 5.096%
2.14.3 | Piping & Structure Works |  | 0.79618 | 39.81%
2.14.4 | Performance test |  | 0.10191 | 5.096%
2.14.5 | Packing Inspection |  | 0.10191 | 5.096%
2.14.6 | IRN |  | 0.10191 | 5.096%
2.14.7 | Final Book |  | 0.10191 | 5.096%
2.15 | Reboiler Burner |  | 2
2.15.1 | PO |  | 0.4 | 20%
2.15.2 | Final Visual and Dimensional Inspection |  | 0.8 | 40%
2.15.3 | Burner Test |  | 0.8 | 40%
2.16 | Painting of Package Assembly (Piping, Structure) |  | 0.05
2.16.1 | Abrasive & Paint Material |  | 0.025 | 50%
2.16.2 | Blasting & Painting (Each Layer DFT, Adhesion) |  | 0.025 | 50%
2.17 | Pickling (For Stainless Steel Part) |  | 0.05
2.17.1 | Pickling and Passivation |  | 0.05 | 100%
2.18 | Preservation |  | 0.05
2.18.1 | N2 Purge /Silica |  | 0.05 | 100%
3 | PACKING |  | 1
3.1 | Packing Inspection |  | 1 | 100%
4 | IRN |  | 1
4.1 | Release Note |  | 1 | 100%
5 | FINAL DATA BOOK |  | 5
5.1 | Final Document Preparation |  | 5 | 100%
6 | IC |  | 1
6.1 | Inspection Certificate |  | 1 | 100%
7 | SAT |  | 1
7.1 | SAT |  | 1 | 100%