## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PR-DS-0003 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: PROCESS DATA SHEET FOR GLYCOL PARTICLE FILTER |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-MF-0010 |  |  | Transmital Date: 2024/12/04
[5 empty] | CRS No: CRS-BK-GCS-MF-120-PR-DS-0003-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به در دسترس نبودن فایل شبیه سازی بسته نم زدا و همچنین عدم ارائه مدارک Sizing تجهیزات، امکان صحه گذاری داده های مندرج در مدرک دیتاشیت فراهم نمی باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای فنی و مالی-قراردادی پیمانکار و سازنده، مسئولیت گارانتی فرآیندی و مکانیکی بسته نم زدا و همچنین بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار و سازنده، اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار می باشد. |  | BK-SUR-ENG-MEC-03-09352 | 2024-06-09 | مورد تایید است.
2 | نظرات ذینفع اصلی پروژه، متعاقبا ارسال گردد. |  | BK-SUR-ENG-MEC-03-09352 | 2024-06-09 | نظر ذینفع اصلی بررسی و پاسخ داده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 09/06/2024 |  |  |  |  | Date: