## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PR-DB-0001 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: BASIS OF PROCESS DESIGN FOR GAS DEHYDRATION PACKAGE |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-MF-0020 |  |  | Transmital Date: 2025/03/09
[5 empty] | CRS No: PEDCO- CRS-BK-GCS-MF-120-PR-DB-0001-V02 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عناوین ذکر شده برای جداول شماره 1-1 و 3-6 و همچنین شماره گذاری تمامی جداول بازبینی گردد. |  |  | 2025-01-07 | با توجه به جلسه جمع بندی نظرات مربوطه (مورخ 1403/08/06) با خریدار و ذینفعان پروژه، اطلاحات مقتضی اعمال گردید.
2 | در بخش Overdesign margin/Holdup Time برای Reboiler مطابق بخش 4.5.2 مدرک Design Criteria پروژه 5% of feed bottom exchange duty نیز بررسی و هرکدام بزرگتر بود به عنوان Overdesign لحاظ گردد. |  |  | 2025-01-07
3 | در بخش Overdesign margin/Holdup Time برای زمان هلدآپ تجهیزات عبارت LSL به Low liquid level تغییر یابد. همچنین زمان هلدآپ برای Surge drum توضیحاتRev قبل مورد تایید بوده و 20 دقیقه برای فاصله سطح Normal تا Low لحاظ گردد. |  |  | 2025-01-07
4 | عبارت Excluded from MFS scope درخصوص Air Blower در بخش 5.7.12 حذف گردد. |  |  | 2025-01-07
5 | توضیحات درخصوص سیستم Anti foam و PH control نیز به مدرک اضافه گردد. |  |  | 2025-01-07
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: 07/01/2025 |  |  |  |  | Date: