## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PR-PF-0001 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-MF-0020 |  |  | Transmital Date: 2025/03/09
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-PR-PF-0001-V03 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد 2، 3 و 4 در Comment Sheet قبلی به قرار زیر همچنان مدنظر است که میبایست تصحیح گردد. |  |  | 2025-01-07 | با توجه به جلسه جمع بندی نظرات مربوطه (مورخ 1403/08/06) با خریدار و ذینفعان پروژه، اطلاحات مقتضی اعمال گردید.
2 | دماهای ورودی و خروجی برای مبدلها در بخش description بازنگری گردد. |  |  | 2025-01-07
3 | اختلاف فشار ذکر شده برای پمپ در بخش description بازنگری گردد. |  |  | 2025-01-07
4 | روی جریان make-up گلایکول Note-5 ذکر گردد. |  |  | 2025-01-07
5 | شماره گذاری تجهیزات میبایست بر اساس روال نامگذاری تجهیزات در پروژه صورت پذیرد. |  |  | 2025-01-07
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: | Signature
| Date:07/01/2025 |  |  |  |  | Date: