## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-PR-PF-0002 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: HEAT AND MASS BALANCE FOR GAS DEHYDRATION PACKAGE |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-MF-0020 |  |  | Transmital Date: 2025/03/09
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-PR-PF-0002-V03 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نام گذاری فازها (Gas, Liquid, Water) همچون فایل Excel ارسالی، ذکر گردد. |  |  | 2025-01-07 | با توجه به جلسه جمع بندی نظرات مربوطه (مورخ 1403/08/06) با خریدار و ذینفعان پروژه، اطلاحات مقتضی اعمال گردید.
5 | دمای دو جریان خروجی شماره 7 و 15 به سمت flare بیشتر از ماکزیمم دمای عملیاتی شبکه flare ( 60C ) می باشد. با توجه به پیوسته بودن این جریان، دمای طراحی شبکه فلر می بایست اصلاح گردد. این مورد در نبد 48 صورتجلسه بررسی مدارک PFD و P&ID نیز درج شده است. (شرکت هیرگان انرژی) |  |  | 2025-01-07
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: | Signature
| Date:07/01/2025 |  |  |  |  | Date: