## Sheet1
COMMENT REPLY SHEET
Document No:BK-GCS-MF-120-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-SVTR-MF-0013 |  |  | Transmital Date:2025/01/05 | :2025/01/2025
Document Title: PROCESS FLOW DIAGRAM FOR GAS DEHYDRATION PACKAGE |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: NISOC-CRS-BK-GCS-MF-120-PR-PF-0001_V02 |  |  | CRS Status: CM | CM
| Comments (NISOC) |  | Email/letter No. | Comment Date | Clarification (By Vendor)
QC comments :
1 |  |  | 03/2294/313406 | 1403/8/12 | تمامی کامنت ها در مدرک به نحو مقتضی اعمال گردید.
2 |  |  | MOM | 1403/08/06 | به نحو مقتضی اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT |  |  |  |  | VENDOR
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | DATE: