## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-MF-120-ME-CN-0005_V00 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-MF-0019 |  |  | Transmital Date: 2025/03/25
Document Title: MECHANICAL CALCULATION BOOK FOR GLYCOL CARBON FILTER (F-200) |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-MF-120-ME-CN-0005_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the attached comments. |  | BK-SUR-ENG-MEC-03-09955 | 2025-01-19 | 1-Wind and Seismic parameters has been revised. 2-All materials are normalized and is noted in GA drawing and this feature is not shown for material description in PV Elite Report. 3-TL to TL is from S.F. of bottom head to face of Upper Body Flange (not blind) and has been revised in GA drawing. in PV Elite calculation has been reported from S.F. of bottom head to outer of blind.
2 | کلیه نقطه نظرات بر روی Data Sheet ها میبایست بر روی مدارک اعمال گردد. |  | BK-SUR-ENG-MEC-03-09955 | 2025-01-19 | Confirmed.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 01/19/2025 |  |  |  |  | Date: